# REPORT TO ENVIRONMENTAL SCRUTINY COMMITTEE	PART 1

19 MAY 2003

____________________________________________________________

BEST VALUE REVIEW OF PROPERTY PHASE 1 AND PHASE II

IMPLEMENTATION PROGRESS REPORT

____________________________________________________________

1.0	RECOMMENDATIONS

1.1	Members are recommended to note the progress made in implementing 	the Phase One and Phase Two Best Value Reviews of Property.

2.0	EXECUTIVE SUMMARY

This report and attached appendices set out progress made in implementing the Phase I and Phase II Best Value Reviews of Property.

It concludes that: -

In respect of the Phase I Review, with the exception of establishing satellite offices good progress has been made against the 41-point Implementation Plan.

As previously reported the main area where progress is behind schedule is in establishing satellite offices.  However progress is being made in establishing a satellite office (and other facilities) at Ordsall Neighbourhood Office and opportunities presented by the LIFT Project are being pursued.

In respect of the Phase 2 review good progress has been made against the 46 point Implementation Plan with 12 action points being completed and a further 9 forming part of an annual process that demonstrates that Best Value processes are now being embedded as normal working practice.

Significant progress has been made on a further 24 action points, although some further detailed attention is required on a number of items in order to move towards completion.

The one remaining action point has been deferred pending the outcome of the proposed JV partnership.

- BACKGROUND DOCUMENTS

Phase I Best Value Review of Property.

Phase II Best Value Review of Property.

.

Report to Environmental Scrutiny Committee 18th November 2002.

- CONTACT OFFICER

## Steven Durbar 793 – 3755 Phase I.

## Peter Openshaw 793 – 3714 Phase II.

5.0	WARDS TO WHICH REPORT RELATES – ALL WARDS

6.0	KEY COUNCIL POLICIES: BEST VALUE

7.0	PURPOSE OF REPORT

This report reviews progress being made in implementing the Implementation Plan for the Phase I and Phase II Reviews.

- BACKGROUND

The Phase I Property Best Value Review considered office support accommodation and strategic property management.  Its findings were reported to Cabinet and Council in September 2000.

The Best Value Inspectorate found that the service was fair and would probably improve.

The Phase II Review considered the Council’s Property Service.  Its findings were reported to Cabinet and Council in March/April 2002.

The Review is available for Best Value inspection, but no date has been set for the inspection.

- CURRENT SITUATION

Progress on implementing the Phase I and Phase II Reviews is noted against the Implementation Plans shown in Appendix I and Appendix 2.  The current position and actions needed are shown in the last column of the Plans.

- CONCLUSION

PHASE 1 REVIEW

10.1	Whilst substantial progress has been made with the Phase I Review, this progress has not been sufficient to meet all the targets set out in the Implementation Plan.

  - The principal deficiency as previously reported is in the introduction of satellite offices. Progress is being made in developing Ordsall Neighbourhood Office where works providing revised office accommodation for various directorates and the library should be completed in July 03. Opportunities for accommodation in the LIFT Project have been pursued but are likely to be limited to different permutations of One Stop Shop, Library and Social Services accommodation depending on the location.

It should be noted that New Prospect Housing Ltd have reviewed the area housing office provision and rationalisation is taking place.

  - The introduction of home-working and hot -desking was identified in the review, as a potential contributor to reducing office space needs.  However home-working and hot-desking has had a very limited impact at this stage and it is unlikely to have any significant impact within the three-year plan period.

  - With regard to the remaining 31 detailed actions within the Implementation Plan 18 actions have been completed and 13 actions are now part of an annual process, which shows that best Value processes are now being embedded as normal working practices.

  - It should also be noted that the three-year Implementation Plan expires in September this year.

It is then proposed that a report will be brought to this committee 	outlining the key achievements in rationalising the office portfolio, 	reviewing the office accommodation strategy and setting out a 	revised 	action plan and strategy to take matters forward.

PHASE 2 REVIEW

  - Good progress has been made over the last six months. Of the 46 specific action points 21 have either been completed or are embedded in annual processes.

Significant progress has been made against a further 24 action points. The one remaining action point has been deferred pending the outcome of the proposed Joint Venture partnership.

Key items to be achieved within the Implementation Plan are: -

    - The reduction of rental arrears.

    - The reduction in the number of buildings with major access problems for the disabled.

    - The improvement in condition of operational and non operational properties

    - Seeking improvements in the performance of the commercial estate

    - The reduction in the number of facility management provider

Directorates

    - The reduction in the running cost of operational buildings

    - The improvement in the levels of client satisfaction in respect of our services

We would also highlight action point 19 where we have exceeded 	demanding target figures in respect of capital receipts, acquisitions and 	rental income.

These targets are key items for the city council and make a significant contribution towards the future regeneration of the city.

### MALCOLM SYKES

DIRECTOR OF DEVELOPMENT SERVICES

# BEST VALUE REVIEW OF OFFICE SUPPORT ACCOMMODATION

# AND STRATEGIC PROPERTY MANAGEMENT

# PHASE 1 IMPLEMENTATION PLAN

# ADOPTION OF A STRATEGIC APPROACH TO PROPERTY

| Item | Objective | Action | Timescale | Responsible Officer | POSITION Reported Nov 02 | POSITION Apr 03 |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Confirmation of Policy by the Council and Directorates | Incorporate property Objectives into the: Strategic plans Service Plans | April 2001 | BV & PT Directors | Completed Being raised with Directorates for 2003/04 service plans | Inclusion now part of annual process of updating Strat & BV Perf Plan Service Plans will be reviewed to check inclusion Completed - question now included in manual |
| 2 |  | Include property questions in Best Value Review Manual | April 2001 | BV & PT | Questions will be included when manual revised following outcomes of BV process & Peer Group reviews |  |
| 3 | Directorates to Recognise and Support the Role of the SPMU | Produce and send out leaflet/ Intranet/ explaining the role of the SPMU | April 2001 | SPMU | Completed | Completed |
| 4 | Adopt a corporate approach to home working/hot desking | Produce a report to Cabinet | June 2001 | Director of Personnel and Performance | No large-scale introduction at this stage Is being applied on a small scale in specific areas. No report to Directors or Cabinet at this stage. | Reported to Directors Team and Scrutiny Ctte. being applied on a small scale in specific areas. Will be promoted through office accommodation moves |
| 5 |  | Communicate the policy to all staff | August 2001 | Director of Personnel and Performance |  |  |
| 6 | Pursue the sharing of properties with other bodies | Hold discussions with Health Authorities. Post Office, Benefits agency, Police | Commenced. Meeting held 2 Feb 01. Work on-going. | Chief Executive Director of Corporate Services | LIFT Project being progressed rapidly by Corp Proj Team | LIFT Project being progressed rapidly by Corp Proj Team |
| 7 |  | Feed results into AMP process | Commenced. Work on going | SPMU | AMP refers to LIFT Project | Completed |
| 8 | Establish financial Incentives to reduce Office space | Report to Scrutiny Committee | March 2001 | Head of Finance | Completed for 02. Review in no longer than 6 months | Review undertaken recommendation that incentives not be introduced |
|  |  | Implement the financial incentives | By April 2002 | Head of Finance |  |  |
| 9 | Align the budgets for property with responsibility | SPMU to liase with City Treasurer in a series of meetings to progress | To commence April 2001 | SPMU | Review situation at end of 02/03 in light of action 9a below. | Review relevance of this objective required |
| 9a | Ensure property costs accurately reflected in service budgets | SPMU to liase with Treasurers in a series of meetings to progress | To commence Sept 2001 | SPMU | Cost centres still to be established for some buildings | Completed Cost centres established as far as appropriate. |

## IMPLEMENTATION PLAN

Securing the Effective Operation of the Strategic Property Management Unit to Support Office Space Reduction

| Item | Objective | Action | Timescale | Responsible Officer | POSITION Reported Nov 02 | POSITION Apr 03 |
| --- | --- | --- | --- | --- | --- | --- |
| 10 | Establishment of the Strategic Property Management Unit | Appoint staff | October 2000 | Director of Development Services | Completed | Completed |
| 11 |  | Confirm role and remit | February 2001 | SPMU | Completed | Completed |
| 12 |  | Consideration of appropriate resources for the SPMU | February 2001 | Director of Development Services | Review due Oct 02 | Completed (Review Oct 03) |
| 13 |  | Confirm arrangements to other officers and teams | March 2001 | SPMU | Completed | Completed |
| 14 | Promote the consideration of strategic property issues | SPMU to liase with appropriate directorates in formulating a property strategy relative to other corporate initiatives eg. Homeworking, hot desking, sharing property with others, financial incentives. | Ongoing to commence February 2001 | SPMU | Programme of issues being considered by AMG | Programme of issues being considered by AMG |
| 15 |  | Report to Directors on homeworking | July 2001 | Director of Personnel and Performance | No report at this stage | Completed |
| 16 |  | Report to Cabinet on homeworking | August 2001 | Director of Personnel and Performance | No report at this stage . | Completed – no report proposed |
| 17 | Improve customer focus of the SPMU | Discussion with all directorates, understanding their objectives | Ongoing to commence February 2001 | SPMU | The 03 round of work to commence in Oct / Nov | Ongoing in part through Service Property Strategy development work |
| 18 |  | Develop use and analyse customer surveys | September 2001 | SPMU | Data for 02 to be collected | Completed |
| 19 | Promote improvement and Efficiency | Set property performance targets | February 2001 reviewed each year | All Directors in liaison with SPMU | Completed | Now part of annual process |
| 20 |  | Apply benchmarking information / internal performance information and trends to improve the property service and the performance of property. | Ongoing, commenced February 2001 | SPMU | Improvement to be achieved through actions set out in BV Imp Plan | Improvement to be achieved through actions set out in BV Imp Plan |
| 21 |  | Targets and performance reported to Scrutiny Committee | December each year | SPMU | Completed | Now part of annual process of reporting to Scrutiny Ctte in July |
| 21a |  | Performance reported to public | T.B.A. | BV & PT | Completed | Now part of annual process of producing Strategic and BV Performance Plan and the Summary Plan issued to all Salford residents & businesses |

### IMPLEMENTATION PLAN

# Implementing Office Space Reduction

| Item | Objective | Action | Timescale | Responsible Officer | POSITION Reported Nov 02 | POSITION Apr 03 |
| --- | --- | --- | --- | --- | --- | --- |
| 22 | Establish current performance of office space to compare with baseline information to monitor improvement | Collect current years performance data from the SAP system | April 2001 | SPMU | Report submitted in July. Further reports will be submitted in accordance with annual programme | Now part of annual process of reporting to Scrutiny Ctte in July |
| 22a |  | Collect current years other performance data from various sources | Nov 2001 | SPMU |  |  |
| 23 | Bring into operation the financial incentives to reduce office space | Directors informed of budget adjustments | For each financial year | Head of Finance | Completed - further review no later than March 03 | Review undertaken recommendation that incentives not be introduced |
| 24 | To obtain financial allocation to fund moves | To submit bid for capital allocation in Councils capital programme | Completed December 2000 | SPMU | Completed | Completed Allocation obtained for 03/04 |
| 25 | To reduce the amount of office space used for storage purposes | Undertake storage review | Completed January 2001 | Director of Personnel and Performance | Report considered by AMG Short Term-reduce amount of stored material Long Term-investigate electronic “paperless” approach | Short Term-reduce amount of stored material Long Term-investigate electronic “paperless” approach |
| 26 |  | Prepare a costed options report on alternative storage options | July 2001 | Director of Personnel and Performance |  |  |
| 27 | To ensure that the implementation plan takes account of measures which will reduce demand for office space | To drive the implementation of the home working policy | Ongoing to commence June 2001 | Director of Personnel and Performance | Successful pilot in Revenues & Benefits. Being considered for expansion. | Small scale introduction progressing |
| 28 |  | Monitor and report implementation of policy and extrapolate impact on property requirement | Report December each year | SPMU liasing with Personnel |  |  |
| 29 | Move towards 4 core sites | Establish delivery teams | Delivery team for 4th core site established and will form basis of the team to deliver the other core site moves | Director of Development Services and Corporate Services | Completed | Completed |
| 30 |  | Confirm suitability of Civic/Crompton/Turnpike as core sites | May 2001 | SPMU in consultation with Appropriate Directors | Completed | Completed |
| 31 32 |  | Undertake Staff/union consultation on 4th core site Confirm the 4th core site | Ongoing, commenced September 2000 February 2001 | Director of Personnel And Performance Directors of Education and Development Services in consultation with the SPMU and delivery team | Completed . Completed | Completed |
| 33 |  | Move to core accommodation | May 2001 - September 2003 | Director of Development Services | Completed Further small moves ongoing | Completed |
| 34 | Establish satellite offices | Establish delivery teams | Delivery team to be established for the pilot offices, | Director of Development Services and Corporate Services | Completed | Note. Revised approach being adopted as reported to and approved by Scrutiny Ctte Jan 03 Rationalisation & change being progressed. Above report identified 7 bldgs targeted for disposal or being sold |
| 35 |  | Identify 3 pilot areas | March 2001 | SPMU and Director of Corporate Services | 3rd pilot to be identified |  |
| 36 |  | Undertake Staff/union consultation | March 2001 | Director of Personnel and Performance | To take place when required. Small scale issues to be dealt with by outstationed Personnel. |  |
| 36a 37 |  | Undertake public consultation Identify 3 satellite office buildings | To be arranged July 2001 | Delivery team Delivery team | Ongoing |  |
|  |  |  |  |  | 3rd building to be identified |  |
| 38 |  | Move to 3 satellite office buildings | October 2001 - May 2002 | Director of Development Services and delivery team | Ordsall proposals being progressed. Walkden proposals dependent on LIFT | See Items 34 to 37 |
| 39 |  | Identify remaining satellite offices and move | January 2002 - September 2003 | Director of Development Services and delivery team | Action needed |  |
| 40 | To raise capital | Sell Surplus properties | November 2001- December 2003 | Director of Development Services | Ongoing | Ongoing N.B. Change of policy from disposal for single capital sum to leasehold disposal at a rental in appropriate circumstances |
| 41 | Ensure improvement is achieved | Monitoring progress against targets and reporting to Scrutiny and budget Committee | Reports December each year | SPMU | Completed | Now part of annual process |

BEST VALUE REVIEW OF PROPERTY SERVICES

PHASE II IMPLEMENTATION PLAN

| ITEM | OBJECTIVE | ACTION | TIMESCALE | RESPONSIBLE OFFICER | POSITION NOV 2002 | POSITION REPORTED APRIL 03 |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | To improve the condition and suitability of property. | Prioritise maintenance expenditure taking account of user and councillor consultation. | Apr 02 – Mar 03 Annual acivity | J. Dooley | Completed. Ongoing through year | The maintenance priorities for 03/04 have been established and will be implemented throughout 03/04 |
| 2. | To improve the condition and suitability of property. | Liaison with tenants re:- security improvements. | Sept 02 – Oct 02 | P. Smith B. Burns | Draft leaflet prepared and is being reviewed prior to circulation | Completed A letter and supporting leaflet sent out with March 03 rent invoices |
| 3. | To improve the condition and suitability of property. | Re-introduce Empty Premises procedure. | June 02 – Oct 02 | P. Smith D. Hoy | Completed. | Completed |
| 4. | To improve the condition and suitability of property. | Review level of maintenance funding. | July 02 – Oct 02 | S. Durbar | Report submitted to Directors Team July 18th pointing out more money required to address backlog Maintenance. Bid submitted for £300k p.a. over each of next 3 years in capital programme. Report with further info to go to Lead Member. Receipts/Repairs need to be pursued. | Complete at this time No additional funding allocated Information provided to Lead Member. Joint Venture partnership may provide opportunity to re visit this issue. |
| 5. | To improve the condition and suitability of property. | Liaison with AHO’s re maintenance around shops. | May 02 – Mar 04 | Estates Surveyors | Awaiting decisions from Housing Services on the Shops Review report and final inclusion/exclusion of Shops from ALMO | Position as Nov 02 Shops excluded from ALMO |
| 6. | To improve the condition and suitability of property. | Access Officer liaison with maintenance staff prioritising Disabled access improvements to buildings with greatest need. | May 02 – Mar 03 Annually thereafter. | J. Dooley | Waiting for list of priorities from Disabled Access Officer before programming works | Agreed programme of works 02/03 completed (Civic/Crompton Hse) priorities for 03/04 agreed. Work programme to be submitted to Lead Member for approval May 03 |
| 7. | To improve the condition and suitability of property. | Reduce amount of property owned and occupied by the Council. | Continuing programme of work. | P. Openshaw | In addition to the sale of surplus assets to generate Capital Receipts reductions in ownership will be achieved through reviews for example of training, space at the Civic/Swinton Hall Depot and Walkden TC. | A report is to be presented to Directors Team on 17 Apr regarding the possible acquisition of additional core site accommodation. This will enable some satellite property to be disposed of |
| 8. | To improve the condition and suitability of property. | Re-grade pedestrian access and provide new entrance doors to Civic Centre. |  | J. Dooley | Completed. | Completed |
| 9. | To improve the condition and suitability of property. | Holding internal building user Focus Group to discuss consultation findings. | Annual activity | J. Dooley | Completed. | 03/04 maintenance budget discussions held with client directorates |
| 10. | To provide a high quality service responsive to client needs. | Working with Building Control to speed up demolition of redundant buildings. | May 02 – July 02 | Case Officers | QA procedure for demolition process prepared. Internal procedures agreed with Building Control and Estates providing some assistance with service disconnections. Assisting Building Control to select a demolition partner or range of demolition partners. | Performance much improved. Regular update reports on progress considered at Dev Services TCG meetings Performance will be monitored to assess appropriateness for further improvements. |
| 11. | To provide a high quality service responsive to client needs. | Create better communications between subscribers and Quaywatch personnel regarding service improvements by providing “key contact” card and website Improving the billing process | Aug 02 – Oct 02 | B. Burns/ P. Openshaw | Work underway. Completed – Billing procedure now on time. | Chameleon Designs appointed to assist with Quaywatch marketing. CD ROM produced to promoted Quaywatch. To be circulated to prospective customers and added to website June 03 |
| 12. | To provide a high quality service responsive to client needs. | Improve liaison with clients on property maintenance issues prior to works. | April 02 Annual activity | J. Dooley | Ongoing discussions with all clients as part of 2002/03 Maintenance Programme | Liaison with all client directorates undertaken in respect of setting the 03/04 works priorities. Ongoing discussions throughout year in relation to implementation of works. |
| 13. | To provide a high quality service responsive to client needs. | Improved liaison with Housing re estate improvement and implications for shops portfolio. | July 02 – Mar 05 | P. Openshaw R. Osborne | Shops report completed and awaiting Housing input. Implementation of actions to follow once Lead Member approval obtained. | Position as at Nov 02 |
| 14. | To provide a high quality service responsive to client needs. | Improving provision of timely advice. | Ongoing. | All | Ongoing through year. Review of current arrangements required. Annual Survey required prior to December 2002 | Ongoing through year. Annual survey sent out awaiting return prior to analysis |
| 15. | To provide a high quality service responsive to client needs. | Hold regular meetings with internal customers to seek feedback. | Apr 02 Ongoing. | Service Manager | Regular meetings held with Housing, Education and Corporate Services. Requires Review. Meetings with other Directorates to be organised by December 2002 | In addition to Nov 02 meetings further meetings now take place with Environmental Services on an as and when required basis AMG meeting s now provide the forum for discussion on all property issues between directorates |
| 16. | To provide a high quality service responsive to client needs. | Establishment of a Strategic Property Management Unit with endorsement of client satisfaction. | Unit established. Annual satisfaction survey. | R. Wynne S. Durbar | Completed. 2002 survey to be undertaken. | Maintenance service survey completed Other annual surveys sent out – awaiting return prior to analysis |
| 17. | To provide a cost effective Property Service. | Purchase SAP property module or other alternative. | July 02 – Oct 03 | P. Openshaw | Selection of a suitable system should be made December 2002. Implementation by October 2003 subject to allocation of Resources | No suitable system was identified to better the current in-house system. The in-house system is to be further developed pending other systems being considered. |
| 18. | To provide a cost effective Property Service. | Increase levels of delegation particularly for Housing Directorate and building work tenders. | May 02 – July 02 | P. Openshaw E. Wilson | Housing Lead Member considered the issue of delegation at meeting on 4/10/02. Cabinet endorsement of proposal now being sought. Suggested increase to financial limits to Corporate Services. Council at its meeting in May did not approve any amendments to the current scheme. | Complete as at this time Approval obtained as per Nov 02 update, but not implemented due to delay in Cabinet approval. No further action on financial limit change. |
| 19. | To provide a cost effective Property Service. | Improve staff appraisal and emphasise target setting. | Oct 02 – Jan 03 | R. Wynne and Appraisors | Clear target setting in the area of Capital Receipts and acquisitions needs to be applied to other areas. | 02/03 targets in respect of capital receipts, rental income and expenditure were exceeded. Application to other areas required. |
| 20. | To provide a cost effective Property Service. | Market test lease renewals acquisitions and disposals. | Sept 02– Feb 03 | P. Openshaw P. Smith | Advert being prepared. Appropriate placing of advert to target suitable contractors being considered. | Core Cities information on market testing these areas has been obtained. Currently being analyzed to asses next steps |
| 21. | To provide a cost effective Property Service. | Property Management to establish closer working with Chief Execs Strategy Unit regarding bids to finance building improvements. | Aug 02 – Nov 02 | E. Wilson | Complete. Discussions held with Strategy Unit. Unlikely there are any current schemes available that we as a Local Authority could bid for. Unable to take any further unless there are changes to existing schemes to allow Local Authority bids to be considered. | Complete Estate working closely with EDU and EDU Best Value Review Team |
| 22. | To provide a cost effective Property Service. | FM provider to be responsible for Civic Centre reception. | Sept 02–Nov 02 | E. Wilson/D. Hoy | Discussions well underway with Corporate Services Funding of posts on reception requires to be finalised likely takeover date 1 October 2002. | Complete Ongoing improvements to Civic Centre reception area |
| 23. | To provide a cost effective Property Service. | Non Housing FM functions to be centralised in Development Services Directorate. | Feb 02 – Mar 04 | E. Wilson/D. Hoy | All Social Services Admin Offices F.M. functions were centralised in D.S. with effect from 1 April 2002. Discussions underway with Education and Leisure. Anticipated all other areas to be transferred to D.S. by 1 April 2003. | Social Services Complete Further discussions required with Education & Leisure and Environmental Services revised transfer date of 1st April 2004 |
| 24. | To provide a cost effective Property Service. | Staff requesting IT training to be enrolled on to ECDL and training to be prioritised. | Dec 01 – Jan 02 Ongoing. | J. Till Appraisors Appraisors | Complete. Continued support and resources to be made available to participating staff. | Enrolment complete 46 staff are enrolled and undergoing the ECDL course |
| 25. | To provide a cost effective Property Service. | Benchmarking with Core Cities to continue considering financial cost of services. | Ongoing throughout the action plan period Mar 02 – Mar 07 | E. Wilson | Ongoing. | There are 13 property indicators on the Core Cities benchmarking club. We are closely involved in 11 areas to compare performance targets ensuring service improvements are made based on best practice examples. |
| 26. | To provide a cost effective Property Service. | Continue process benchmarking with Manchester CC through core cities. | Ongoing. | E. Wilson | Rent Reviews and Lease Renewals process benchmarking completed. Awaiting next Core Cities meeting in Liverpool in October. | Benchmarking with two private organisations has taken place. Review need for Surveyors to serve notices direct. Review to standardise lease agreements to be considered |
| 27. | To provide a cost effective Property Service. | Develop common benchmarking areas for maintenance service, operational service costs and property running cost. | Ongoing throughout the action plan period Mar 02 – Mar 07 | J. Dooley/SPMU | We will need to review information from various sources may overlap/ duplicate/compliment each other. National PI overall costs for operational and non-operational properties produced through the AMP. | Visit to Bury to take place to review Best practice. Now members of the NW Benchmarking Group in respect of property maintenance. |
| 28. | To provide a cost effective Property Service. | Review hourly rates – generate income for investment in service development but remain competitive. | Dec 02 – Mar 04 | P. Openshaw E. Wilson | Work to be commenced in Dec 02. | Some comparable evidence obtained from Core Cities Benchmarking Club. To be applied to Salford operations and new hourly rates to be produced in conjunction with the proposed new Joint Venture arrangements. |
| 29. | To provide a cost effective Property Service. | Introduce process improvements. | Dec 02 – Jan 03 Ongoing. | E. Wilson/P. Smith SPMU C. Platt | Work to be commenced in Dec 02. Some preliminary review work has already been undertaken and sales of property are now advertised on the web site. | Review in process to be completed by June 03 A number of process improvements have been implemented in Property Management in respect of activities previously undertaken by legal. |
| 30 | To provide a cost effective Property Service. | Salford/Private partnership arrangements to be reviewed to ensure ongoing effectiveness. | July 02 Annual activity | J. Dooley K. Wolstencroft | Formal review to be undertaken in January and July each year. | Review meeting held with existing partner on Education projects. Other partners for Education being considered prior to proposed Joint Venture Partnership agreement |
| 31. | To provide a cost effective Property Service. | Direct electronic time charge recording system be explored. | June 03–Aug 03 | P. Mallinder | Due to commence June 03. | Timemaster system for all staff in Development Services being considered – implementation to be agreed. |
| 32. | To provide a cost effective Property Service. | Explore benefits of private sector Facilities Management Operations. | May 03 – Jan 05 | E. Wilson/D. Hoy | Work to be commenced in April 2003 may be affected by proposals for external partnerships | Deferred pending outcome of proposed Joint Venture Partnership |
| 33. | To provide a cost effective Property Service. | Establish partnership with a construction company in accordance with Rethinking Construction principals for provision of programmed and responsive repairs. | Jan 02 – July 03 | M. Sykes/DMG Ditto B. Taylor M. Sykes/DMG B. Taylor/R.Wynne M. Sykes/DMG/ Lead Member/ Cabinet | Preparatory works are well underway. An advertisement asking for expressions of interest will be placed shortly. Open day organised for 1st November 2002 to discuss Rethinking Construction. | Categories and structures agreed OJEC advert imminent and replies Based on status and capacity questionnaire will be considered leading to tenders for a number of companies in each category Proposed start dates proposed. |
| 34. | To provide a cost effective Property Service. | New IT equipment and Software to be installed. | Jan 02 – Sept 02 Annual activity | E. Wilson P. Openshaw | Completed. | Bid made for 03/04 priorities £17830.00 Awaiting decision |
| 35. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Improve communication with property occupying Directorates to gain greater prior knowledge of building closures. | Feb 02 – Dec 02 | SPMU & A. Cartwright | Surplus Property Policy now in operation. Monitoring required through AMG to ensure effective application. | Still being developed and improved |
| 36. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Alternative means of marketing vacant premises to be pursued. | Aug 02 – Dec 02 | P. Smith | Existing procedures and budget being considered. Discussions to take place with marketing company to investigate other options prior to preparing plan and sales/advertisements through website taking place. | Marketing report obtained. Advertisements have been improved in line with recommendations. Work to improve coverage taking place with EDU |

| 37. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Improve AMP assessment rating. | May 02–July 02 | SPMU | AMP submitted June 2002. Decision on 2002/03 AMP expected Dec 02/Jan03. | Improvement achieved Asset Management Plan assessed as “GOOD” by Government Office No longer required to submit AMP for assessment |
| --- | --- | --- | --- | --- | --- | --- |
| 38. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Corporate Property Strategy to receive approval. | May 02–June 02 | R. Wynne | Completed. | Complete |
| 39. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Promote availability of incentives for vacant premises. | Ongoing. | P. Smith | Existing incentives continue to be offered. Need to link to Marketing Plan with any new incentives as required. | Marketing report did not provide any new options although expanding boundary monies being pursued with EDU Existing incentives continue to be offered |
| 40. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Improve performance on rent collection. | Apr 02 – Mar 03 Ongoing. | E. Wilson | Completed. Completed. Detailed discussions ongoing with Corporate Services (Treasurers and Legal) in order to reduce current levels of debt and to reduce the possibility of future rental arrears. Visits to Best Practice Local Authorities to be undertaken by Dec 02. | Rental arrears are decreasing Ongoing dialogue taking place with Finance and Legal leading to proactive action against tenants in arrears. Best practice information obtained and being analysed |
| 41. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Explore sale and partnership opportunities with the private sector and other public sector providers to improve industrial unit occupancy levels particularly on high void estates. | June 02–Dec 03 | E. Wilson & P. Smith | Problem Industrial estates identified. Consideration to be given to the most appropriate schemes to be taken forwards. Taylorson Street Estate identified for disposal. Marketing details to be prepared. | Report detailing proposals for rationalisation of industrial estates to be considered by P&D Lead Member May 03 |
| 42. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Reduce the amount of money spent on property by reducing the amount of property occupied and overall average running costs per SQ/M. | Ongoing. | SPMU/D. Norbury | Area based reviews due to start with Irlam and Cadishead in Nov 02, as a pilot. The AMG has approved this. | Irlam and Cadishead area review delayed but now underway |
| 43. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Reduce amount of property occupied by increasing intensity of use, sharing and transfer of properties to other providers. | Ongoing. | D. Norbury S. Durbar D. Norbury | Work on the LIFT project is continuing although the Modernising Service Delivery Partner Group has not met since its inaugural meeting in January. | Review of existing office accommodation will be completed by end of July 03 with outcomes and recommendations reported to AMG, Directors Team and Lead members as appropriate. |
| 44. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Reduce overall average running costs by analysing individual building running costs and seeking efficiency gains. Targeting poor performing buildings for disposal. | July 02 - Ongoing | D. Hoy SPMU D. Norbury | We have data for 01/02 financial year we do include this info in property appraisal reports submitted to AMG. | Data for 02/03 will be analysed in Apr/May. Performance data provided to occupying directorates – more action needed to use information positively in developing property strategy |
| 45. | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Explore long term procurement arrangements with private companies to establish partnership to increase private and public sector investment in property. | Apr 02 – Sept 03 | M. Sykes/DMG B. Taylor M. Sykes/DMG B. Taylor M. Sykes/DMG/ Lead Member/ Cabinet | Preparatory works are well underway. An advertisement asking for expressions of interest will be placed shortly. | Advert placed and preferred Joint Venture model with secondment of staff endorsed by Cabinet. OJEC advert for expressions of interest expected May 2003 |
| 46 | To reduce the amount of operational property and average running costs and improve the rate of return from the commercial estate. | Implement Surplus Property Policy | Apr 02 – Aug 02 | SPMU/D. Norbury PJO | Complete. Ongoing work to secure reductions in operational property by selling surplus assets. Industrial estate performance to be analysed by Dec 02. Ongoing attempts to improve income from the commercial estate by review of marketing options (see No 36) | Industrial estate analysis will now be completed in April 2003 Ongoing work within the remainder of the commercial estate taking place to identify capital receipts and opportunities for additional rental income. |

# Comments

Attached reports 43 and 331 ph 1 & 2 imp plans

Attached to report 504 and document 43 pjo (phase 2 imp plan) to scrutiny 18/11/02

# Text boxes

APPENDIX 1

##### APPENDIX 1

# APPENDIX 2

### ITEM  9