Project Plan and key milestones:

|  | Task/issue | 2001 | 2002 |
| --- | --- | --- | --- |
|  |  | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar |
| 1 | Establish scope, terms of reference | ----- | ----- | ----- | ----- | ----- | ----- | ----- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Identify review team | ----- | ----- | ----- | ----- | ----- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Visioning workshop determine 4C strategies |  |  |  |  |  |  | ----- |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Undertake 4C projects |  |  |  |  |  |  |  | ----- | ----- | ----- | ----- | ----- | ----- |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Undertake EFQM assessment |  |  |  |  |  |  |  | ----- | ----- | ----- | ----- | ----- | ----- |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Compile costed options with advantages, disadvantages |  |  |  |  |  |  |  |  |  | ----- | ----- | ----- | ----- | ----- | ----- |  |  |  |  |  |  |  |  |  |
| 7 | Consult stakeholders on options |  |  |  |  |  |  |  |  |  |  |  |  |  | ----- | ----- |  |  |  |  |  |  |  |  |  |
| 8 | Undertake options appraisal |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ----- | ----- | ----- | ----- |  |  |  |  |  |
| 9 | Compile Final Report and draft Improvement Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ----- | ----- | ----- |  |  |  |
| 10 | Quantify significant improvements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ----- | ----- |  |  |  |  |
| 11 | Undertake final stages challenge |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ----- |  |  |  |  |
| 12 | Reporting process (see below) |  |  |  |  |  |  |  |  |  |  | ----- |  |  | ----- |  |  | ----- |  |  | ----- |  |  |  |  |
| 13 | Complete Improvement Plan and Dispatch report to BVI |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ----- | ----- | --- |
| 14 | Inspection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Reporting Process:			Current Transport Arrangements (Feb 02)

Passenger Transport Provision – 4C Analysis and EFQM Appraisal (May 02)

Options for Change (Aug 02)

Report and Recommendations (Nov 02)

Improvement Plan and Action Plans (Feb 03)