| IMPROVEMENT TARGETS | Baseline | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- |
| Cost of Property Management staff per sqm of operational building | £3.35 | Management cost per square metre to be in line with top quartile performance DTLR Property PI No.3a |
| Reduce number of Property/FM provider Directorates | 5 | 4 | 3 | 2 | 2 | 2 |
| Rent arrears as a % of rent received | 26.87% | 22% | 18% | 13% | 9% | 5% |
| Improve staff rating on training for the job | 3.45 | 3.5 | 3.7 | 3.8 | 4.0 | 4.01 (Av of sample authorities) |
| Improve staff rating on dealing with perceived under-performing staff | 4.63 | 4.5 | 4.4 | 4.3 | 4.2 | 4.06 (Av of sample authorities) |

| TIMESCALE | ACTION POINTS | ACTION REQUIRED | COMMENCING | RESPONSIBLE OFFICER | RESOURCE |
| --- | --- | --- | --- | --- | --- |
| SHORT TERM | Consider purchase of SAP property module or other alternative | Working Group to concludes considerations and make recommendations | April 2002 | P. Openshaw | Existing Staff |
|  | Increase levels of delegation particularly for Housing Directorate and building work tenders | Propose revised scheme of delegation to Housing Directorate Seek raising financial limits with Director of Corporate Services | May 2002 May 2002 | P. Openshaw E. Wilson | Existing staff Exiting Staff |
|  | Liaison with tenants re: - Security improvements | Options to be identified and discussed | May 2002 | P. Smith B. Burns | Existing Staff |
|  | Improve staff appraisal and emphasise target setting | Agree directorate wide improvements Agree clear targets and monitor performance | Oct 2002 Dec 2002 | R. Wynne and Appraisors | Existing Staff |
|  | Staff requesting IT training to be enrolled on to EDLC and training to be prioritised | Enrolment to be arranged Appraisal to identity priorities | Apr 2002 Ongoing | J. Till Appraisors | Existing Staff Existing Staff |
|  | Market test lease renewals acquisitions and disposals | Advertise for expressions of interest | Sept 2002 | P. Openshaw & P. Smith | Existing Staff |
|  | Non Housing FM functions to be centralised in Development Services Directorate | Implement in conjunction with Social Services Education and Leisure and Environmental Services FM providers Centralise responsibility for Civic Centre reception | Feb 2002 Sept 2002 | E. Wilson/D Hoy E. Wilson/D. Hoy | Existing Staff |
|  | Building maintenance to establish closer working with EDU regarding bids to finance building improvements | Appropriate procedure to be agreed with EDU | Sept 2002 | E. Wilson | Existing Staff |
| MEDIUM TERM | Benchmarking with Core Cities to continue considering financial cost of services | Attend and support Core Cities Group | Ongoing | E. Wilson | Existing Staff |
|  | Continue process benchmarking with Manchester CC | Quarterly meetings to continue | Ongoing | E. Wilson | Existing Staff |
|  | Develop common benchmarking areas for maintenance service | Identify appropriate PI and BM sources | Ongoing | J. Dooley | Exiting Staff |
|  | Undertake comparison of operational service costs | Identify appropriate PI and BM sources | Sept 2002 | SPMU | Existing Staff |
|  | Develop common benchmarking areas fro property running cost | Identify appropriate PI and BM sources | Ongoing | SPMU | Existing Staff |
|  | Review hourly rates – generate income for investment in service development but remain competitive | Compare current charges with BM’s and Competition. Agree appropriate charge consult customers | Dec 2002 | P. Openshaw E. Wilson | Existing Staff |
|  | Improve process improvements | Apply revised procedures Annual review of property strategy Pursue requirements of e-government | Oct 2002 Dec 2002 Ongoing | E. Wilson/P. Smith SPMU C. Platt | Existing Staff |
|  | The Salford / E.C Harris partnership arrangements to be reviewed to ensure ongoing effectiveness | Undertake 6 monthly monitoring and review Implement necessary action | July 2002 | J. Dooley & K. Wolstencroft | Existing Staff |
|  | Direct electronic time charge recording system be explored | Assess pilot system in Architectural Services Assess and implement as appropriate | June 2003 July 2003 | P. Mallinder | Finance to be identified |
| LONG TERM | Establish partnership with a construction company in accordance with Rethinking Construction principals for provision of programmed and responsive repairs | Preparatory works Produce brief Advertise Shortlist Evaluate proposals Appoint partner | Ongoing Aug 2002 Oct 2002 Jan 2003 Mar 2003 Jul 2002 | M. Sykes / DMG Ditto B. Taylor M. Sykes / DMG B. Taylor/ R Wynne M. Sykes / DMG/Lead Member/Cabinet |  |
| ACHIEVEMENT | New IT equipment and Software to be installed |  | Completed |  |  |

# Text boxes

# OUTCOME TARGET AFTER REVIEW

### TO PROVIDE A COST EFFECTIVE PROPERTY SERVICE

# IMPROVEMENT THEME

##### IMPROVE SERVICE EFFICIENCY