| BEST VALUE REVIEW: - MAINTENANCE OF THE HIGHWAY/STREETCARE | SERVICE AREA: RECYCLING |
| --- | --- |
| SERVICE IMPROVEMENT PLAN |  |

# AREAS FOR IMPROVEMENT

There is a corporate need to invest in this service area to significantly improve the recycling performance and meet Government Standards. Such investment must be matched by development of initiatives, through public and private partnership, and educational programmes to develop a culture of community involvement in environmental protection.

# IMPROVEMENT TARGETS

| Indicator | Baseline 99/2000 | Est. 2001/02 | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. BVPI82(a) % of the total tonnage of household waste arisings which have been recycled . | 6.6 | 5* | 7 | 10 | 20 | 21 | 22 |
| 2. BVPI 82(b) % of total tonnage of household waste arisings which have been composted. | **0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 3. LPI The number of home compost bins provided per annum | 500 | 500 | 500 | 500 | 500 | 500 | 500 |
| 4. LPI% of population resident in the authority’s area which are served by a kerbside collection of recyclables or within 1km radius of a recycling centre. | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

* Reduction due to determination by the Environment Agency that soil forming material would not be accepted as a recyclate.

** City promotes home composting but this is not accounted for in BVPI definition which excludes home composting.

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| --- | --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |  |
| 1. Create a recycling budget to support the recycling programme. | Seek both internal and external funding opportunities. | April 2002 and ongoing | Director | CL | £200K to £2M |
| 2. Establish a kerbside pilot scheme for multi-material collection. | Enter into partnership with suitable service provider and the community. | May 2002 | AD(C) | ABCK | £200K |
| 3. Increase Awareness of recycling and waste minimisation initiatives | Deliver proactive education and awareness programmes to the whole of the Community | Ongoing | Salford Pride Unit | C | Directorate Budgets |
| 4. Increase number of “bring sites” by one per year | Acquire relevant funding. Identify locations | April 2002 Onwards | DMT | BC | £10K per annum. |
| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| Medium Term |  |  |  |  |  |
| 1. Improve utilisation of Civic Amenity Sites to encompass recycling | Consult and influence GMWDA | June 2002 onwards | AD(C) | BCK | Waste Disposal Levy |
| 2. Enhance Corporate Recycling Schemes | Development of Green Co-ordinators within Directorates | Mid 2002 | Deputy Director | E | Directorates’ Resources |
| 3. Develop wider ranging partnerships for recycling. | Liaison with external bodies | Mid 2002 | DMT | BCK | Maximise external funding opportunities |
| 4. Promote the acquisition of an additional 500 home compost bins per annum. | Marketing and Delivery of Subsidised compactors | Mid 2002 and ongong | DMT | BC | £5K per annum. (50% funding from Landfill Tax Credit). |
| Long Term |  |  |  |  |  |
| 1. Offer reduced rates for commercial recycling | Develop and implement policy | April 2003 | AD(C) and Deputy Director | BC | Self Financing within Commercial Contracts |
| 2. Increase recycling rates to 10% to meet Government standard | Implement short and medium term actions | 2003/2004 | DMT | C | Cost of short and medium term actions |
| 3. Enable recycling investment through a change in current waste disposal financial and operational methodologies. | Move from current levy payment to tonnage based disposal charging | April 2003 | Director/ Council | JKL | From revised GMWDA charging approach. |
| 4. Increase recycling rates to 20% to meet Council pledge | Implement short and medium term actions | 2004/05 | DMT | L | Total cost of short and medium term actions |
| Achieved |  |  |  |  |  |
| 1. Update the Recycling Plan to take account of the National Waste Strategy | Update Plan | November 2001 | DMT | C | NONE |
| Achieved and Ongoing |  |  |  |  |  |
| NONE |  |  |  |  |  |