| BEST VALUE REVIEW: - MAINTENANCE OF THE HIGHWAY/STREETCARE | SERVICE AREA: STREET CLEANSING |
| --- | --- |
| SERVICE IMPROVEMENT PLAN |  |

# AREAS FOR IMPROVEMENT

The delivery of a better quality service through improved frequency of sweeping, utilising increased mechanisation, at a cost commensurate with other Metropolitan “Sister” authorities, providing directly comparable Services. The commitment to 100% service delivery, on a predetermined and specified day, with such information being provided to the whole Citywide Community.

# IMPROVEMENT TARGETS

| Indicator | Baseline 99/2000 | Est. 2001/02 | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. BVPI89 % of people satisfied with cleanliness standards (i..e. keeping land clear of litter and refuse). | 32 | 44 | 53 | 62 | 70 | 71 | 73 |
| 2. LPI% of highways that are of a high or acceptable standard of cleanliness. | 87 | 91 | 93 | 95 | 96 | 97 | 98 |
| 3. LPI% of main roads cleaned every week. | - | - | 100 | 100 | 100 | 100 | 100 |
| 4. LPI% of other streets cleaned every three weeks | - | - | 100 | 100 | 100 | 100 | 100 |
| 5. *LPI number of litter bins provided per square km of relevant land and highways for which the authority is responsible for keeping clear of litter and refuse | - | - | - | - | - | - | - |
| 6**LPI net spending per head of population on street cleansing. | 8.81 | 7.53 | 7.61 | 7.68 | 7.76 | 7.84 | 7.91 |
| 7.LPI % occasions that all strategic routes were gritted prior to the formation of ice. | 100 | 100 | 100 | 100 | 100 | 100 | 100 |
| 8. LPI % response within target times for removal of graffiti (a) offensive/racist/etc. (b) other | - | - | 75 | 80 | 85 | 90 | 100 |
| 9. LPI% of abandoned vehicles removed within eight days of service of the required statutory notice. | - | - | 100 | 100 | 100 | 100 | 100 |

* Audit Commission/IdeA Local Indicator for which no targets yet developed and need to consider effectiveness of this particular indicator.

** Costs allow for projected annual indexation of circa 3% but concurrent efficiency savings of 2% equating to a net increase of 1%.

*** This indicator will be superseded if legislation changes or a partnership ensues with Greater Manchester Police.

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| --- | --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |  |
| 1. Inform the public of specific pledged sweeping dates. | Produce and issue a 3-year programme calendar. | April 2002 | DMT | BD | £20K |
| 2. To increase sweeping cycles to achieve a city-wide sweep every three weeks as a minimum | Implement review of Street Cleansing and “fine tune” routes and rounds. | April 2002 | AD(C) | ABH | Reinvest Savings from human resource reductions. |
| Medium Term |  |  |  |  |  |
| 1. To carry out a customer survey, by telephone, on revised service provision. | Prepare questionnaire and identify target customers. | December 2002 | DMT | BH | Directorate Budgets |
| 2. Introduce geographical monitoring system. | Acquire system and commission. | September 2002 | AD(C) | BDH | £66K set up costs. £7K per annum revenue costs. |
| 3. Establish a litter enforcement regime. | Staff Training. Liaise with “Safer Salford” and Development Services Directorate for diversified use of warden type services and parking attendants. | September 2002 | Deputy Director/ AD(C) | BDH | £20K set up costs. |
| 4. Improve response time for removal of abandoned cars. | Consider revised guidelines for abandoned car removal when published. Implement proposed partnership with Greater Manchester Police. | Reliant on Secretary of State Mid 2002 | CX/Council | C | £60K |
| 5. Improve response to all requests for graffiti removal. | Increase investment. Increase coverage of Service. Increase speed of response. | Mid 2002 | AD(C) | BC | £60K via external funding, e.g. ERDF/NRF |
| Long Term |  |  |  |  |  |
| 1. To improve the standard of street cleansing, within the City, to within top quartile of metropolitan Authorities. | Implement review of Street Cleansing in full. | 2004/005 | AD(C) | ABD | Directorate Budgets |
| 2. To achieve Chartermark Status for Street Cleansing Service | Develop a comprehensive Bid | 2005/06 | DMT | B | None |
| Achieved |  |  |  |  |  |
| 1. Adopt a Development Control Policy, within the Planning Process, for the provision of litter bins. | Approval of Planning Regulatory Panel sought by Development Services Directorate. | September 2001 | Planning Services of Development Services Directorate | EJ | None |
| 2. Reduce the cost per head of population of street cleansing. | Implementation Review of Street Cleansing. | November 2001 | AD(C) | AG | None |
| 3. Ensure 100% Service Delivery through alternative employment practices/partnerships. | Obtain Council approval for a policy on alternative employment practices | May 2001 | AD(C) | ABCDHKL | Directorate Budgets |
| Achieved and Ongoing |  |  |  |  |  |
| 1. Improve Weed Control | Increase investment. Expand coverage. Place whole service provision within Environmental Services. | December 2001 June 2002 | AD(C)/ Development Services | BEL | £135K to bring sites up to standard. £47K per annum increase to budget for maintenance of improvements. |
| 2. Improve customer consultation processes. | Regular six monthly surveys | November 2001 | DMT | BH | £5K per annum (EnCams Independent Surveys). |
| 3. Increase number of litter bins | Maintain litter bin policy and allocate budget. | Ongoing | AD(C) | B | Directorate Budgets and External funding Opportunities. |
| 4. Seek external funding/sponsorship for litter bins. | Proactive Marketing and Sponsorship Approach | Ongoing | AD(C) | K | External funding support. |
| 5. Increase level of mechanisation. | Reinvest savings. Seek external funding. Arrange contract hire agreement. | November 2001 and ongoing | AD(C) | ABHK | Reinvest savings from human resource reductions. External funding bids. |