| BEST VALUE REVIEW: - MAINTENANCE OF THE HIGHWAY/STREETCARE | SERVICE AREA: REFUSE COLLECTION |
| --- | --- |
| SERVICE IMPROVEMENT PLAN |  |

# AREAS FOR IMPROVEMENT

The quality of the refuse collection service, in terms of service delivery and problem rectification, as regards missed bins, was a key area for improvement. This service enhancement should also seek to achieve cost reduction whilst ensuring equality of service provision by addressing the issue of non-collection on Bank Holidays and at Christmas.

# IMPROVEMENT TARGETS

| Indicator | Baseline 99/2000 | Est. 2001/02 | 02/03 | 03/04 | 04/05 | 05/06 | 06/07 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. *BVPI86 Cost of Waste Collected Per Household | 18.90 | 19.40 | 19.59 | 19.79 | 19.99 | 20.19 | 20.39 |
| 2. **BVPI88 Number of waste collections missed per 100,000 collections of household waste | 123 | 174 | 90 | 80 | 70 | 60 | 50 |
| 3. LPI Average Time Taken To Remove Flytipping (a) requiring specialist equipment (b) not requiring specialist equipment | - 5 | - 8 | 14 6 | 12 4 | 10 3 | 8 2 | 6 1 |
| 4. LPI % of missed collections put right at the end of the next working day | 58 | 100 | 100 | 100 | 100 | 100 | 100 |
| 5. LPI % of requests for removal of bulky household waste completed within five working days. | 25 | 50 | 100 | 100 | 100 | 100 | 100 |

* Cost increases as it allows for indexation at circa 3% and required efficiency savings of 2% equating to a 1% overall increase

** Estimate for 2001/2002 is based on nine months and includes “start up” problems with “new” refuse collection service, from May to August 2001, which had been expected.

# PERFORMANCE IMPROVEMENT PLAN

| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| --- | --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |  |
| 1. To reduce the cost of Service Provision by £150K per annum. | Implement Review of Refuse Collection in full | March 2002 Outturn | AD(C) | GJ | NONE |
| 2. To remove fly-tipped material requiring specialist equipment within ten working days of receipt of report. | Allocate and consolidate Client Directorate Budgets to Environmental Services | April 2002 | Director | ABEH | Consolidate Existing Council Budgets in a single holding fund. |
| 3. To remove fly tipped material not requiring specialist equipment within three working days of receipt of report. | Allocate and consolidate Client Directorate Budgets to Environmental Services. | April 2002 | Director | ABEH | Consolidate Existing Council Budgets in a single holding fund. |
| 4. To collect all bulky waste within five days of request. | Implement review of Refuse Collection in full. | May 2002 | AD(C) | BH | None |
| 5. To carry out a customer survey by telephone on revised service provision. | Prepare Questionnaire. Identify Target Customers. | May 2002 June 2002 | DMT | BH | Directorate Budgets |
| 6. Improve Reliability and Image of the Vehicle fleet. | Enter into a Contract Hire Agreement | February to July 2002 | AD(C) | BDK | Directorate Budgets |
| Action Points | Actions Required | Timescale | Responsible Officer | Reason for Improvement | Resources |
| Medium Term |  |  |  |  |  |
| NONE |  |  |  |  |  |
| Long Term |  |  |  |  |  |
| 1. To achieve Charter Mark Status for Refuse Collection Service | Develop a comprehensive bid | September 2003 | DMT | B | NONE |
| Achieved |  |  |  |  |  |
| 1. Ensure profitability of Commercial Refuse Service. | Identify Costs and Income. Restructure Service. Continually Monitor Trading Account. | May 2001 Ongoing | AD(C) | H | Maintain and enhance market share. |
| 2. Ensure 100% Service Delivery through alternative employment practices/partnerships. | Obtain Council Policy approval. Implement Review of refuse collection in full. | May 2001 | AD (C) | ABCDHKL | Directorate Budgets |
| 3. Introduce 4 day working on a zoned basis. | Implement Review of Refuse Collection in Full | May 2001 | AD(C) | BDFH | Directorate Budgets |
| 4. Improve Rectification Rates of Missed Bins to 100% within 24 hours. | Implementation Review of Refuse Collection in Full | August 2001 | AD(C) | ABH | Directorate Budgets |
| 5. 100% Removal of Excess Waste | Implement Refuse Collection Review in Full | August 2001 | AD(C) | BH | Directorate Budgets |
| 6. Resolution of Non-Collection on Bank Holidays | Implement Refuse Collection in Full | August 2001 | AD(C) | BFH | Directorate Budgets |
| 7. Improve Customer Relations | Reduce level of missed Bins Improve Rectification Rates. Reduced Complaints. Attend Community Meetings | August 2001 Ongoing | AD(C) | BEH | Directorate Budgets |
| 8. Introduce Service Between Xmas and New Year | Implement Refuse Collection Review in Full | December 2001 | AD(C) | B | Directorate Budgets |
| 9. To reduce number of missed Bins to within top quartile of metropolitan Authorities | Implement Refuse Collection Review in Full. | March 2002 | AD(C) | ABC | Directorate Budgets |
| Achieved and Ongoing |  |  |  |  |  |
| 1. Improve Customer Consultation Processes | Regular six monthly surveys | Mid 2002 | DMT | BH | Directorate Budgets |