P.I. Ref 2.11

Fourth Quarter 2001/02 Comparator Action Plan

Performance Indicator Action Plan				  	       	Date: 08/04/02

| Comments on Current Performance: The Government has set a top quartile level of 29 days. As a result of a revised method of calculation on this indicator by the Audit Commission and the Housing Inspectorate visit to Stockport MBC, Salford has revised the calculation method of BVPI 68 for 2001/02, which previously excluded a number of let property from the calculation. As a result of this recalculation reported average re-let times have increased from 70 to 109 days. This figure is the best estimate based on the most up to date information that we received on 25/4/02. This is a further increase of 3 days over final quarter of the year. However in terms of actual performance when using the same calculation method and comparing to the previous year, performance has actually improved from 112. This improved performance is despite a major Housing restructure and disruption in the first quarter of 2001. Given the implementation of the objectives set out in the action plan below it is planned that further reductions will be made next the year to try and achieve the set target of 56 days. |
| --- |
| Barriers to Improvement: Changing demand for social housing in general Environmental issues and neglect of property by other landlords Demographic changes in Salford Housing market and competition Surplus stock to actual demand High turnover level of voids Lack of stock/low turnover in area where demand exists Poor image and perceived crime and nuisance. |
| Current/Proposed Action: Best Value review on voids & letting. Set up specialist letting teams each with Team Leader Expand and increase resources to Marketing Team Set up and deliver staff training packages specific to letting property. Set local “letting” and “average time re-let” targets per team and monitor. Strategically review void property using ABC void process – linked to disposal strategy. Set up Best Practice team specific to letting. Set void targets for contractor to return void property repaired in a fit to let state. Review and revise procedures for void property. Review IT monitoring of void property stages. Launch letting interactive web site. Open Property shop with high street location. Review furnished tenancies. Review and set letting property standard. Review current letting policy. Develop specific local lettings plans linked to marketing. Introduce a new IT system for allocations/lettings property. Set up a performance indicator for retention of tenants and bench- mark with family members. Develop good practice measures to retain tenants. Measure the %v of offers made by telephone as opposed to by letter, as a means of speeding up the process. Develop Performance Management Strategy and Manual to improve monitoring arrangements. | Current Status: Completed Completed – set up in April 2000. Completed June 2001. Ongoing – 2-Day course on letting held September 2001. Further training provided on new policy and computer system March / April 2002. Set 2000 and reviewed April 2001. Further review to be carried out April 2002 and in April of each subsequent year. Ongoing work carried out by Strategy Section. Written procedure in place. Established April 2001 and meet monthly. Set August 2001 in consultation with void repairs contractors. To be reviewed April 2002. Reviewed May 2001 and revised. Staff training completed on new procedures. Further review and procedures to be updated following introduction of new computer system and allocations policy, May2002 Reviewed August 2001 and revised. Staff training completed on new procedures for IT input. Changes made on IT report monitoring. Further review to be carried out May / June 2002, following the introduction of the repairs module of I-SYS computer system. Site now live www.salfordpropertyshop.com Shop opened to the public6th April 2002. Internal Audit carried out, recommendations of report have been implemented. Letting standard drawn up and Implemented November 2001. Revised letting policy implemented April 2002. Ongoing with new Team Leaders (Letting) taking central role. Online from April 2002. Included in Best Value Service Improvement Plan for completion by April 2003. Method of measurement to be identified and Performance Indicator set in first quarter of 2002/3. Draft manual produced April 2002. manual to be completed by September 2002. |
| Top Quartile to be Achieved By (Date): | Lead Officer: Elaine Hargreaves Ext 1704. |