|  | PART 1 (OPEN TO THE PUBLIC) | ITEM NO |
| --- | --- | --- |

REPORT OF THE DIRECTOR OF DEVELOPMENT SERVICES AND THE DIRECTOR OF ENVIRONMENTAL SERVICES

TO THE ENVIRONMENTAL SCRUTINY COMMITTEE ON 21ST OCTOBER, 2002

TITLE: BEST VALUE REVIEW OF MAINTENANCE OF THE HIGHWAY / STREETCARE IMPLEMENTATION PROGRESS REPORT

RECOMMENDATIONS: That Members note the progress made in implementing the best value review That Members approve the future quarterly monitoring, commencing January 2003

EXECUTIVE SUMMARY: The maintenance of the Highway / Streetcare review was completed in March 2002. The final report and improvement plan were approved by this committee at its meeting on 11th March, 2002. The Audit Commission inspected the review in May 2002, publishing their findings – a one star service with positive prospects for improvement in July, 2002 This report is the first progress report in the implementation stage of the review. The schedules attached indicate the target and actual position against the various improvement indicators, along with progress / achievement of the actions identified which contribute towards the improvements. Representatives of the Directorate involved will discuss the contents of the schedules at the meeting. It is proposed that reports will follow on a quarterly basis, commencing January 2003, in accordance with the corporately agreed best value process.

BACKGROUND DOCUMENTS Maintenance of the Highway / Streetcare Final Report (Available for public inspection) Maintenance of the Highway / Streetcare Improvement Plan

CONTACT OFFICERS: Paul Mallinder 793 3606, Dave Tinker 793 2002

WARD(S) TO WHICH REPORT RELATE(S) : All wards

KEY COUNCIL POLICIES: Best Value

# Report to Environmental Scrutiny Committee

Highway Maintenance / Traffic and Transportation/ Street Lighting Improvement Plan.

Progress Update, October 2002.

Improving the Condition of Pavements

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| Community Perception | -39% | -39% | No re-survey yet undertaken |
| Stabilise claims paid out | £2.1m | £2.1m | On target |
| Repairing dangerous roads and pavements within 24 hours | 97% | 97% | 98% |

| Objective | Action | Timescale | Position October 2002 | Comments |
| --- | --- | --- | --- | --- |
| R1Target planned maintenance resources to high risk areas | Analyse GIS Plans for “hot spots” | March/April 2002 | Achieved |  |
| R2 Seek Cabinet Agreement to using bitmac as standard except in designated areas | Obtain Cabinet view to policy change in principle | April 2002 | Achieved |  |
|  | Produce cabinet report seeking a resolution | May 2002 | Achieved |  |
| R3 Determine designated areas excluded from bitmac policy | Seek cabinet approval to designated areas | June 2002 | Not Achieved. | Further work required to designate specific areas |
| R4 Improve the Inspection regime | Introduce new computer system incorporating hand held devices | April 2002 | Achieved |  |
|  | Increase Inspector numbers | During 2002 | Not yet Achieved. | Attempts at recruitment made but no suitable applicants |
|  | Re- define inspector roles | April 2002 | Achieved |  |
|  | Trial various methods of actioning repairs | During 2002 | Partly achieved. | Trials undertaken but not yet reviewed |
| R5 Merge the highway client and DLO | Devise and consult on staffing | May 2002 | Achieved July 2002. |  |
|  | Determine facilities required | June 2002 | Achieved. Finance confirmed. |  |
|  | Design and Construct building | December 2002 | On target |  |
| R6 Establish a consultancy with a construction company to introduce fresh thinking, prior to seeking tenders for an operational partner | Prepare Brief | July 2002 | Achieved |  |
|  | Advertise for expressions of interest | October 2002 | Not now considered to be required as firms interviewed during the BVreview |  |
|  | Shortlist | January 2003 | Achieved |  |
|  | Seek tenders | August 2003 | On target | Accord plc appointed October 2002 |
|  | Evaluate and appoint |  | On target for October 2002 |  |
| R7 Introduce a Rapid Repair Service | Carry out further trials | April. May 2002 | Achieved |  |
|  | Consider implications of trials on Code of Practice | May/June 2002 | Not Yet achieved |  |
|  | Implement/publicise Rapid Repair service | August 2002 | Not yet achieved |  |
| R8 Establish closer liaison with Environmental Services via an Officer Partnership Board | Agree Constitution | April 2002 | Achieved |  |
|  | First Meeting | May 2002 | Achieved |  |
| R9 Revise Risk Management Process | Change claims handling process | Ongoing | Progressing |  |
|  | Implement SBS | August 2002 | Achieved |  |
|  | Improve communication with claims handling agents | Ongoing | Progressing |  |

# The Response Time to Non Urgent Works Orders

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| Non dangerous defects repaired within 2 weeks | 65% | 70% | 70% |

| Objective | Action | Timescale | Position October 2002 | Comments |
| --- | --- | --- | --- | --- |
| R10 Revise practices | Purchase infra red patching system | April 2002 | Achieved |  |
|  | Staff training on system | June 2002 | Achieved |  |
|  | Launch Operation | July 2002 | Achieved | Coverage in Salford Advertiser Results of a A six week review A 58% time and cost saving on repairing a pothole 50mm deep A 17% time and cost saving on a pothole 25mm deep. 14 tonne of dense bitumen used in 26 days. Used to be 118 tonne. 104 tonne less of excavated carriage way to be disposed of, reducing disposal and land fill tax cost 88% of old carriageway surface retained and recycled £30,000 per year has been freed up to fund more improvements |
|  | Improve clarity of information produced through SBS | April 2002 | Achieved |  |
|  | Consider response implications of the Code of Practice | July 2002 | Achieved |  |

# Reducing  the Number of People Killed or Seriously Injured on Roads

| Indicator | 2001 Baseline | 2002 target | 2002 actual to date |
| --- | --- | --- | --- |
| Number of KSI’s | 110 | <95 | 43 Jan - June 2002 . Was 44 Same period 2001. |

| Objective | Action | Timescale | Position October 2002 | Comments |
| --- | --- | --- | --- | --- |
| R11 Seek resources through a PSA bid | Prepare background to bid | February 2002 | Achieved |  |
|  | Present to Cabinet | February 2002 | Achieved |  |
|  | Submit bid | March 2002 | Achieved. | Bid was successful |

The Provision of Customer Information

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| Highway Routing information for disabled people | No information | Full information | No Information |

| Objective | Action | Timescale | Position October 2002 | Comments |
| --- | --- | --- | --- | --- |
| R12 Improve information for disabled people in conjunction with the Disability Access Forum | Disability Access Forum to identify suitable ways of publicising routes | By June 2002 | Date Not achieved but work is progressing | Trupti Patel ( Traffic Officer) is formulating a joint document with Access Officer Judith Irving. Manchester City Council’s document may be used as a base version |
| R13 Improve public communication through the web site | Post on the web site a schedule of major utility works being carried out within the City | May 2002 | Achieved |  |
| R14 Produce alley gating guide | Complete consultation on the guide | September 2002 | On target |  |

# Reducing Opportunites to Commit Crime

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| The number of alley gating projects completed | 2 | 4 | On target |

| Objective | Action | Timescale | Position October 2002 | Comments |
| --- | --- | --- | --- | --- |
| R15 Progress further alley gating projects in conjunction with community committees | Programme of work to be determined in conjunction with partners | On going | Progressing | The Highway Maintenance Manager is currently dealing with 2 requests for closures |

Improving Facilities for Disabled People

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| The percentage of pedestrian crossings with facilities for disabled people | 59% Previous definition | 59% Based on previous definition | 59% Based on previous definition |

| Objective | Action | Timescale | Position October 2002 | Comments |
| --- | --- | --- | --- | --- |
| R16 LTP monies to be redirected at this PI | Procure a survey of work required and phasing options | April 2003 | Achieved | Ahead of schedule. A phased improvement plan will shortly be developed. |

Improving Ease  of Use of Footpaths

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| Percentage of footpaths easy to use | 50% | 65% | On target |

| Objective | Action | Timescale | Position October 2002 | Comments |
| --- | --- | --- | --- | --- |
| R17 That measures are taken to improve this PI | Ordering of new footpath signs | March 2002 | Achieved |  |
|  | Commence installation | June 2002 | Installation progressing | Approximately 10 of 40 signposts installed so far |

# Improving the Condition of Street Lighting Columns

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| The percentage street lighting columns in need of urgent replacement | 10% | 11% | Est 11% |

| Objective | Action | Timescale | Position October 2002 | Comments |
| --- | --- | --- | --- | --- |
| R18 Produce a business case for funding | Survey street lighting stock | June 2002 | Partially Achieve | Will now be a part of the PFI work |
|  | Consult with Unison | April 2002 | Achieved |  |

# Improving the Management of the Service

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| Improve quality of Highway Information Records | Satisfactory | Move towards Good | On target for long term objective |
| Degree of compliance with Code of Practice for Highway Maintenance | 55% full 27% partial 18% none | 58% full 30% partial 12%none | On target |

| Objective | Action | Timescale | Responsible Officer | Position October 2002 | Comments |
| --- | --- | --- | --- | --- | --- |
| R20 Improve Highway records | Complete National Street gazetteer level | June 2002 |  | Achieved |  |
|  | Carry out study of existing record systems compatibility with SBS | April 2002 and ongoing |  | On target |  |
|  | Further progress the implementation of the SBS system |  |  | On target |  |
| R21 Further progress position against the Highway Maintenance Code of Practice | Further progress | ongoing |  | Progressing |  |

# Increasing the level of Investment in the Highway

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| Increase baseline expenditure | 100% | 100% | 100% |
| Maintain levels of capital investment | 100% | 100% | 100% |
| Obtain capital investment from external partnership | Nil | Nil | Nil |

| Objective | Action | Timescale | Position October 2002 | Comments |
| --- | --- | --- | --- | --- |
| R22 Ensure joint working with Regeneration Teams | Seek clarification of the bidding process | May 2002 | Achieved |  |
|  | Put forward ideas to include in bids | June 2002 onwards | Progressing |  |
| R23 Director of Corporate Services to instigate a process that models the SSA allocation to verify it | Review process with Director of Corporate Services | May 2002 | Achieved |  |
| R24 Explore long term Strategic partnership arrangements | Consultation, brief preparations etc. | September 2002 | On target | Awaiting City Council decision about size and scoping. |
|  | Advertise for expression s of interest | October 2002 | On target | Working group is set up. An advertisement seeking private sector proposals for partnership models is due to be placed at end October 2002 |

# Recycling/ Refuse Collection/ Street Cleansing/ Themed Issues/ Dog Wardens Improvement Plan

## Progress Update, October 2002

RECYCLING

| ## INDICATOR | 2001/2 BASELINE | 2002/3 TARGET | 2002/3 ACTUAL TO DATE |
| --- | --- | --- | --- |
| BVPI 82 a Percentage of domestic waste arisings recycled | 5.47% | 7% | Figures not yet available – provided by GMWDA mid 2003 |

| ### OBJECTIVE | ### ACTION | ### TIMESCALE | ### POSITION OCT 02 | ### COMMENTS |
| --- | --- | --- | --- | --- |
| Issue 500 compost bins per annum from 2002/03 – 2006-07 | Home compost bins are made available to the public at subsidised rates. | #### April 2002 – March 2007 | ##### Ongoing | The provision of home composters is a central element to promoting domestic waste recycling |
| Create a budget to support recycling programme | Following a successful DEFRA bid, financial committment has been given by the City Council to provide revenue support for the recycling programme | #### April 2003 | ##### Achieved |  |
| Establish a kerbside multi-material collection scheme | NDC and DEFRA funding will allow at least half the city to receive kerbside collection of recyclables. | #### April 2003 | #### Substantially Achieved | A second bid to DEFRA has been made via GMWDA , if successful all the city should receive the service by 2004/05. |
| Increase awareness of recycling and waste minimisation initiatives | A Greater Manchester wide publicity campaign will be introduced due to funding received from DEFRA | 2003- Onwards | Achieved – finance confirmed | A publicity/communications strategy is currently being developed |
| Increase the number of sites by one per annum, year commencing 2002/03 | 2 sites have been introduced during 2002/03 | ##### Ongoing | ##### Achieved | Following a successful LPSA bid 20 mini-recycling sites will be created at the city’s high rise blocks over the next 2 years. |

| Through partnerships with GMWDA improve CA sites recycling activities. | A bid has been submitted to DEFRA to improve all CA sites in Greater Manchester in relation to improving their ability to increase domestic recycling levels | 2003/04 | Awaiting decision from DEFRA | Waste being delivered to CA sites is rising rapidly and therefore there is a need to address this urgently regardless of the outcome of the DEFRA bid |
| --- | --- | --- | --- | --- |
| Enhance corporate recycling schemes | A report has been prepared by the Environmental Services Directorate on how to increase corporate recycling levels | 2003/04 | Report to be presented to Cabinet October 2002. | The outcome of cabinets response to the report will determine future actions |
| Develop wider range of partners to increase recycling rates | As part of the tendering process to identify potential providers of kerbside collection schemes, new contacts will be made | ##### April 2003 | Tendering assessment is currently being carried out | It is vital to develop links with collectors and reprocessors if the city is to develop a sustainable recycling programme |
| Consider offering reduced rates for Commercial Recycling by end April 2003 | A report is being produced to identify a differing scale of charges for customers who recycle their waste | ##### April 2003 | ##### Ongoing |  |
| Increase recycling of domestic waste to 10% by 2003/04 to Government targets | A kerbside collection scheme to 45,000 properties is currently being planned. It is expected these collections will help achieve the required recycling rate. | ##### April 2003 | ##### Partly Achieved | The city’s current recycling rate of 5.47% will form the foundation for the 10% target which needs to be met. |
| Increase investment in recycling operations by bringing about changes in current waste disposal and operational methodologies by April 2004 | The Environmental Services Directorate has produced a report for Cabinet which outlines a series of options to achieve more economical waste disposal changes. This will be presented to cabinet in October 2002. | ##### April 2004 | ##### Partly Achieved | The decision of Cabinet will determine the course of actions to be taken in the future provision of waste disposal /treatment services to the City. |
| Increase recycling of domestic waste to 18% by 2005/06 to meet Government targets and City Council pledges. | The development of kerbside collections together with existing recycling sites, and home composters should help reach the required target | ##### March 2006 | ##### Ongoing |  |
| Update the City’s Recycling Plan to take account of the National Waste Strategy 2000. | Updated information has been added to the city’s recycling plan. | 2002 | ##### Achieved |  |

STREET CLEANSING

| ## INDICATOR | 2001/02 BASELINE | 2002/03 TARGET | 2002/03 ACTUAL TO DATE |
| --- | --- | --- | --- |
| LPI 16% of highways that are of a clean- acceptable standard | 91.86% | 93% | 96% |

| OBJECTIVE | ACTION | TIMESCALE | ### POSITION OCT’02 | COMMENTS |
| --- | --- | --- | --- | --- |
| Achieve local P.I targets, as highlighted in BVPP 2002/03 | Monitoring of service performance both operationally and statistically is carried out | ##### March 2003 | ##### Achieved |  |
| Develop calendar to inform public of specified dates of cleansing in their areas | Printing and distribution to all households of street sweeping calendar | 2002 | Achieved (May 2002) |  |
| Increase city-wide sweeping frequency to a minimum of every 3 weeks | All residential areas now receive a three-weekly sweep as a minimum. | 2002 | Achieved (May 2002) |  |
| Undertake a customer survey by telephone on revised/improved street cleansing | To be carried out by Contract Services administration and operational staff | ##### December 2002 | Survey has now begun with a finish date of December 2002 |  |
| Introduce a Geographical Monitoring Service | Trials of tracking system completed, now need to identify source of finance. | ##### September 2002 | ##### Partly Achieved |  |
| Establish a litter enforcement programme. | Pilot area being considered for use of on the spot fines. | ##### September 2002 | ##### Partly Achieved |  |
| Improve removal time of abandoned vehicles | Partnership with Greater Manchester police has given responsibility to police to remove vehicles on behalf of the City Council. | 2002 | ##### Achieved | Response time now within 25hours. |
| To improve standard of street cleansing to within top quartile of Metropolitan Authorities | Increased level of mechanical sweeping operation and increased frequency of sweeping across the city | 2004/05 | ##### Ongoing | Due to Encams no longer carrying out Metropolitan cleanliness surveys there will be a need to develop new methods of benchmarking performance. |

| Develop formal strategy for the allocation and siting of litter bins | Formal internal policy adopted as to siting of litter bins across the city | 2001 | ##### Achieved |  |
| --- | --- | --- | --- | --- |
| To achieve Charter Mark status for Street Cleansing | Preparations underway | 2005/06 | ##### Not Achieved | New criteria being developed by Chartermark which will need to be assessed. |
| To reduce cost per head of population for provision of street cleansing services | Due to recent investment in greater levels of machinery to improve cleanliness levels this has proved difficult to achieve | 2001 | ##### Not Achieved | Remains an ongoing target |
| Ensure 100% service delivery through alternative employment practices/partnerships | Partnerships developed which allows use of agency staff to cover sickness and holidays ensuring 100% cover | 2001 | ##### Achieved |  |
| Improve customer consultation | Increased level of customer consultation via ENCAMS survey | 2001 | ##### Ongoing | The Environmental Services is developing a consultation strategy which identifies levels of consultation required. |
| Increase the number of litter bins | Partnership with GMPTE has allowed over 200 additional bins to be sited at bus stops across the city | Ongoing | ##### Achieved/Ongoing |  |
| Seek external funding/sponsorship for litter bins | Partnership with Trash Media has resulted in almost 100 extra bins across the city. | Ongoing | ##### Achieved/Ongoing |  |
| Increased level of mechanisation to deliver better quality street cleansing | 14 New mini sweepers have been introduced, which have led to higher frequencies of street cleansing | ##### Begin in 2001 | ##### Achieved |  |

REFUSE COLLECTION

| ### INDICATOR | 2001/02 BASELINE | 2002/03 TARGET | 2002/03 ACTUAL TO DATE |
| --- | --- | --- | --- |
| The cost of waste collection per household | £19.95 | £19.59 | £18.90 |
| The number of collections missed per 100,00 collections | 98 | 70 | 57 |

| OBJECTIVE | ACTION | TIMESCALE | POSITION OCT’02 | COMMENTS |
| --- | --- | --- | --- | --- |
| Reduce the cost of service provision by £150k per annum | By amalgamating teams, reducing relief staff and team numbers savings of £150k per annum have been achieved | ##### May 2002 | ##### Achieved |  |
| To collect all bulky waste within 5 days of receiving the request | All bulky waste is now collected as part of the normal domestic waste collection round | ##### May 2002 | ##### Achieved |  |
| Carry out customer surveys by telephone | Survey questionnaires have been prepared and contact has been made with customers | ##### December 2002 | ##### Partly Achieved | Survey has been linked in with street cleansing survey |
| Improve reliability and image of vehicle fleet | New vehicle leasing programme has resulted in 3-year replacement programme for all RC Vehicles. 11 new vehicle received 1/7/02 | ##### July 2002 | Achieved |  |
| Achieve Charter Mark Status | Preparations currently underway | ##### September 2003 | ##### Ongoing |  |
| Ensure profitability of commercial refuse collection service | New partnership has allowed use of agency staff to cover sickness & holidays |  | ##### Ongoing |  |
| Ensure 100% service delivery through alternative employment practices/partnerships. | New partnerships has allowed use of Agency staff to cover sickness and holidays | ##### May 2001 | ##### Achieved |  |
| Introduce 4 day working on a zoned basis | 4 day working week introduced to resolve issue of non-collection on Bank Holidays | May 2001 | #### Achieved |  |
| Improve rectification rates of missed bins | Better quality of monitoring by Environmental Co-ordinators has significantly reduced levels of missed bins | ##### August 2001 | ##### Achieved | Levels of missed bins has fallen from 98 per 100,00 (2001/02) to 57 per 100,000 (Sept 2002/03) |
| 100% removal of excess waste | All refuse placed out by residents is now removed | ##### August 2001 | Achieved |  |

| Resolution of non-collection on Bank Holidays | The introduction of the 4-day working week (Tues-Fri has now resolved the issue of non-collection on Bank Holiday Monday | August 2001 | Achieved |  |
| --- | --- | --- | --- | --- |
| Improve customer relations | All front-line staff receive customer care training | Ongoing | Achieved/Ongoing |  |
| Introduce service between Christmas and New Year | The service between Christmas and New Year was introduced in December 2001 | December 2001 | Achieved |  |
| Reduce the number of missed bins to within the top quartile of Metropolitan Authorities | Significant reductions in missed bins have occurred through improved monitoring by Environmental Co-ordinators | ###### March 2002 | ###### Partly Achieved | This aimed to be benchmarked against other Metropolitan Authorities as part of the PI system. However this PI has now been abolished, therefore alternative benchmarking procedures will need to be devised |
| Improve customer consultation | A survey is to be undertaken in October 2002. An Encams survey for street cleansing will also have reference to refuse collection | Ongoing | Achieved | The Environmental Services Directorate is currently developing a consultation strategy which identifies the amount of consultation each service area needs to carry out. |

## DOG WARDENS

| ### INDICATOR | ### 2001/02 BASELINE | ### 2002/03 TARGET | ### 2002/3 ACTUAL TO DATE |
| --- | --- | --- | --- |
| Indicators for this service have only been recently developed and therefore no performance data can be provided, however those proposed are as follows |  |  |  |
| Number of fixed penalties issued | Not Applicable | Not Available | Not Available |
| Response time in dealing with a stray dog | Not Applicable | Not Available | Not Available |

| OBJECTIVE | ACTION | TIMESCALE | POSITION OCT 02 | COMMENTS |
| --- | --- | --- | --- | --- |
| Implement Dog (Fouling of Land Act) 1996 | The consultation period was begun in April 2002 and following this period, the use of enforcement measures will begin in October 2002 | ##### June 2002 | ##### Achieved |  |
| Establish effective private sector service provision. | The Dog Warden Service has been placed out to tender and was awarded to Leigh Animal Sanctuary Home who currently operate the service on behalf of the Directorate which began on 1st April 2002 | ##### September 2002 | ##### Achieved |  |

THEMED ISSUES

| INDICATOR | 2001/02 BASELINE | 2002/03 TARGET | 2002/3 ACTUAL TO DATE |
| --- | --- | --- | --- |
| Due to this area of the implementation plan still being the subject of inter-Directorate discussions no performance date can at present be provided. |  |  |  |

| OBJECTIVE | ACTION | TIMESCALE | POSITION OCT 02 | COMMENTS |
| --- | --- | --- | --- | --- |
| To Remove large amounts of fly-tipping which needs specialist equipment within 10 days of notification. | Such material is either moved via the Directorate itself using heavy plant or an outside contractor when more specialised equipment is needed. e.g. bulk carriers | ##### Ongoing | ##### Achieved Over 90% of all occurrences dealt with within 10 days. |  |
| To remove fly-tipped materials that do not require specialist equipment within 3 days | The directorate removes all such materials using either Refuse Collection or Street Cleansing vehicles and staff. | ##### Ongoing | ##### Achieved Over 90% of all occurrences dealt with within 3 days. |  |
| Re-locate gully emptying crew from Environmental Services Directorate to Development Services. | Discussions are currently being progressed | ##### December 2002 | Partly Achieved |  |
| Relocate drainage crew from Environmental Services Directorate to Development Services | Discussions are currently being progressed | December 2002 | Partly Achieved |  |
| Place weed control under the Environmental Services Directorate by transferring function from Development Services | Discussions are currently being progressed | ##### December 2002 | Partly Achieved |  |