# PROGRESS REPORT ON PART 1 SERVICE PLAN 2001/2002

# MONTH :JAN 2002

| KEY OBJECTIVE | PERCENTAGE COMPLETED | OFFICER RESPONSIBLE | COMMENTS |
| --- | --- | --- | --- |
| Introduce more effective marketing arrangements for letting void properties by March 2002. | 75% | E. Hargreaves /P Davidson | Via 5lettings and Marketing teams, property shop, Web site and Marketing Plan |
| Extend centrally based marketing team into a Property Shop by August 2001 (carried over). | 90% | E. Hargreaves /P Davidson | Target date Feb 2002. Shop opens 5/6th April 2002 |
| Establish 5 local marketing teams by July 2001 (carried over). | 100% |  | Completed April 2001 |
| Simplify rehousing procedures with the introduction of a new Lettings Policy by August 2001 (carried over). | 90% | J. Molloy/P Davidson | Go live April 2002 |
| Improve the marketing of council property and changing the image of housing in the City in line with the new Marketing Strategies Plan, over the next 2 years 50% completed by March 2002. | 100% | Sue Hill | Plan published |
| Continually reduce the average time to relet empty properties to achieve the Governments upper quartile of 29 days by 2005. Relet time of 48 days to be achieved by March 2002 | 25% | P Davidson | New teams and procedures in place |
| Introduce new lettings policy to reflect the findings of the Green Paper by August 2001 including: A customer choice model Simplified lettings Link marketing to availability Review special needs housing team in light of the new letting policy. | 75% | P Davidson E Hargreaves | Policy to be introduced April 2002 |
| Carry out an EFQM assessment of 50% of housing management services by March 2002. |  | G. Rearden | No longer a corporate requirement now integrated in best value process |
| Implement the Corporate Equality of Service Delivery Policy by March 2002. | 50% | G.Rearden/ Maurice Leigh |  |
| Achieve a minimum level 2 of the Commission for Racial Equality Standard by March 2002 | 50% | G. Rearden/ Maurice Leigh |  |
| Review options for collection of cash in conjunction with Director of Corporate services. Complete by March 2002. | 100% | D. Walsh | Complete September 2001 |
| Further extend the new Salford Care on Call Service to take on 250 additional users by March 2002. | 80% | K. Micklewright | On target |
| Review housing services for the elderly as part of the Housing/Social services “support for older people at home Best Value review” to be completed June 2001. | 100% | K. Micklewright | Review complete, findings of review to be implemented over the next5 years period |
| KEY OBJECTIVE | PERCENTAGE COMPLETED | OFFICER RESPONSIBLE | COMMENTS |
| Agree timescales for implementing the findings of the joint Housing/Social Services “Support for older people at home Best Value review” by September 2001. | 100% | K. Micklewright | Best Value final report submitted to scrutiny committee Feb 2002. |
| In Partnership with other RSLs produce an information pack detailing all the City’s sheltered accommodation by December 2001. | 100% | K. Micklewright | Completed in May 2001 |
| Provide a responsive call out service for Irwell Valley Housing Association and Henshaws Association for the Blind, increasing to 6 households by September 2001. | 100% | K. Micklewright | Completed in September 2001 |
| Hold a collaborative event to involve users and raise awareness of the City’s services for Older People by July 2001. | 100% | K. Micklewright | Completed in May 2001 |
| Establish a specialist Nuisance Team to support area staff by June 2001. | 100% | Matt Jones | Complete |
| Carry out a feasibility study into outsourcing the provision of temporary accommodation for homeless families complete by March 2002. | 50% | A. Lunt | On target |
| Review the effectiveness of “The Supporting Families in Little Hulton Project” by December 2001. | 75% | J. Samuels | On Target |
| Complete the re-location of the Housing advice Centre from Eccles to the Civic Centre in Swinton by May 2001. | 100% | J. Samuels | Complete |
| Establish the new Housing Advice Service and obtain the Community Legal Service Partnership Quality Mark for information and casework by March 2002. | 90% | J. Samuels | Due by end of September 2001. On Target |
| To carry out “a count of rough sleepers” in Salford as part of the National Census Arrangements, complete by May 2001. | 100% | J. Samuels | Complete |
| Re-house and support 212 Asylum Seekers who are dispersed to Salford during the financial year 2001/2002. To complete the recruitment of a joint Housing/Social services team to manage this process, by July 2001. | 75% | J. Samuels |  |
| Carry out Best Value review of area service delivery 100% complete by March 2002 including: Responsive repairs Voids and Lettings Cash Collection and Rent Arrears Estate Management Caretaking and Cleaning Improve customer feedback across all services | 80% 80% 70% 70% 70% 60% | G. Rearden | Cash has been outsourced |
| KEY OBJECTIVE | PERCENTAGE COMPLETED | OFFICER RESPONSIBLE | COMMENTS |
| Review the Tenants Compact by March 2002. | 100% | M. Thornley | Complete |
| Develop the role of area staff with tenants groups complete by October 2001. | 25% | M. Thornley | On hold due to restructuring and move to ALMO |
| Develop the role of the People’s Forum in working in partnership with Housing Services to carry out best value reviews. Complete by March 2002, but this will be an ongoing item to fit with the 5 year review programme. | 100% | M. Thornley | Scrutiny Panel membership(4) and part of Best Value Focus Groups |
| Develop Community Lettings training for staff and tenants by December 2001. | 100% | M. Thornley | Complete |
| PROPERTY MAINTENANCE |  |  |  |
| Deliver property maintenance in accordance with the Integrated Housing Repair and Improvement Programme 2001/2002. | 75% | N. Sedman | Programme on target |
| To complete 75% of all day to day repairs within target times set by the council from date reported by tenant | 80% | K. Pearson | Increased budget provision to tackle held work. Situation will improve when H.A’s begin to re-prioritise wrongly categorised emergency jobs which will be addressed as part of Salford North Pilot |
| To integrate Building Services into Property Maintenance as part of the best value review | 60% | K Pearson | This is ongoing a part of a long term implementation plan |
| STRATEGY |  |  |  |
| Implement the Reducing Burglary Initiative Programme Phases 2 by March 2002. | 100% | Stephen Jolley | Complete |
| Develop and produce the Year 2 Business Plan for the directorate including enhanced option appraisal techniques for the future of Council Stock in the city by March 2002. | Business Plan 100% complete; Revised Option Appraisal Techniques 75% complete | Alan Lunt | Business plan will need to be enhanced for Arms Length Company Status Bid. |
| Develop and implement improved communication with the Young People of Salford on housing matters by March 2002. | 25% | Sue Hill | Initial Meetings held with Youth Staff. Meeting with Lead Member for Youth planned for Mid August. JE will prepare training pack for Youth Forums by November 2001 Pack complete now a PSA Target |
| Develop further Home Energy Conservation measures and review and enhance the Fuel Poverty report by December 2001. | 90% | Ade Alao | HECA 5th progress report and fuel povert report submitted to DTLR on 31 August 2001. Awaiting feedback from the secretary of state |
| KEY OBJECTIVE | PERCENTAGE COMPLETED | OFFICER RESPONSIBLE | COMMENTS |
| Implement the 2001/2 Housing Investment Programme including:- Improvements to the environment of Council Estates Regeneration of Private Sector Housing priority areas Introduce a system for the accreditation of Private Landlords and further investigate the potential for the licensing of Private Landlords | 1) 80% 2) 80% 3) 70% | 1) Alan Lunt 2) John Wooderson 3) Ellie Taylor | 1) most schemes up to sketch scheme, tender or on site 2) Key schemes in Broughton, Eccles, Seedley & Langworthy underway. Scoping reports on Duchy, Weast and New Weaste planned for August, September and October. Renewal Area declarations likely to be key Solution. 3) Report on progress approved by Lead Member Housing and Crime Reduction Panel. Licensing of Private Landlords will depend upon Government Legislative timetable. |
| Introduce a range of comprehensive enforcement measures e.g. Closing Orders Repairs Notices for those home owners and private landlords who fail to maintain their homes by March 2002. | 60% | John Wooderson | Difficulties in recruiting staff have meant that this target has slipped |
| Establish options for dealing with residents trapped in Negative Equity within regeneration areas report to be completed by June 2001. | 100% | Anna Charlton | Pilot currently underway. |
| Maintain a profile nationally through the Local Government Association in developing responses to the governments' Housing Green Paper and statement. | 100% | Harry Seaton | Comprehensive response to consultation papers etc. and leading auth. On Home Swapping initiative. |
| Progress a strategic partnership with the Council of Mortgage Lenders to be completed by March 2002 | 50% | Bob Osborne | Working with Manchester City Council as part of the Housing market renewal fund. |
| HOUSING DLO (OPERATIVES DIV.) |  |  |  |
| To deliver the responsive repairs contract in accordance with the specification. Meeting response times for contractors performance in 90% of the cases | 100% | Jim Caufield |  |
| To deliver planned maintenance contracts in accordance with the specification in 100% of the cases. | 75% | Nigel Sedman | On target |
| FINANCE |  |  |  |
| To manage the financial resources and Support Services of the Housing Directorate in line with the General and Revenue account budget requirements. | 100% | D. Wright | Completed |
| To finalise accounts for 2000/2001 by 31st August 2001 | 100% | D. Wright | Completed 17th August 2001 |
| To prepare Budgets for 2002/2003 by 30th November 2001 | N/a | D Wright |  |
| KEY OBJECTIVE | PERCENTAGE COMPLETED | OFFICER RESPONSIBLE | COMMENTS |
| SPECIAL PROJECTS |  |  |  |
| To introduce the following modules by 31st March 2002: Rent Accounting Estate Management ( Customer Services 1 Noise and Nuisance) Responsive Repairs including repair appointments) Allocations Stock condition Homelessness | 40% | G Strachan | The completion date for the implementation of all the modules is September 2002. |
| PERSONNEL |  |  |  |
| To have gained Investors In People accreditation for the whole of the Directorate by 31 March 2002. | 70% | D. Hall | Unable to meet timescales due to lack of resources. |
| Provide a Human Resource Strategy to include Recruitment, Training, Attendance Management and Staff Appraisal by March 2002. | 100% | D. Hall | Awaiting DMT approval. |
| LEGAL |  |  |  |
| Respond to all statutory repair claims within the timescales identified within the court processes 100% Provide training to housing staff on legal matters to at least 75 staff by 31st March 2002 | 100% 40% | S. Roxborough S. Roxborough |  |
| SERVICE DEVELOPMENTS |  |  |  |
| Develop new option appraisal strategy for void properties. | 100% | Alan Lunt |  |
| Improve the marketing of our homes |  | Sue Hill |  |
| Re-organise front line services at the housing offices, to assist customers who want to make a telephone enquiry or have an interview with staff. | 100% | J. Prince |  |
| Introduce a specialist nuisance team to tackle local nuisance issues | 100% | M. Jones | September 2001 |
| Implementation of extended services in relation to private sector housing and the development of a range of interventions to prevent the decline of housing markets and to aid the regeneration of the city | 70% | John Wooderson | Government guidance now in place and being reviewed |
| KEY OBJECTIVE | PERCENTAGE COMPLETED | OFFICER RESPONSIBLE | COMMENTS |
| The development of a range of Marketing and Communications projects emerging out of the Marketing Strategy for the Housing Service. | 75% | Sue Hill | Internet/Web development well advanced. Specific success with the Marketing of Elderly Services and Strategy and National Recognition for success of Independence Day Event. Team currently working on a range of projects including - cash collection - ASBO team marketing - Neighbourhood Wardens - Welcome Pack - Clearance Pack - Homeswap Pack - Renting a Home Booklet |
| Improve recruitment and training within the directorate. | 50% | Doug Hall | New Training Strategy Drafted. Training Plan by 31 March 2002. Some new recruitment processes introduced. Evaluation required |
| Reduce sickness levels | 30% | Doug Hall | New attendance management policy introduced. Some training to be given. Responsibility for absence levels lies with managers. |
| Improve customer feedback across all services | Private Sector Housing 30% | John Wooderson | Service Charter to be developed by December using Wigan Best Value Review as a template |
| Improve the delivery of the implementation of the Corporate Equality of Service Delivery Policy. | 50% | M Leigh |  |