Report to Environmental Scrutiny Committee

Development Control Improvement Plan

Progress Update, February 2003

The Speed of Processing of Planning Applications

Percentage of Planning Applications determined by Officers

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date (31.12.02) |
| --- | --- | --- | --- |
| 1. Percentage of major planning applications given a decision within 13 weeks government target 60% - BVPI 109a) | 33% | 60% | 44% |
| 2. Percentage of minor planning applications given a decision within 8 weeks (government target 65% - BVPI 109b) | 60% | 65% | 62% |
| 3. Percentage of other planning applications given a decision within 8 weeks (government target 80% - BVPI 109c) | 77% | 80% | 80% |
| 4. The time from initial receipt of a planning application to and arriving with the case officer. | 11 days | Within 3 days | 10 days (7.6 days for January) |
| 5. The number of decisions delegated to officers as a percentage of all decisions, (government target of 90% to be achieved by all authorities every year – BVPI 188) | 65.7% | 90% | 72.24% |
| 6. The number of Tree Preservation Order Applications determined within 6 weeks | 36% | 50% | 50% |

| Action Point | Action Required | Timetable | Actual Progress | Comments |
| --- | --- | --- | --- | --- |
| R1 Implement Oce process review to move to a digitally based service | Send out to tender Appoint FM contractor Implement action plan | August 2002 October 2002 November 2002 | Achieved Achieved Progressing - Pilot document management project being initiated |  |
| R2 Extend the use of GIS to speed processes up and improve quality including:- accuracy of data reliability and consistency of data comparison of multiple data seta | Plot applications Input and correct constraint and historic data to speed up flow and improve accuracy Upgrade computer system to integrate with GIS (Uniform version 7) Introduce use of postcodes Acquire and install higher spec computers | Achieved March 2004 June 2003 2003/2004 2002/2003 | In progress In progress Included in computer system upgrade In progress Computers ordered |  |
| R3 Ensure adequate staffing levels and flexible structure | Obtain authority for DC Manager to recruit establishment posts under delegated authority Flexibility of structure achieved through use of small applications team Respond to peaks of work and specific tasks by use of contract services |  | Achieved Budget allocated | Small applications team established. This team, led by a Principal Planning Officer supports the 2 area teams (north and south). |
| R4 Further develop the performance culture Focus staff on key improvements | Incorporate performance issues and target setting into appraisal system Staff training | October 2002 | Achieved Achieved |  |
| R5 Modernise how the City Council consults with regular users to secure quicker and more efficient transactions | Develop electronic consultation with consultees Commence consultation with regular customers via email E-consultation with all consultees | April 2003 September 2003 April 2004 | Limited interest, however, this will follow the establishment of document management and upgrade of planning applications computer system. Both projects have been initiated. |  |
| R6 Increase the percentage of planning applications determined by officers | Review scheme of delegation Report to Lead Member Report to Chair of Panel Consult all elected members Consult Planning User Panel Report to Cabinet and Council Introduce and publicise new scheme | May 2002 June 2002 July 2002 July/August 2002 September 2002 September 2002 October 2002 | Achieved Achieved Achieved Achieved Achieved Community Committee consultation substantially achieved. Introduce April 2003 |  |
| R7 Improve the speed of processing Tree Preservation Order applications | Additional staff (planning assistant) Use of GIS – TPO data Arboricultural advice | 2002/2003 | Achieved Digitising of TPO data has commenced. Achieved |  |
| R8 Improve access to service | Install public access package to Uniform version 7 Engage with corporate GIS development to facilitate customer access to service data including location of TPOs, listed buildings, conservation areas. | 2003/2004 2004 | This will follow introduction of planning applications computer system upgrade. |  |

# Customer Relations

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| 1. Number of hours the office is open to visitors | 37 hours per week | 40 hours per week | 40 hours per week |
| 2. Percentage of applications that can be submitted on line | NIL | NIL | NIL |
| 3. Planning Information available to minority groups |  | Produce multi-lingual pamphlet | Draft pamphlet produced |
| 4. Customer Satisfaction – The percentage of customers satisfied with the service they received (Top Quartile – 81%) | 87% (2000/2001) | No target for 2002/2003 Survey to be undertaken 2003/2004 | _ |

| Action Point | Action Required | Timetable | Actual Progress | Comments |
| --- | --- | --- | --- | --- |
| R9 Extend opening hours on Thursdays from 8.00am to 7.00pm | Produce protocol Consult staff Liaise with Building Managers re opening, security issues etc Publicise Staff rota Commence opening | Commence opening 26 September 2002 | Achieved Opening commenced on 3rd October, 2002. |  |
| R10 Improve the web site | Enable applications to be submitted via the web Incorporate search facility Public access to database | January 2004 | Signed up to planning portal Upgrade of planning application computer system confirmed – this includes public access module and search facility |  |
| R11 Improve access to the service by Black and ethnic minority groups | Produce multi-lingual leaflet and poster promoting the service Promote service with talking news | 2002/2003 | Achieved Language-line adopted by City Council |  |
| R12 Improve reception by implementing reception action plan | Highlight columns making them more visible Improve layout of reception furniture Provide better stands for documents | November 2002 to April 2003 | Achieved |  |
| R13 Publish service standards and information on planning applications on web site and poster in reception | Update website Produce poster | Achieved and review annually | Achieved and review regularly |  |
| R14 Introduce Duty Officer system | Establish protocol Train staff Produce rota | January 2003 | Achieved |  |
| Medium Term |  |  |  |  |
| R15 Submit charter mark bid to maintain continual improvement on customers issues | Produce draft Submit bid | 2003/2004 | This will be progressed when the assessment/application criteria is finalised |  |
| R16 Implement Peer Review Group 4 strategy | Monitor black and ethnic minorities Improve access to service | 2003/2004 | Monitoring commenced Impact assessment of Planning and Transportation Regulatory Panel and planning application process being undertaken. Monitoring commenced. |  |
| Long Term |  |  |  |  |
| R17 Develop strategy for access to services via Contact Centre and One Stop Shop | Engage with corporate strategy | 2004/2005 | Implementing corporate document management system to link with Contact Centre and One Stop Shops | This is subject to pilot project being successful. If not the original Oce project will be initiated. |

Quality of Outcomes/Added Value

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to 31.12.03 |
| --- | --- | --- | --- |
| 1. The percentage of plans which have been amended prior to a decision being taken to improve quality of outcome | No data |  | 1473 |
| 2. The number of maladministration findings | 1 | 0 | 0 |
| 3. The percentage of appeals allowed | 35% | 35% | 42% |
| 4. Percentage of enforcement cases resolved within 13 weeks |  | 70% | 76% |
| 5. Number of formal complaints about the service (non-ombudsman & upheld) | 0 | 0 | 0 |
| 6. % of S.106 Agreements (planning gain) secured and required by policy | 100% | 100% | 100% |
| 7. Applicants of 50% of major planning applications engaged with Development Team | - | 25% | 7.8% |

| Action Point | Action Required | Timetable | Actual Progress | Comments |
| --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |
| R18 Publicise the Development Team Approach | Publicised on the website and ongoing |  | Achieved and progressing |  |
| R19 Proactive compliance checking | Establish framework Link with Building Control Train staff Publicise | 2003/2004 | Commence April 2003 |  |
| R20 Adopt SPG for Telecommunications | Complete consultation Approval by Council | January 2003 March 2003 | Not Achieved Some rewording of the document necessary to use plainer language. This followed community committee consultation. Expected completion June 2003 |  |
| R21 Introduce members review of decisions | Produce protocol Introduce members inspection | 2002/2003 | Achieved Inspection undertaken November 2002 |  |
| Medium Term |  |  |  |  |
| R22 Produce Planning Application checklist to improve quality of submission of planning applications | Adopt national planning application checklist | 2003/2004 | Prior to adoption of national planning checklist, Draft Check list has been produced |  |
| R23 Review staff manual on consultation | Produce staff manual Train Staff | 2003/2004 | Progressing Draft manual has been produced Staff training on consultation has commenced |  |
| R24 Review existing SPG for Hot Food Uses | Await issue of Government proposals in respect of revisions to Use Classes Order Report to Lead Member Consultation Address responses Lead Member Council | 2003/2004 | Government proposals on changes to Use Classes Order not yet issued |  |
| R25 Commission Greater Manchester Geological Unit to monitor major minerals and waste development and ensure compliance with conditions | Produce service agreement Implement | 2003/2004 | Progressing |  |
| Long Term |  |  |  |  |
| R26 Produce new Supplementary Planning Guidance and review existing following review of Unitary Development Plan | A range of topics will be identified by the reviewed UDP which will require the production of SPG | 2003/2004/2005 | The topics identified for SPG in the first deposit draft UDP have been identified |  |

Transparency, Probity, Fairness and Consistency in Decision-Making

| Indicator | 2001/2 Baseline | 2002/3 target | 2002/3 actual to date |
| --- | --- | --- | --- |
| Number of award of costs against City Council | 0 | 0 | 0 |
| Number of complaints received and upheld relating to local Code of Conduct | 0 | 1 | 1 |
| Number of complaints received and referred to National Standards Committee and upheld | 0 | 0 | 0 |

| Action Point | Action Required | Timetable | Actual Progress | Comments |
| --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |
| R27 Revise Local Code of Conduct for Officers and Members dealing with planning matters in light of new publicised national and LGA guidance | Produce report Report to Lead Member Report to Council Implement and train staff and members | 2002/2003 March 2003 | Substantially Achieved Code of conduct has been revised. Reported to Lead Member 2nd December 2002 Reported to Standards Committee on 2nd December 2002 Reported to Planning and Transportation Regulatory Panel on 19th December 2002 Awaiting comments of District Audit – aim to report to Council March, 2003 |  |
| R28 Produce Quality Assurance procedure for Planning and Transportation Regulatory Panel | Produce draft procedure Report to Lead Member and Chair of Regulatory Panel Consult members Train Members Implement | 2002/2003 | Achieved Achieved Achieved Achieved Achieved Achieved | April 2002 June 2002 September 2002 Reported to Lead Member with final draft December 2002 Reported to Regulatory Panel December 2002 Approved by Chairman of Regulatory Panel January 2003 Implemented January 2003 |
| Medium Term |  |  |  |  |
| R29 Produce policy on achieving a responsive dialogue with local people rather than just consultation (see Camden and Wirral) | Undertake research Produce draft policy Report to Lead Member Undertake consultation Report to Lead Member Train staff/implement and publicise | March 2003 September 2003 October 2003 November 2003 February 2003 March 2004 | Commence project in March 2003 |  |
| R30 Improve reporting of planning applications to Planning and Transportation Regulatory Panel | Improve layout of furniture in committee room Introduce more effective presentation techniques Improve access to committee rooms Improve customer care | 2004 |  |  |

Overall Conclusions

The critical performance indicators relate to the speed of processing of planning applications and the percentage of planning applications determined by Officers. These are Best Value Performance Indicators and are utilised in the Comprehensive Performance Assessment. Whilst the "other" planning applications are on target (80%), the major and minor planning applications speed of processing, whilst improving, are not yet on target.

The Improvement Plan addresses this. Increased officer delegation (R6) will be in place from April, 2003 and with the benefits arising from Document Management (R2) and the planning applications computer system upgrade (R2), improvements in performance management (R4), electronic consultation (R5), the aim is to achieve all of this sections performance targets in 2003/2004. Prince 2 will be used for project management purposes for Document Management and the computer upgrade.

In terms of Customer Relations, the office has extended opening on Thursdays (R9) and access to the service has substantially improved through the introduction of the website (R10) and the adoption of languageline (R11).

Quality of Outcomes/Added Value is a critical area of the planning system and the results are very positive in this area. There have been no findings of maladministration, but the appeals allowed record is 7% below target, enforcement is exceeding the target whilst planning gain is being secured when required in all cases. More major planning applications need to undergo the Development Team Approach since the target is 25% but only 7.5% has been achieved. It should be noted, however, that the criteria has only recently changed to include all major applications. Improvements in the promotion and publicising of the approach should encourage more developers to use the initiative. The Development Planning Best Value review Improvement Plan indicates the DTA will be reviewed in summer 2003.

A significant improvement is the member review of planning decisions. This was a valuable exercise involving members and officers with an external perspective provided by Doctor Roy Darke of Oxford Brookes University Planning School. He also provided a very positive assessment of the event.

The indicators for Transparency, Probity, Fairness and Consistency in Decision-making are positive. There were no awards of costs against the City Council on planning appeals, no upheld complaints to National Standards Committee and one upheld by the Standards Board.

A significant improvement is the Quality Assurance achieved by the Planning and Transportation Regulatory Panel and the revisions to the Planning Code of Conduct. This will be introduced once District Audit have responded and the Code has been adopted by Council.

Overall, good progress is being made in achieving the aims of the best value review.