## PUBLIC
REPORT TO NEW PROSPECT BUDGET and
PROCUREMENT COMMITTEE 27.5.04
PUBLIC SECTOR HOUSING
INVESTMENT MONITORING
BACKGROUND
1 | Board members are reminded that NPHL manages the programme
on behalf of the City Council
2 | The resource provision was agreed by the City Council as part of :-
a) The HRA 2003/4 Budget Report
b) The City Council Capital Programme 2003/4
3 | 2003/4 PROGRAMME
A comparison of the resources for 2003/4 with the current outturn
spend can be summarised as follows:-
|  |  | capital | revenue | total
|  |  | £m's | £m's | £m's
| resources |  | 20.891 | 20.988 | 41.879
| actual spend |  | 18.135 | 20.839 | 38.974
| variance |  | -2.756 | -0.149 | -2.905
Subject to the approval of the City Council the resources of £2.905m
not used in 2003/4 can be carried forward into 2004/5 to fund
capital programme slippage from 2003/4 and the revenue commitments
arising from the 2003/4 repairs programme
4 | 2004/5 PROGRAMME
A comparison of the resources for 2004/5 with the current forecast
spend can be summarised as follows:-
|  |  | capital | revenue | total
|  |  | £m's | £m's | £m's
| forecast spend |  | 25.883 | 22.175 | 48.058
| resources |  | 24.608 | 19.214 | 43.822
| resource transfer |  | -2.961 | 2.961 | 0
| revised resources |  | 21.647 | 22.175 | 43.822
| overprogramming |  | 4.236 | 3.5527e-15 | 4.236
4.1 | The forecast spend includes the estimated slippage and revenue
commitments arising from the 2003/4 programmes
4.2 | The resources assume that the £2.905m of unused resources from
2003/4 can be carried forward into 2004/5
4.3 | To enable a balanced revenue budget to be achieved HRA resources
can be transferred from the Capital programme resources to the
revenue budget .This will result in an overprogramming level of £4.236m
on the Capital programme and will represents 20% of capital programme
resources