______________________________________________________________

REPORT OF THE DEPUTY DIRECTOR OF HOUSING AND PLANNING

______________________________________________________________

TO THE LEAD MEMBER FOR HOUSING FOR INFORMAL

ON 20th May 2008

______________________________________________________________

TITLE: Update of Salford’s Affordable Housing Programmes 2004-06 and 2006-08.

______________________________________________________________

RECOMMENDATIONS:  That Lead Member for Housing:

- Notes the progress and amendments to date in the delivery of the 2004-06 and 2006-08 Affordable Housing Programmes (AHP).

______________________________________________________________

1. 	EXECUTIVE SUMMARY

1.1	This report provides the Lead Member with an overview of the delivery of the AHP over the last two bidding rounds (2004-2006 and 2006-2008).

1.2	The 04-06 update informs Lead Member two of the three schemes have been completed, with the third expected March 09.

  - The report also provides an update on the final allocation and progress in delivering the 06-08 programme.  Following amendments and changes, the final allocation was 265 units, with £18,147,624 grant funding and a total investment of £36,726,363.  Of the originally approved schemes 2006-2008, there are three schemes that have been identified as at risk of not being delivered within Housing Corporation timescales.  As a result actions have been undertaken by the Council and the RSLs to mitigate risk in two cases, but in one case funding has been returned to the Housing Corporation.  The Council and its partners are working to identify a way forward for this scheme  and Lead Member will be kept informed of progress.

______________________________________________________________

BACKGROUND DOCUMENTS:

Lead Member for Housing report: Update of Salford’s Affordable Housing Programmes 2004-06 and 2006-08 December 07.

Lead Member for Housing report: Review of Salford’s Affordable Housing Programme 2004-2008 and planning for the 2008-2011 bidding round (June 2007).

_____________________________________________________________

ASSESSMENT OF RISK:

The potential for not delivering the schemes allocated funding in the AHP 2006-2008 places future allocations to Salford for 2008-2011 at risk.

______________________________________________________________

SOURCE OF FUNDING:

Housing Corporation grant from their Affordable Housing Programmes 2004-06 and 2006-08.

______________________________________________________________

LEGAL IMPLICATIONS:

Ian Sheard

Ext: 3084

Confirms that there are no comments from the legal viewpoint

FINANCIAL IMPLICATIONS:

Nigel Dickens

Ext: 2585

Confirms that there are no financial implications

## COMMUNICATION IMPLICATIONS:

## Councillors, senior staff and partner organisations need to be kept informed of those AHP bids at risk of non-delivery. On completion, scheme openings can provide a positive image of Salford to the wider national audience.

VALUE FOR MONEY IMPLICATIONS:

By working pro-actively with partners and delivering schemes we would seek to obtain best value for money from the grant allocation received from the Housing Corporation.

CLIENT IMPLICATIONS:

Many of the schemes that have received an allocation are housing developments on Council owned land and/or within development agreements that the Council has with its private developer partners. Securing the grant allocated is intrinsically linked with the progress of master plans, site assembly and planning applications being delivered by the Council’s private developer partners, Salix Homes or Urban Vision on behalf of the Council..

PROPERTY:

The developments are on Council owned / former owned land or owned by partners and RSLs.  Details are presented within the scheme summary information.

_____________________________________________________

HUMAN RESOURCES: Whilst delivery of schemes rests with the RSLs, Salford City Council is responsible for monitoring the delivery of AHPs.

CONTACT OFFICER:

Mark Hart: Strategy and Partnerships Team

0161 793 2039

mark.hart@salford.gov.uk

______________________________________________________________

WARD (S) TO WHICH REPORT RELATE (S):

Langworthy

Broughton

Kersal

Irwell Riverside

Irlam

Cadishead

Swinton North

Winton

Claremont

____________________________________________________________

KEY COUNCIL POLICIES:

Housing Market Renewal Update 08

Draft Housing Strategy 2007-2010,

Salford Supporting People Strategy 2005-2010.

______________________________________________________________

DETAILS:

2.	2004-2006 Affordable Housing Programme

2.1	Of the original 2004-2006 programme, three schemes were identified as at risk of non-delivery, but following suitable and appropriate actions two schemes have been completed, whilst the other has commenced building on site and is due to complete in March 09.  Further details are provided below. Full details of all AHP 2004-06 schemes can be found in Appendix 1.

2.2	Richmond Hill / Broughton Tavern (Irwell Valley Housing Association): The Irwell Valley Scheme consisting of 57 units, with grant allocation of £849,108 and the total scheme cost was  £8,246,273 was successfully opened and launched by Secretary of State, Rt Hon Hazel Blears MP in March 2008.

2.3	Japan Street (Great Places): Japan Street is a  development of 6 x 4 bed houses in the Broughton Village HMR neighbourhood.  The delay in progressing the Japan Street scheme has arisen due to a worn dirt track at the site, which the City Council identified as a footpath. Great Places was granted planning permission for the development of the six units by the City Council, on condition of a footpath closure order being obtained.  Great Places had been in negotiations with the City Council over a contract sum for the development of the land, but pulled out of these negotiations until the issue of the footpath closure had been resolved.  This has now been resolved.

2.3.1	Due to constant communication between Great Places, the Housing Corporation and the City Council, Great Places has been permitted to retain the £555,317 of grant funding  despite the delays.  The scheme started on site in January 08 and the expected completion date is March 09.

2.4	Phase 12 (William Sutton): This new build development for 13 units for rent consisted of: 3 x 2 bed houses, 5 x 3 bed houses, 4 x 4 bed houses & 1 x 2 bed bungalow.  The total cost of this scheme was £1,605,268 with Housing Corporation grant funding of £494,012.

2.4.1	The initial developers unfortunately went into liquidation towards the end of the project, which resulted in handover occurring in April 08.   The Council and Housing Corporation were informed throughout.

3.	2006-2008 National Affordable Housing Programme

  - Salford was originally allocated £16,899,544 for the 2006-2008 National Affordable Housing Programme (NAHP).  Changes to the programme including withdrawal and amendments to schemes in Salford, plus the successful allocation of opportunities arising from slippage from the regional programme to Salford has resulted in a final allocation of 265 units, with grant funding of £18,147,624 and a total investment of £36,726,363.

  - Progress to date with the 2006-2008 programme is very encouraging, with all but three schemes completed.  Of those remaining one is expected to complete by March 09.  However, two schemes have not been pursued, but the funding from one scheme was reallocated to another NAHP scheme in Salford.  Although one allocation had to be returned to the Housing Corporation, the City Council and its partners are working to identify a way forward for this scheme and Lead Member will be kept informed of progress.

  - In addition Salford successfully secured an additional three schemes through under spend in the NAHP two of which have already been completed and a third is expected to complete August / October 08.  Details of progress with all these schemes are given below.  Full details of all NAHP 2006-08 schemes can be found in Appendix 2.

  - Duchy Bank (Manchester Methodist Housing Association - Great Places Housing Group):. The Great Places development of 37 new build units with a grant allocation of £320,000 and total scheme costs of £1,196,050 was completed and launched by Rt Hon. Hazel Blears in April 08.

  - Devonshire Square (Contour):  Contour made a successful bid to the Housing Corporation for £804,800 of grant funding to build 30 houses of New Build HomeBuy . This scheme was completed March 08 with total scheme costs expected to be £3,875,796.

3.5.1	To support the marketing and promotion of all the units on the development, City Spirit and Contour HA have jointly appointed Savills.  Savills are also being used to market the Hamilton St scheme (see 3.8 for details).

3.6	Broughton Green (Agudas Israel):  This development was successful in attracting under spend from elsewhere in the region.  Located in Broughton Green, this development provided 20 affordable rented houses consisting of: 2 x 3 bed, 8 x 4 bed, 6 x 5 bed and 4 x 6 bed.  The total cost for the schemes was £5,294,325 with a £2,600,070 grant secured.

3.6	Lower Broughton Phase 1 (Contour): Contour successfully bid for £8,160,000 grant with a total cost of £13,222,473 with 102 rented units.  Phase 1a and b consisted of: 14 x 2 bed apartments, 11 x 2 bed houses, 16 x 3 bed houses and 3 x 4 bed houses.  Phase 1c and d consisted of: 20 X 2 bed apartments, 15 X 2 bed houses, 20 x 3 bed houses and 3 x 4 bed houses.  A total of 92 affordable units for social rent have been completed and successfully let to residents, with a further 10 affordable units for rent to be provided in Phase 4.  These 10 are expected to be completed in September 08.

3.7	Lower Broughton Phase 4 (Contour): Originally this scheme was secured in the 08-11 NAHP, but was brought forward and included in the 06-08 programme due to opportunities arising from slippage elsewhere in Housing Corporation funding.  This scheme will provide 40 rented units consisting of 30 x 2 bed apartments and 10 x 3 bed houses.  The total cost is £5,440,091 with a grant of £2,320,000 (£58,000 per unit).  The scheme started on site in January and is due to be completed in August / October 08.

3.8	Hamilton Street (Contour): This scheme is situated in the Broughton Neighbourhood Renewal Area.  The site includes the development of nine new build units.  Richardson Projects started on site in December 2006 and completed construction in December 2007 with all nine properties handed over to Contour.  The total cost of the scheme was £1,288,543 with a grant of £278,500.

3.8.1	Phase 1 of the scheme was for 6 x 3 bed S/O houses.  However, grant funding of £110,000 was recycled from the Chapel St allocation (see 4.3 below) to purchase the remaining three units (mentioned above).  These 3 x 3 bed houses have now been converted to S/O.

3.9	Kersal High School (Contour):  Salford successfully secured two allocations for the Kersal High School site from the 2006-2008 AHP.  The bids were for a mix of eight houses for social rent and for shared ownership, as part of a wider development plan in the NDC area of Charlestown and Kersal.  The total cost for the scheme was £1,186,173 with a total allocation of £570,000.

3.9.1	Phase 1 was for five rented 2/3 bed houses at a cost of £700,714 with a grant of £458,000.  Phase 2 was for 3 x 2 bed houses for New Build Homebuy at a cost of £485,459 with a grant of £112,000.  Following a series of meetings to overcome unforeseen planning and contractual issues between the council and the developer, all eight units have been completed and successfully sold or let.

3.9.2	A further three units for New Build Home Buy will be completed by August 08, but 06-08 funding wasn’t secured.  Contour have expressed an interest in seeking to submit a bid to the Housing Corporation through the Regular Market Engagement (RME) to fund this.

3.10	Salford Phase 13 (William Sutton): New Build Homebuy scheme provides 6 x 2 and 3 bedroom houses and 8 x 2 bedroom apartments.  William Sutton was successful in securing £772,254 grant funding, total scheme costs being £1,438,352.  Delays due to the diversion of a gas main and access to the site issues were resolved and the scheme was completed by March 2008.

3.11	Kimberley Street and Symonds Street (Great Places): Great Places identified two council-owned properties on Kimberley Street and one on Symonds Street, that were long-term voids in need of extensive refurbishment and that were causing blight to the neighbourhood.  Following lead member approval (November 06) these units were sold to Great Places who successfully refurbished and let them in the summer 07.  The grant allocation transferred from Ackworth Rd, was £80,000 with the total cost of the scheme being £119,701.

3.12	Salford Women’s Only Accommodation (Great Places): This supported accommodation scheme is specifically for resettling women who have been accommodated inappropriately in secure settings due to their health related offending past. Great Places, working in partnership with care provider ‘Imagine’ were successful in obtaining £692,000 of grant monies to build 8 x 2 bedroom apartments that will specifically meet the needs of this client group. Total scheme costs will be £1,665,300. All apartments are for social rent.

3.12.1This scheme has suffered a number of delays, and the Housing Corporation were kept fully aware.  All issues have now been resolved and works started on site in May 2007 (originally May 06) and was completed in January 2008.

### 4.0	Schemes at risk 2006-2008 AHP

4.1	Of the originally approved schemes 2006-2008, there are three schemes that have been identified as at risk of not being delivered within Housing Corporation timescales.  Actions by partners to mitigate risk have been successful in two cases, but in one case funding has been returned to the Housing Corporation.  Further details are provided below.

4.2	Langworthy Churches (Previously Eccles New Road scheme -  Great Places): Great Places submitted a bid to the Housing Corporation for a development of 24 x 2 bed and 6 x 1 bed apartments.  Part way through negotiations to purchase the site from private ownership, negotiations stalled and due to uncertainty the Housing Corporation agreed to transfer the allocation to the Langworthy Churches scheme.  However, there was a minimal reduction in the grant from funding secured from £1,644,000 to £1,550,000.

4.2.1	The Langworthy Churches scheme is a mixed-use development incorporating 16 two-bed and 6 one-bed apartments, the church, a community centre, a sports hall and a café.  Due to the substitution of the original scheme the timescales for delivery have been delayed. The scheme started on site in March 2007 (previously June 2006 - Eccles New Road).  However there have been contractual issues between the developers and the contractors. These issues have regrettably not been resolved and have resulted in the termination of the contract with the contractor. As a result there are to be further delays to the completion of the build, now expected March 09.  Any additional costs are being borne by the developers and Great Places.  Progress will continue to be monitored.

4.3	Chapel Street (Contour): Contour received an allocation of £110,000 from the Housing Corporation for five New Build HomeBuy units, which would have been part of a larger private development being led by Hightop Developments Limited.  However, soon after receiving the allocation, plans for the development by Hightop were withdrawn.

4.3.1	Subsequently Contour appraised a number of development sites in the Chapel Street area but have been unable to secure a scheme due to the high land values.  	As a result, Contour successfully sought Council support and Housing Corporation approval to use the grant allocation on this scheme to fund an additional three S/O houses on the Hamilton Street scheme.  Although this resulted in the net loss 2 units (the original Chapel Street allocation was for five units) the total number of people the units are designed for will be the same (15 people).  Furthermore, Contour have provided the Housing Corporation with two non grant funded units to ensure that build figures and targets are met.

4.4	St Mark’s Lane (Great Places): This scheme lies adjacent to the Japan Street site referred to in section 2.5 of this report. Great Places made a successful bid to the Housing Corporation for £488,000 of grant funding with total scheme costs expected to be £1,075,200. The site includes the development of 4 x 3 and 4 x 4 bed houses, half for rent and half for New Build HomeBuy.

4.4.1	Due to the sites close proximity and similar issues to Japan Street and the risk of a Town and Village Green (TVG) status application, after consulting with the Council and Housing Corporation, Great Places were unable to pursue this option within the agreed scheme deadline and returned the funding to the Housing Corporation.  Great Places and the Council are working to identify a way forward.

5.0       Conclusion

5.1      The Lead Member for Housing is asked to:

- Note the delivery of the outstanding AHP 2004-06 schemes, specifically Japan Street (Great Places), Phase 12 (William Sutton) and Richmond Hill / Broughton Tavern (Irwell Valley).

- Note the progress made to date in the delivery of the 2006-2008 Affordable Housing Programme, and actions identified to address those schemes that have been identified as at risk of not being delivered within Housing Corporation timescales.

Bob Osborne,

Deputy Director of Housing and Planning

| Appendix 1 – Housing Corporation ADP 2004-2006 |
| --- |
| Neighbourhood | Ward | RSL | Scheme | Total costs | Grant | No. of Units | New build / Rehab | Tenure | Type |
| Seedley and Langworthy | Langworthy | MMHG | Salford Re-improvements | £427,904 | £213,953 | 16 | Rehab | Rent | 16 x 2 / 3 bed houses (works to existing properties) |
|  | Langworthy | MMHG | Langworthy rehabs | £481,163 | £434,513 | 6 | Rehabs | Rent | 6 x 2 / 3 bed houses |
|  | Langworthy | MMHG | Alpha street phase 2 | £1,126,888 | £661,768 | 8 | New build | Rent | 8 x 2 / 3 bed adapted bungalows |
|  | Langworthy | MMHG | Improvement for Sale 1 | £66,751 | £20,000 | 1 | Rehab | Shared ownership | 1 x 2 bed house |
| Broughton Village | Broughton | Space | Salford re-improvements | £385,882 | £166,965 | 21 | Rehab | Rent | 21 x 2 / 3 bed houses (work to existing properties) |
|  | Broughton | Space | Salford re-improvements | £201,500 | £118,684 | 13 | Rehab | Rent | 13 x 2 / 3 bed houses (works to existing properties) |
|  | Broughton | Space | Winterford Road | £1,077,292 | £637,541 | 11 | New build | Rent | 8 x 2bed bungalows and 3 x 2bed wheelchair accessible bungalows |
|  | Kersal | Space | Japan Street | £840,379 | £555,319 | 6 | New build | Rent | X 4 bed houses |
| Pendleton | Langworthy | WSHA | Salford ph 11 | £651,834 | £277,506 | 7 | New build | Rent | 2 x 2 bed houses, 3 x 3 bed houses and 2 x 4 bed houses |
|  | Langworthy | WSHA | Salford ph 12 | £1,605,268 | £494,012 | 13 | New build | Rent | 1 x 2 bed bungalow, 3 x 2 bed houses, 5 x 3 bed houses 4 x 4 bed houses |
|  | Irwell Riverside | IVHA | Richmond Hill / Broughton Tavern | £8,246,273 | £849,108 | 57 | New build & rehab | Shared ownership and sale | 45 x New Build HomeBuy & 12 sale |
|  | Irwell Riverside | IVHA | Springfield Lane (US) | £6,875,840 | £1,053,914 | 50 | New build | Shared ownership | 50 x 1 / 2 bed apartments |
|  | Irwell Riverside | IVHA | Carolina House | £738,263 | £248,321 | 6 | New build | Shared ownership | X 2 / 3 bed houses |
| Supported accommodation | Irlam | St. Vincent’s | The Crescent | £248,040 | £78,966 | 2 | New build | Rent | 2 x wheelchair accessible bungalows |
|  | Cadishead | St. Vincent’s | Sussex Road | £292,500 | £199,789 | 2 | New build | Rent | 2 x wheelchair bungalows |
|  | Cadishead | St. Vincent’s | Hamilton Avenue | £513,630 | £319,051 | 4 | New build | Rent | 2 x wheelchair bungalows |
|  | Langworthy | MMHG | 81 Lower Seedley Road | £69,222 | £34,611 | 1 | Rehab | Rent | 1 x 4 bed house |
|  | Claremont | MMHG | 94 Claremont Road | £69,222 | £34,611 | 1 | Rehab | Rent | 1 x 3 bed house |
| Total |  |  |  | £23,917,851 | £6,398,632 | 225 |  |  |  |

| Neighbourhood | Ward | RSL | Scheme | Total Costs | Grant | No. of Units | SOS | PC | New build/ Rehab | Tenure | Type |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Seedley and Langworthy | Irwell Riverside | MMHG | Duchy Bank | £1,196,050 | £320,000 | 10 | 09/06 | 04/08 | New build | NBHB | 6 x 2/3 bed houses |
|  | Langworthy | MMHG | Langworthy South East (Langworthy Churches) | £2,375,000 | £1,550,000 | 22 | 10/07 | 12/08 | New build | NBHB | 22 x 2/3 bed houses |
| Broughton | Broughton | Contour | Devonshire Square | £3,875,796 | £804,800 | 30 | 08/06 | 09/07 | New build | NBHB | 30 x houses |
|  | Broughton | Contour | Clarence street Phase 1a and b | £5,703,812 | £3,520,000 | 44 | 10/07 | 12/08 | New build | Rent | 14 x 2 bed apartments 11 x 2 bed houses 16 x 3 bed houses 3 x 4 bed houses |
|  | Broughton | Contour | Clarence street Phase 1 c and d | £7,518,661 | £4,640,000 | 58 | 10/08 | 08/09 | New build | Rent | 20 x 2 bed apartments 15 x 2 bed houses 20 x 3 bed houses 3 x 4 bed houses |
|  | Broughton | Contour | Phase 4 | £5,064,650 | £2,320,000 | 40 | 02/08 | 10/08 | New Build | Rent | 30 x 2 bed apartments 10 x 3 bed houses |
|  | Broughton | Agudas Israel | Broughton Green Phase 1 | £3475,000 | £1,700,070 | 12 |  |  | New Build | Rent | 3 x 4 bed 5 x 5 bed 4 x 6 bed |
|  | Broughton | Agudas Israel | Broughton Green Phase 2 | £1,819,325 | £900,000 | 8 |  |  | New Build | Rent | 2 x 3 bed 5 x 4 bed 1 x 5 bed |
| Hill Top area | Broughton | Contour | Hamilton Street Phase 1 | £859,029 | £168,500 | 6 | 09/06 | 12/07 | New build | NBHB | 6 x 2 bed houses |
|  | Broughton | Contour | Hamilton Street Phase 2 | £429,514 | £110,000 | 3 | 09/06 | 12/07 | New Build | NBHB | 3 x 2 bed houses |
| North Irwell Riverside | Kersal | Contour | Kersal High School Rent | £700,714 | £458,000 | 5 | TBC | 08/07 | Rent | Rent | 5 x 2/3 bed houses |
|  | Kersal | Contour | Kersal High School phase 1 | £485,459 | £112,000 | 3 | TBC | 11/07 | New build | NBHB | 3 x 2 bed houses |
| Pendleton | Langworthy | William Sutton | Salford phase 13 | £1,438,352 | £772,254 | 14 | 11/06 | 11/07 | New build | Rent | 8 x 2 bed apartments 1 x 2 bed house 5 x 3 bed house |
| Swinton | Swinton North | MMHG | Kimberley St and Symonds St | £119,701 | £80,000 | 2 | 11/06 | 04/07 | Rehab | Rent |  |
| Supported accommodation | Winton | MMHG | Salford women’s only accommodation | £1,665,300 | £692,000 | 8 | 05/06 | 05/07 | New build | Rent | 8 x 2bed apartments |
| Total |  |  |  | £36,726,363 | £18,147,624 | 265 |  |  |  |  |  |

# Footnotes

Great Places was established in 2006 after Manchester Methodist Housing Group and Ashiana Housing Association merged.  Space New Living joined the group in January 2007.

# Text boxes

Part 1