## hip mon report 6.10.2000
HOUSING INVESTMENT PROGRAMME (1999/2000-2002/3)
MONITORING REPORT
POSITION AS AT 31.8.2000
1 | SUMMARY OF FORECAST SPEND AND RESOURCES (£M's)
|  |  | 2000/1 |  | 2001/2 | 2002/3
SPEND
|  | COMMITTED | 17.928 |  | 1.286 | 0.222
|  | PROPOSED | 4.801 |  | 15.214 | 9.591
|  | TOTAL | 22.729 |  | 16.5 | 9.813
| RESOURCES |  | 22.42 |  | ? | ?
| RESOURCE SHORTFALL |  | 0.309 |  | ? | ?
2 | POINTS
(a) | Resource excess in 1999/2000
The internal resource savings arising from the 1999/00 resource excess of £0.732m have now
been carried forward into 2000/1 and have been used to reduce the overprogramming level .
(b) | 2000/1 HIP
The 2000/1 HIP(current forecast £22.729m) includes new starts to maximise the resources available
(currently £22.420m)with an overprogramming level (currently £0.309m) to compensate for
likely slippage and savings during the year.
(c) | Eccles Town Centre Redevelopment-replacement council houses
The estimated cost of replacing council houses needing to be demolished is £0.6m .
Provision was made in the original Capital Programme for 2000/1 for this payment to be
made to Housing .However ,following a review of the Eccles Town Centre project ,
it is unlikely that the payment can now be funded in 2000/1.
The current HIP resources for 2000/1 do not include the £0.6m
When the indebtedness to the HRA is next reviewed the £0.6m can be taken into account
along with the effects of the temporary rule / use of capital receipts etc.
3 | Actual spend to date in 2000/1
Payments to the end of August 2000 are £5.479m which represents 24% of the forecast spend
for 2000/1.This can be compared with spend at the end of August 1999 which represented 25%
of the programmed spend
4 | Variations since previous report (Lead Members Briefing 14.7.2000)
| £m's |  |  | 2000/1 | 2001/2 | 2002/3
| spend forecast | current |  | 22.729 | 16.5 | 9.813
|  | previous |  | 22.6 | 16.328
|  | variation |  | 0.129 | 0.172
| resources | current |  | 22.42
|  | previous |  | 21.58
|  | variation |  | 0.84 | ?
| overprogramming | current |  | 0.309
| (underprogramming) | previous |  | 1.02
|  | variation |  | -0.711 | ?