| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- |

REPORT OF

THE HEAD OF HOUSING SERVICES

TO HOUSING LEAD MEMBER on 7th APRIL 2005

TITLE: PUBLIC SECTOR CAPITAL PROGRAMME 2004/05

RECOMMENDATIONS:

- That Lead Member notes the position of the programme as at the 17th March 2005 and receives a further report on the final position for the year.

EXECUTIVE SUMMARY:

This report gives the details of the current position for the 2004/05 Public Sector Capital Programme.

BACKGROUND DOCUMENTS:

(Available for public inspection)

Approved capital programme 2004/05

NPHL Monitoring Data

Financial Information from SAP

ASSESSMENT OF RISK:

Failure to monitor the programme could result in significant overspends or under utilisation of resources, this will have an impact upon decent homes standards.

THE SOURCE OF FUNDING IS:

Not applicable as the report is commenting on the financial position.

LEGAL ADVICE OBTAINED:

Not required for this report.

FINANCIAL ADVICE OBTAINED:

Report prepared by the out stationed Principal Group Accountant for Chief Executive’s.

CONTACT OFFICER:

Nigel Dickens 0161 793 2585

WARD(S) TO WHICH REPORT RELATE(S):

All

KEY COUNCIL POLICIES:

COUNCIL CAPITAL BUDGET 2004/05

DETAILS (Continued Overleaf)

- Background Information

  - The Council has approved a Public Sector Capital Programme of £21.8m for 2004/05 and it is the responsibility of NPHL to manage and monitor this on behalf of the Council.

  - During the last few months’ officers from both NPHL and the Council have been working together to develop a more robust system for the monitoring of schemes and the programme.

  - This is to avoid the year end position for 2003/04 where the programme had underspent by £2.7m as has been previously reported to Lead Member, it will be recalled that these resources have been carried forward.

  - These arrangements have been submitted to previous Lead Member meetings where presentations have been made by colleagues from NPHL and it has been accepted that there are good systems in place to monitor the programme.

- Details of Report

  - Initial Level of Over-Programming for 2004/05

    - The original approved resources by the Council for 2004/05 Public Sector Capital Programme were £21.8m.

    - Following discussions with colleagues in NPHL schemes to the potential value of £26.3m were developed and progressed as part of the programme for 2004/05.

    - This gave an over-programming level of £4.5m or 20% of the programme. Experiences from 2003/04 when the programme underspent indicate that a good level of over-programming is required to allow schemes to be brought forward should others slip.

    - It was considered that this level of over-programming at the start of the year was satisfactory and could be managed through monitoring for the remainder of the year to ensure that for 2004/05 the budget will be fully utilised but not overspent.

  - Actual Position as at 17th March 2005

    - There are a total of 68 elemental scheme surveys, which have been undertaken since the beginning of May 2004. Each of the 68 scheme surveys has now been completed. The surveyors within NPHL have carried out the elemental scheme surveys. Any properties subject to either tenant refusal or no response are being visited further by the customer liaison officers of both NPHL and the partners.

    - There are 66 partnering schemes now on site (98% of the decent homes programme). By the end of March 2005 there will be a total of 67 schemes on site (99%), with the remaining 1 scheme (1%), scheduled to start on the programme in September / October 2005.

    - The four partners are currently undertaking work in their respective geographical areas as follows:

Wates (Eccles), (Worsley & Little Hulton):

- Lancaster Rd, Full Central Heating

- Newlands, Bathrooms/Full Rewires/Kitchens

### Liverpool Rd, Kitchens/Electrical Upgrades

- Higson Ave & Peel Green Rd - Kitchens/Bathrooms/Rewires

- Astley Rd, Kitchens

- The Avenues, Roofing/Repointing/Cavity wall ties

- Peel Green Phase 1, Repointing/Cavity wall ties

- De Traffords/Moorfield, Bathrooms

- Mees Square, Bathrooms

- Albert St, Kitchens/Bathrooms/Electrical Upgrades

- Worsley Rd. North, Roofing/Bathrooms/Rewires

- Bridgewater Rd, Bathrooms

- 53 – 67 Manchester Rd, Kitchens

- Mitchell St., Kitchens

Bramalls (Salford South):

- Moss Meadow, Bathrooms/Electrical upgrades

- Southgarth, Bathrooms/Full Rewires

- Tootal, Heating/Electrical upgrades/Kitchens

- Light Oaks Rd, Electrical upgrades

- Duchy, Electrical upgrades

- Edgehill Rd, Full Rewires/Repointing/Roofing/Cavity wall ties

- Devon Close, Kitchens

- Cressington Close, Kitchens

Whites (Swinton):

- The Valley Estate, Prior to Paint and Full Central Heating

- Worsley Rd, Kitchens/Partial rewires

- Manchester Road South, Partial Rewires/Kitchens

- Parkfield & Moorfield, Bathrooms

- Agecroft, Kitchens/Electrical Upgrades

- Mossfield, Electrical Upgrades

NPHL Maintenance Division (Swinton, Salford North, Eccles):

- Beehive Estate, Prior to Paint

- Albion Stadium, Prior to Paint

- Canterbury Gardens, Prior to Paint

- Lower Broughton 4, Electrical Upgrades

- North Clifden Lane, Kitchens/Electrical Upgrades

- Floral Court, Bathrooms/Full Rewires

- Kersall Cell, Heating/Electrical Upgrades

Pre-Partner Contractors (Swinton, Worsley, Eccles):

- Wardley Est., Partial Rewires

- Temple Drive, Electrical Upgrades

- Dudley Rd. & Cumberland Dr., Heating

- The Meadows, Heating

- Baines Ave, Roofing

- Crossfields, Roofing

- 1 – 5A Warren St., Roofing

    - Out of the 66 schemes on site, 39 schemes (60% of the total schemes) have to date been completed. These schemes are as follows:

- Moss Meadow, Electrical upgrades (21 Properties)/ Bathrooms (1 Property) - Bramall

- Light Oaks Rd, Electrical upgrades (6 Properties)  - Bramall

- Edgehill Rd, Rewires/Roofing/Repointing & Cavity Ties (16 Properties) – Bramall

- Southgarth, Bathrooms (70 Properties) / Rewires (77 Properties) – Bramall

- Duchy, Electrical Upgrades (261 Properties) - Bramall

- Mitchell St, Kitchens (22 Properties) – Wates

- 53-67 Manchester Rd, Kitchens (5 Properties) – Wates

- De Traffords, Moorfield, Bathrooms (20 Properties) – Wates

- Newlands,  Bathrooms (74 Properties)/ Rewires (92 Properties)/ Kitchens (17 Properties) – Wates

- Lancaster Rd, Heating (145 Properties) – Wates

- Albert St, Kitchens (35 Properties) – Wates

- Peel Green Ph1, Cavity Ties (154 Properties) - Wates

- The Avenues, Roofing/Repointing/Cavity wall ties (50 Properties) – Wates

- Liverpool Rd, Kitchens (10 Properties)/Rewires (14 Properties) – Wates

- Astley Rd, Kitchens (37 Properties) – Wates

- Worsley Road North, Rewires (30 Properties) – Wates

- Higson Ave/Peel Green Road, Kitchens (8 Properties)/Rewires (39 Properties)  - Wates

- Worsley Rd, Kitchens (105 Properties), Rewires (110 Properties) – Whites

- Agecroft, Kitchens/ Electrical Upgrades (23 Properties) – Whites

- Parkfield/Moorfield, Bathrooms (86 Properties) - Whites

- The Beehive, Prior to Paint – (245 Properties) NPHL DLO

- Wardley, Partial Rewires (28 Properties) – Pre-Partner Contractor

- Temple Drive, Electrical Upgrades (68 Properties) – Pre-Partner Contractor

- The Meadows, Heating (51 Properties) – Pre-Partner Contractor

- Dudley Rd. & Cumberland Ave. (64 Properties) – Pre-Partner Contractor

- Baines Ave, Roofing (22 Properties) – Pre-Partner Contractor

- Warren Street, Roofing (12 Properties) – Pre-Partner  proe

- Crossfields, Roofing (35 Properties) – Pre-Partner Contractor

    - There is now no over-programming within the forecasts compared to the original £4.5m. This has reduced due to savings on contracts due to not all properties in a scheme being required to be done and revised forecasts being received from partners for schemes on site.

    - As at the 17th March 2005 the actual expenditure incurred was £19.8m or 91% of the approved programme and there are further certified payments in the process of being paid that increase this to £20.3m or 93%. Additionally there are fees to be recharged of approximately £1.5m thereby fully utilising the available resources.

    - Whilst there are still further transactions to be processed it is currently forecast based on the available information that the final figure will be within plus or minus of 1% of the available resources. This is as a result of the excellent programming and monitoring that has occurred during the year.

- Conclusions

  - NPHL have developed a good system for monitoring the projects from both an operational and financial perspective and the information produced is a good management tool.

  - The programme will fully utilise the budget.

- Recommendations

  - That Lead Member notes the position of the programme as at the 17th March 2005 and receives a further report on the final position for the year.