| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- |

#### REPORT OF THE STRATEGIC DIRECTOR OF HOUSING AND PLANNING

### TO THE LEADER MEMBER FOR HOUSING

ON 10th February 2005

TITLE:  BLOCK IMPROVEMENTS TO PROPERTIES IN ‘THE ARROWHEAD’, CHARLESTOWN.

# RECOMMENDATIONS:

- That the proposed Block Improvement of ‘The Arrowhead’ area be approved.

- That the target cost and guaranteed maximum price for Phase Three be approved.

EXECUTIVE SUMMARY:

The Arrowhead area in Charlestown has been identified as a priority for improvement and it is proposed to undertake a block improvement scheme in the area.  The work will be undertaken by Cruden Construction, one of the Council’s two partner contractors for this category of work.  It is proposed that a target cost and guaranteed maximum price for the third stage of this improvement work be approved to enable the scheme to proceed.

BACKGROUND DOCUMENTS:

New Deal for Communities Development Framework and Neighbourhood Renewal Assessment.

## ASSESSMENT OF RISK:

Low

## THE SOURCE OF FUNDING IS: New Deal for Communities and Housing Market Renewal Fund. Grants supported by City Council resources.

LEGAL ADVICE OBTAINED: Yes, from Ian Sheard

## FINANCIAL ADVICE OBTAINED:  Yes from Nigel Dickens

CONTACT OFFICER:    Peter Dunbevand                   0161 793 2877

(Architectural and Landscape Design Service)

# WARDS TO WHICH REPORT RELATES:  Pendleton

# KEY COUNCIL POLICIES:  Procurement Strategy and the Rethinking Construction Implementation Strategy.

##### DETAILS

1.0	BACKGROUND

  - The Arrowhead area in Charlestown (bounded by Cromwell Road, Gerald Road and Seaford Road) has been identified as a priority for housing improvement and a programme of block improvement is proposed.  The area is also within the Housing Market Renewal Fund Pathfinder area.

  - The work will be undertaken by Cruden Construction, one of the Council’s two partner contractors for this category of work.

- THE PROPOSAL

  - ‘The Arrowhead’ comprises 9 shops and 145 houses within the area bounded by Cromwell Road, Gerald Road and Seaford Road.  It comprises 1-19 and 2-32 Beeley Street, 142-194 Cromwell Road, 133-161 Gerald Road, 1-43 and 2-48 Haddon Street, 2-10 Rowsley Street and 105-159 Seaford Road.  The area has been split into three phases for the purposes of carrying out this work.

  - Phases one and two have already been approved and the contract for the work has been awarded under the Council’s Rethinking Construction strategy.  Due to the nature of the contract for the work, by approving phases one and two approval was effectively given to award the entire contract, and the Council would be in breach of contract if it did not now give approval for phase three of the work.  The purpose of submitting this report is to approve the target and guaranteed maximum costs for this phase of the scheme.

  - Work on the first phase of this scheme is due to start on 24th January 2005.

  - Survey work is now completed in respect of a further 67 properties at 163-175 Gerald Road, 180-194 Cromwell Road, 2-48 Haddon Street and 105-159 Seaford Road.

  - It is proposed that the refurbishment work to these properties will include the following:

- Repair of window and door frames [to front of properties]

- New rainwater goods and fascias [to front and rear of properties]

- Re-pointing and repair of brickwork [to front of properties]

- Renewal of bay roofs as required

- Brickwork cleaning [to front of properties]

- Renewal boundary walls [to front of properties]

- Re point and renew capping to rear walls as required

- External painting [to front of properties]

  - The partnership project team has agreed a target cost of £740,527 for this third phase, with a resulting guaranteed maximum price of £777,553.

  - The contractors’ proposal represents a unit cost of £11,052.64 per house.  This compares with a unit cost of £16,406 on the first phase.

  - As with phases 1 & 2 the cost includes the following:

- The provision of out-of-hours security (not previously provided – the contractor took the risk on previous schemes)

- The costs of managing the site (supervision) allows for more supervision than on competitively tendered schemes.  This would result in better quality of workmanship and customer care.

- Improved welfare facilities.

- A higher figure has been allowed for demolition work than was the case on previously tendered schemes of this nature, in order to address perceived health and safety risks.

  - Both the Council and its partner contractor are on a steep learning curve as far as the partnering process is concerned and it is hoped that improvements will be introduced over time, resulting in more efficient working, which will reduce the unit cost and / or represent better value.  In particular partnering will bring the following benefits:

- A long-term relationship between the council and the contractor working to deliver improvements over a five-year period.

- Improved local employment and training.

- Improved finishing times with less disruption to residents and fewer defects.

- Improved health and safety.

- Better quality of work.

- Enhanced customer satisfaction.

3.0	FINANCIAL IMPLICATIONS

3.1	As stated earlier, the contractor has proposed a target cost for the initial work of £740,527.  Based on this figure, expenditure would be phased as follows:

|  | 2004/05 | 2005/06 | 2006/07 | Total |
| --- | --- | --- | --- | --- |
| Target Cost for the Works |  | 740,527 |  | 740,527 |
| Design Service Fees | 26,863 | 50,000 | 894 | 77,757 |
| Total Target Cost | 26,863 | 790,527 | 894 | 818,284 |

  - Based on the target cost, the total guaranteed maximum price (for the works) will be £777,553.  If the actual cost exceeds the target cost the contractor and the council will share that additional cost up to the guaranteed maximum price.  The maximum cost that the council could have to fund would, therefore, be £759,040 (plus design fees).

4.0	CONCLUSION

4.1	Approval of the target cost and guaranteed maximum price for the third group of properties will enable the contractor to take steps to mobilise work on site as soon as possible and maximise expenditure in 2005/06.

  - This is one of the first partnered block improvement scheme undertaken within the city and lessons will be learned from it, together with the other projects in this year’s programme, which will lead to improvements and greater clarity of approach in subsequent schemes.

MALCOLM SYKES

Strategic Director of Housing and Planning

BOB OSBORNE

Head of Housing

___________________________________________________________________