| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- |

# REPORT OF

# THE HEAD OF HOUSING SERVICES

# TO HOUSING LEAD MEMBER on 12th JANUARY 2006

# TITLE: PRIVATE SECTOR CAPITAL PROGRAMME 2005/06

# RECOMMENDATIONS:

- That Lead Member notes the current position for 2005/06 and receives further monthly reports throughout the year.

# EXECUTIVE SUMMARY:

This report gives the details of the current position for the 2005/06 Private Sector Capital Programme.

# BACKGROUND DOCUMENTS:

(Available for public inspection)

Approved capital programme 2005/06

Regeneration Monitoring Data

Financial Information from SAP

# ASSESSMENT OF RISK:

Failure to monitor the programme could result in significant overspends or under utilisation of resources and failure to maximise external funding opportunities.

# THE SOURCE OF FUNDING IS:

Not applicable as the report is commenting on the financial position.

# LEGAL ADVICE OBTAINED:

Not required for this report.

# FINANCIAL ADVICE OBTAINED:

Report prepared by the out stationed Principal Group Accountant for Chief Executive’s.

# CONTACT OFFICER:

# Nigel Dickens 0161 793 2585

# WARD(S) TO WHICH REPORT RELATE(S):

# All

# KEY COUNCIL POLICIES:

# COUNCIL CAPITAL BUDGET 2005/06

# DETAILS (Continued Overleaf)

- Background Information

  - The Council has approved a Private Sector Capital Programme of £35m for 2005/06 as part of the Council’s Capital Programme for 2005/06. It is the responsibility of officers to manage and monitor this on behalf of the Council and report on any issues arising to Lead Member as appropriate.

  - This programme was as a result of officers from Housing, Seedley and Langworthy, New Deal for Communities, Development Services and Chief Executive’s working together to develop the programme for 2005/06. This was also to help formulate the discussions for next Housing Market Renewal Prospectus and Annual Investment Plan.

  - This is to ensure that the programme meets not only the requirements of Housing but also the different regeneration initiatives such as Housing Market Renewal (HMR), Single Regeneration Budget, New Deal for Communities and English Partnerships.

  - Following the 2004/05 out-turn and as subsequently agreed by the Joint Lead Members for Housing and Customer and Support Services there has been a carry forward of resources of £1.9m to support the 2005/06 programme.

  - It has previously been reported that an amount of £2.7m has been identified as slippage that can be offered to the ODPM as part of the Pathfinder’s required cut to HMRF. It should be noted that for the next Prospectus this has not been included in the assumptions as it is considered that there should be lobbying to have this re-instated in addition to the future allocations.

  - The ODPM has subsequently indicated that they expect the full amount of cuts requested which now equates to £4m for Salford. There has therefore been a need to identify further slippage of £1.3m on top of the £2.7m referred to above.

  - The above points mean that together with some adjustments for grants that the level of resources available to fund the 2005/06 programme is £33.7m.

- Details of Report

  - 2005/06 Programme

    - The current programme is £35.5m which means that there is an amount of over-programming of £1.8m.

    - It is not considered that this will cause a problem as this represents an over-programming level of 10% on expenditure still to be incurred, which at this point in the year is an acceptable amount and will be managed within the Council’s internal resources.

    - The table below shows how this over-programming fits with the different available resources:

| Funding Source | Programme £ m | Level of Resources | Amount of Over-Programming |
| --- | --- | --- | --- |
| Housing Market Renewal | 24.956 | 18.220 | 6.736 |
| City Council Resources | 5.730 | 10.622 | -4.892 |
| New Deal Grant | 1.550 | 1.550 | 0 |
| SRB 5 | 1.573 | 1.573 | 0 |
| Specified Capital Grant | 0.676 | 0.676 | 0 |
| ERDF | 0.579 | 0.579 | 0 |
| English Partnerships | 0.500 | 0.500 | 0 |
| Total | 35.564 | 33.720 | 1.844 |

    - What the above table demonstrates is that over-programming is within Housing Market Renewal to the extent of £6.7m and this will be funded through the use of Council resources.

    - As at the 30th November 2005 actual expenditure was £16.1m or 48% of the programme. Of this £11.9m was eligible for Housing Market Renewal.

    - With Housing Market Renewal being the main resource within the programme the table below shows this part of the programme by intervention area:

| Intervention Area | Programme £m | Level of Resources | Amount of Over-Programming | Actual Spend at 30/11/05 |
| --- | --- | --- | --- | --- |
| Strategic Site Assembly | 14.226 | 9.587 | 4.639 | 6.772 |
| Securing Development | 2.106 | 1.858 | 0.248 | 1.153 |
| Supporting Home Ownership | 1.110 | 0.550 | 0.560 | 0.444 |
| Home Improvements | 4.184 | 3.166 | 1.018 | 2.628 |
| Registered Social Landlords | 1.002 | 1.000 | 0.002 | 0.006 |
| Sustaining Neighbourhoods | 1.088 | 0.819 | 0.269 | 0.094 |
| Delivery | 1.240 | 1.240 | 0 | 0.826 |
| Total | 24.956 | 18.220 | 6.736 | 11.923 |

    - The above table now reflects the revised HMRF programme that has been submitted to the Board following the changes brought about through the £4m slippage requested by the ODPM. It can be seen from the table that there is a healthy amount of over-programming in most areas.

    - It should be noted that due to the nature of the expenditure within Delivery there is not any need to have over-programming as the target will be achieved. Therefore the only area of note in relation to over-programming is Registered Social Landlords where the amount is minimal as is actual expenditure incurred. However there are only five projects within this intervention and these will be delivered through the use of a Section 22 agreement and as such the risk of these not being delivered at present is low.

    - The table also shows that in most interventions actual expenditure already incurred is a major amount of the available resources through HMRF. The two areas where expenditure is low are Registered Social Landlords (covered in the above paragraph) and Sustaining Neighbourhoods.

    - Whilst there seven projects within the Sustaining Neighbourhoods intervention the one of note is the Streetscape project which has a HMRF approval of £0.63m. This project is itself made up of a number of individual schemes most of which are scheduled to commence in the New Year. Providing this occurs then there will be no problems in regard to achieving the use of resources in this intervention.

- Conclusions

  - The further cuts requested by the ODPM for HMRF have been managed through the amount of over-programming. The slippage of £4m now requires considering in relation to the programme submitted through scheme update for 2006/07.

  - For HMRF there is a good level of over-programming across most of the programme thereby giving the confidence that it will be delivered.

- Recommendations

  - That Lead Member notes the current position for 2005/06 and receives further monthly reports throughout the year.