| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- |

REPORT OF

THE HEAD OF HOUSING SERVICES

TO HOUSING LEAD MEMBER on 13th JANUARY 2005

TITLE: PRIVATE SECTOR CAPITAL PROGRAMME 2004/05

RECOMMENDATIONS:

- That Lead Member notes the position of the programme as at the 30th November 2004 and receives further reports for the remainder of the year.

EXECUTIVE SUMMARY:

This report details the current position for the 2004/05 Private Sector Capital Programme.

BACKGROUND DOCUMENTS:

(Available for public inspection)

Approved capital programme 2004/05

Regeneration Monitoring Data

Financial Information from SAP

ASSESSMENT OF RISK:

Failure to monitor the programme could result in significant overspends or under utilisation of resources and failure to maximise external funding opportunities.

THE SOURCE OF FUNDING IS:

Not applicable as the report is commenting on the financial position.

LEGAL ADVICE OBTAINED:

Not required for this report.

FINANCIAL ADVICE OBTAINED:

Report prepared by the out stationed Principal Group Accountant for Chief Executive’s.

CONTACT OFFICER:

Nigel Dickens 0161 793 2585

WARD(S) TO WHICH REPORT RELATE(S):

All

KEY COUNCIL POLICIES:

COUNCIL CAPITAL BUDGET 2004/05

DETAILS (Continued Overleaf)

- Background Information

  - The Council has approved a Private Sector Capital Programme of £34.6m for 2004/05 and it is the responsibility of officers to manage and monitor this on behalf of the Council.

  - During the last few months’ officers from Housing, Seedley and Langworthy, New Deal for Communities, Development Services and Chief Executive’s have been working together to develop the programme for 2004/05 and the commitments arising from this into 2005/06 and future years. This is to help formulate the discussions for next year’s programme and the next Housing Market Renewal prospectus

  - This is to ensure that the programme meets not only the requirements of Housing but also the different regeneration initiatives such as Housing Market Renewal (HMR), Single Regeneration Budget, New Deal for Communities and English Partnerships.

- Details of Report

  - 2003/04 Final Position and Developments in 2004/05

    - It will be recalled from previous meetings that the 2003/04 private sector capital programme overspent the available resources by £2.2m for reasons previously reported.

    - The Council has now assumed that there will be no clawback in 2004/05 and this has been built into the projections for the 2005/06 programme.

    - Therefore the current approved resources for the programme are £29m; the reason for the difference from the original £34.6m is that this included the Approved Development Programme, which has been excluded for monitoring purposes.

    - Although no payback is required in 2004/05 through ongoing monitoring it may transpire that a proportion of it may become achievable by moving resources around, this would lessen the impact on next year’s programme.

    - Additionally following numerous meetings with English Partnerships the amount of funding for the programme has reduced significantly to £0.32m, thereby reducing the resources for the full programme to £24.7m.

  - Actual Position as at 30th November 2004

    - As at the 30th November 2004 actual expenditure incurred was £9.1m or 37% of the programme. An exercise has also been undertaken to review the level of commitments and this is currently at £17.9m or 72% of resources. The table below shows the commitments against the funding sources:

|  | Committed | Funding Source | % Committed |
| --- | --- | --- | --- |
| English Partnership | 0.165 | 0.320 | 52% |
| City Council | 4.711 | 5.317 | 89% |
| HMRF | 9.475 | 13.008 | 73% |
| New Deal | 0.646 | 1.450 | 45% |
| SRB 5 | 1.532 | 1.602 | 96% |
| Other Grant | 1.330 | 1.330 | 100% |
| Total | 17.859 | 23.027 | 78% |
| Council not Allocated | - | 1.657 | - |
| Total Resources | 17.859 | 24.684 | 72% |

    - In order for the current position to be clearly understood the above table is recast below by intervention area and area of expenditure.

|  | Committed | Budgeted Spend | % Committed |
| --- | --- | --- | --- |
| Strategic Site Assembly | 4.942 | 7.209 | 69% |
| Securing Development | 1.432 | 2.336 | 61% |
| Supporting Home Ownership | 1.981 | 1.981 | 100% |
| Home Improvements | 4.675 | 5.363 | 87% |
| Registered Social Landlords | 0 | 0.120 | 0% |
| Sustaining Neighbourhoods | 0.403 | 1.273 | 32% |
| Outer City | 4.426 | 4.745 | 93% |
| Total | 17.859 | 23.027 | 78% |
| Resources not Allocated | - | 1.657 | - |
| Total | 17.859 | 24.684 | 72% |

    - What the tables demonstrate is that good progress is being made towards achieving an element of the required clawback in the current year. Consequently if the £1.657m is viewed as the clawback and therefore not allocated then in effect 78% of the available resources have already been committed. This also alters the actual expenditure percentage from 37% of paragraph 2.2.1 to 40%.

    - From the tables above it can be seen that the Strategic Site Assembly programme is now well committed through the removing of the English partnerships funding and there are no concerns that this will be fully achieved. It should be noted that the definition of committed is for those schemes that are actually with Legal Services for completion.

    - There is a potential problem with a scheme for Securing Development on the gap funding in Broughton due to concerns from the Environment Agency. This scheme has been put on hold following the recent developments and consideration is being given by the various parties as to how this will progress. As such there is a potential £500k that might not be spent and approval might have to be sought to move this into site assembly.

    - The Sustaining Neighbourhoods line comprises a few projects the main one being Streetscapes for which most of the schemes within this are now commencing and should achieve spend by the end of the year.

    - Whilst the above only concentrates on the position to the end of November it was reported that at the monitoring meeting in December that there was good progress for both expenditure and commitments during this month, therefore again indicating that the programme is going to be delivered.

- Conclusions

  - The programme is currently forecast to underspend by £1.6m and this will contribute towards the required clawback form 2003/04 and therefore should not be allocated to further schemes.

3.2 	Generally the programme is on target to be delivered after allowing for the clawback.

- Recommendations

  - That Lead Member notes the position of the programme as at the 30th November 2004 and receives further reports for the remainder of the year.