ACHIEVING A FIT FOR PURPOSE

HOUSING STRATEGY

FOR SALFORD

ACTION  PLAN

REVISION 2 8th AUGUST 2003

### CONTENTS

- Housing Strategy Statement 2004/2007 - Framework and Content

- Housing Strategy Delivery Plan Template 2004/2007

- HRA Business Plan - Framework and Content

- Work plan

5.	Timeline

(1) HOUSING STRATEGY STATEMENT 2004-2007

Below sets out the intended structure of the Housing Strategy Statement.

FOREWARD

CHALLENGES AND PRIORITIES (executive summary)

#### CHAPTER 1 - A STRATEGY FOR HOUSING IN SALFORD – 3 year

- Salford’s Vision and the corporate context;

  - Salford’s neighbourhood renewal strategy/neighbourhood planning, delivery and management;

  - Corporate business planning and the links to the Councils Capital Investment Strategy;

  - Political and strategic partnership arrangements/partnerships generally including the Local Strategic Partnership

  - The Salford Housing Partnership and the role of Housing Services (Including structure)

  - Customer/stakeholder involvement in shaping the strategy;

- Salford’s Housing Market;

  - National/regional/local strategy integration

  - Housing Market Renewal

  - Resources

- Bringing it all together – Salford’s Housing Strategy

  - Structure of document

CHAPTER LEAD: KEVIN SCARLETT

STRATEGY SPLIT IN TWO PARTS: CENTRAL AND WEST

THE FOLLOWING WILL FORM SECTIONS WITHIN EACH.

A) UNDERSTANDING OUR HOUSING MARKET AND NEEDS

- Profile of the housing market: -

  - Population etc.

  - Market at City and neighbourhood level

    - at risk, vulnerable, secure

    - current drivers	university, economic, educational, community safety

  - Health and social care needs - Supporting People

    - Homelessness

    - Older People

    - Asylum/refugees

    - B&ME needs

    - Children and young people.

  - Key drivers for the future housing market:

PRIORTIES FOR ACTION

What we need to do to improve our knowledge and understanding of our housing markets and housing needs.

#### CHAPTER LEAD: PAUL LONGSHAW

##### B) MANAGING THE HOUSING MARKET AND WIDENING CHOICE

- Partnerships

  - Regional

  - Corporate

  - Regeneration

  - Planning

  - Developers

  - RSLs	Joint commissioning etc.

- Mechanisms to meet need/demand issues

  - Planning

    - Sustainability – tenure mix, infrastructure development

    - Affordable homes

    - Encourage good design

    - Regional impacts/RPG and adjacency

  - Private Sector -

    - Tackle low demand – empty homes in all sectors

    - interventions/enforcement/accreditation

  - Public sector

    - Choice based lettings

    - Rationalisation

    - Involvement in strategy development

PRIORTIES FOR ACTION - What we need to do to manage the market and improve choices more effectively

CHAPTER LEAD: KEVIN SCARLETT

C) MEETING VULNERABLE PEOPLES HOUSING NEEDS AND THE NEEDS OF OTHER GROUPS

- Tackling homelessness – the Homelessness Strategy and Action Plan;

- Supporting People Strategy;

- Meeting needs of people with other special needs:

  - Older people

  - Delayed discharges

  - Adaptations/disability

  - Young people/children

  - Teenage parents

  - Asylum Seekers/Refugees

  - B&ME housing needs and community cohesion

- Gaps in provision

PRIORTIES FOR ACTION - What we need to do to meet the needs of vulnerable people and groups.

CHAPTER LEAD: PAUL LONGSHAW

D) INVESTING IN SALFORDS HOUSING STOCK

Context

- Public and Private Sector stock condition

- HMR (Central)

- Locality issues/sustainability

- Energy efficiency

- Disability

Private Sector

- Market restructuring

- Private rented sector

- Supporting owner occupation

- Housing renewal policy/HMR toolkit (Central)

- Option appraisal/risk analysis

PRIORITIES FOR ACTION - To include housing renewal strategy and policy, HMRF, enforcement, new tools etc

#### Public Sector

#### Asset appraisal/HMR impact (central)

- Estate/Neighbourhood Ranking Matrix

- New investment needs/decent homes

- TMO’s/elderly/high rise/blocks/general

- Revised option approvals

- Asset appraisal of RSL’s stock

- Energy Efficiency

PRIORITIES FOR ACTION –asset appraisal, improving performance, decent homes driver, what is it we need to do to meet the investment needs of our stock.

Procurement

- Partnering in public/private sectors

- Developers/contractors forum

- Bovis/Countryside/Urban Splash etc.

CHAPTER LEAD:  GILL LENG

E) SUSTAINING NEIGHBOURHOODS AND COMMUNITIES

- Advent of neighbourhood/market renewal planning process;

- Neighbourhood management;

- Seedly and Langworthy/NDC/Broughton/Chapel Street/Central Salford [in appropriate section];

- Community safety/ASB

- Street scene and the environment;

- Community cohesion;

- Training and employment;

- Community finance;

- Community development and capacity building;

- Arts in regeneration.

- Early warning system

PRIORTIES FOR ACTION - What is it we have to do to achieve sustainable communities

CHAPTER LEAD: PAUL LONGSHAW

F) RESOURCES

- Summary of recent performance/achievement/levels of investment

- Capital resources available to the Council

- Meeting decent homes target/HRA business plan

- Investment in the private sector/home ownership

- Investment in regeneration

- HMRF

- Investment to meet affordable homes

PRIORTIES FOR ACTION - What we are assuming/how we are planning to resource our priorities and any additional assistance we will need

CHAPTER LEAD: KEVIN SCARLETT

CHAPTER 2 - DELIVERING OUR STRATEGY – ACTION PLAN

- Delivery plan 2004 – 2007

- BVPI/PSA targets etc.

- Monitoring and review mechanisms

- Continuous improvement / processes

- Ownership of the Strategy

CHAPTER LEAD: PAUL LONGSHAW

(2) HOUSING STRATEGY DELIVERY PLAN TEMPLATE 2004/2007

| Salford’s Corporate Strategic Objective |  |
| --- | --- |
| Housing Strategic Objective | - To be developed |
| Service Priority |  |

| Action | Lead/Partners | Outcome | Milestones - Time | Resources |
| --- | --- | --- | --- | --- |

(3) HRA BUSINESS PLAN

#### Below sets out the intended structure of the HRA Business Plan – 30 yr:

CHAPTER 1	- STRATEGIC CONTEXT

- Communities Plan and Salford’s Vision;

- Decent homes;

- PSA plus review/investment options;

- HMRF/regeneration;

- Step change.

CHAPTER 2	- THE HOUSING STOCK

- Nature, number etc.

- Stock condition;

- Decent homes;

- Energy Efficiency;

- Resources needed/financial profiles;

- Additional funding identified (ALMO);

- Asset appraisal and drivers/approach taken;

- Capital programme performance.

CHAPTER 3	- WHAT CUSTOMERS WANT?

- Salford Standard

- HMR/low demand/regeneration;

- Stock option appraisal;

- Consultation/ customer involvement;

- Approach TMO’s/HRB’s/ALMO/SHELTERED;

- Ranking the stock/we cant do everything at once;

- Supported housing needs;

- Choice based lettings;

- Process for continuous engagement.

CHAPTER 4	- PERFORMANCE

- BV reviews/BV & LPI’s;

- ALMO performance

- CPA/PSA etc.

CHAPTER 5 	- RESOURCES

- Service and investment planning – corporate context;

- Additional HRA resources required;

- Rent convergence

- Partnering – managing the investment.

CHAPTER 6	- STRATEGY FOR THE NEXT 6 /30 YEARS

- Financial profiles/stock condition surveys;

- Neighbourhood/estate ranking matrix

- Investment plan/asset management plan - Partnering Action Plan

(4) WORK PLAN

OBJECTIVE ONE; TO UNDERSTAND OUR HOUSING MARKETS AND NEEDS

OVERALL LEAD: PAUL LONGSHAW

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Develop detailed market review information including: | MHe/CM | Mid-September SHMT 22/9, LMB 2/10, Cab Brief 14/10, Cab 22/10 |  |
| Housing Demand Study | Mhe/PL | End August Dataset check | Depending on dataset |
| Housing Moves Survey | Mhe |  |  |
| Quality of Life study | Cexecs |  |  |
| CURS/sub-regional intelligence and analysis | Mhe |  |  |
| Links to other demographic, economic and other intelligence. | Mhe |  |  |
| 2001 census information | Mhe/MH/JR |  |  |
| Commission Market Review document | PL |  | £9,000 |
| GIS Licences and training | GL/JW/Planning |  | £10,000 (poss. impact on IT systems) |
| Investigate Consumer Information system (Mosaic etc) | Mhe/GL |  | Cost implications |
| Investigate sustainability model HCH | PL |  | Cost implications |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Commission detailed needs analysis including: - | PL |  |  |
| Agree approach to BME Housing Needs | MB/SP | Discussion with GONW September | Possibly Survey/research £ |
| Supporting People needs mapping | SP/Mhe |  | SP |
| Homelessness research. | Janice | Homelessness Action Plan |  |
| Older people/elderly village study | Jean |  |  |
| Complete analysis of demand for sheltered accommodation | Jean/PL/LS | November |  |
| Complete Housing Strategy Consultation and Involvement Plan: - | MH/CM | August |  |
| Event in October City wide consultation – corporate consultation mechanism | MH | October | Cost of event organisation/facilitation |
| Identify priorities for Action & Consultation workshops | MH/CM | September – after Market review |  |

OBJECTIVE TWO: 	MANAGING THE HOUSING MARKET AND WIDENING CHOICE

OVERALL LEAD: KEVIN SCARLETT

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Develop and formalise linkages with the planning function to include: - |  |  |  |
| UDP & Area Plans | DV/PL |  |  |
| Affordable homes policy | DV |  |  |
| Design and lifetime homes; | RSL/KS & DEvans/BWhitmarsh |  |  |
| CABE involvement; | Ro |  |  |
| Additional homes and sustainability/land use and availability; | JR & Mhe |  |  |
| Confirm role in Neighbourhood Planning/Delivery - | KS |  |  |
| Establish, formalise and launch the Salford Housing Partnership | AH | August meeting Launch at Strategy event in October | RSL resource |
| Evaluate joint commissioning/partnership arrangements with RSL’s Central West | AH | August/Sept | RSL resource |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| HMR prospectus approval/delivery team in place | KS | September | HMRF |
| Commence review of housing renewal strategy and policy | EJW/JC ? | September ? |  |
| Establish strategy structure (development, delivery and monitoring mechanisms) | KS/GL | Structure proposed July First meetings August | ? |
| Complete choice based lettings proposal | TBI | Principle to October Conclusion by 04 | Cost implications of choice based lettings to be evaluated as part of exercise |
| Identify Priorities for Action/Consultation | KS | September |  |

OBJECTIVE 3: MEETING VULNERABLE PEOPLE’S HOUSING NEEDS /OTHER GROUPS

WITH SPECIFIC NEEDS

OVERALL LEAD; PAUL LONGSHAW

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Links to Homelessness Strategy and Action Plan | Janice | July completion Attendance at Homelessness Forum |  |
| Links to Supporting People Strategy and review/mapping/priorities Consultation & needs analysis | PL/SP | August – initial discussion |  |
| Links to health and care plans and priorities including: / support Children and Young People Strategy; Community Care Plan; Older People Strategy; Health and well being etc LIFT/SHIFT; Domestic Violence; Learning disability. Sure Start /Connexions | Jean & SP & SS | August |  |
| Links to Asylum Seeker action and priorities/NASS | Janice | July |  |
| Address BME Housing Needs as identified | MB/SP | October/December |  |

OBJECTIVE 4: INVESTING IN SALFORD’S HOUSING STOCK

OVERALL LEAD:  GILL LENG

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Complete HRA Business Plan: | Graham Moody |  | Issues – lack of anyone in strategy team to do asset related work and constraints of NPHL being able to do work |
| Context; |  |  |  |
| Asset Appraisal and Management Plan; |  |  |  |
| Housing stock condition; |  |  |  |
| Non decency; |  |  |  |
| Resources needed; Energy efficiency; |  |  |  |
| Capital programme performance; |  |  |  |
| Financial Profiles etc; |  |  |  |
| Complete Financial Models | Graham Moody | September |  |
| Option Appraisal process and/update/options analysed and decisions taken |
| Bidding/expressions of interest | DV/CMe/MH/MD | September? |  |
| Partnering arrangements and finalisation – complete Partnering Plan | KS | September |  |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Identify investment needs in the private sector: - | EJW | September | ? £ ? |
| Context; |  |  |  |
| Housing Renewal Strategy |  |  |  |
| Stock condition |  |  |  |
| Non decency/unfitness |  |  |  |
| Anticipating HHSR |  |  |  |
| Energy Efficiency |  |  |  |
| Disability |  |  |  |
| Identify investment needs in the RSL sector: - | AH/GL | September | RSL/SCC |
| Business Plans |  |  |  |
| HMRF Impact |  |  |  |
| Asset Appraisal |  |  |  |
| Promotion of Egan principles/partnering across all sectors/establish Developers Forum | GL to lead with support from KS/TBI RSL/Planning-DC/NRHL | October/November |  |

OBJECTIVE 5: SUSTAINING NEIGHBOURHOODS AND COMMUNITIES

CHAPTER LEAD; PAUL LONGSHAW

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Established and secure corporate agreement to Neighbourhood Planning and Regeneration Delivery process | KS | September ? |  |
| Develop Neighbourhood Management model - delivery Salford First? | KS | October |  |
| Links to community safety/ASB/cross tenure ASB Initiative | MHe/CM |  |  |
| Develop arts in regeneration initiative | KS/CM | March 2004 |  |
| Construction training/employment academy | KS/CM | May 2004 |  |
| Community finance development and linkages | MHe/CM | March 2004 |  |
| Continue to deliver & maintain Early Warning System | PH/MHe/CM/ |  |  |
| Environment |  |  |  |
| Community Cohesion | MB |  |  |

OBJECTIVE 6: RESOURCES

OVERALL LEAD: KEVIN SCARLETT

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Links to corporate Capital Strategy/Asset Strategy | KS | September |  |
| Identify resource opportunities within all regeneration funding in City | GL/CM/KS | September |  |
| Housing Capital Programme (public/private) | GL/JW | September |  |
| ADP | AH/GL | September |  |
| Other resources e.g. Planning | GL | September |  |

5) Timetable

| 21/7 | 28/7 | 4/8 | 11/8 | 18/8 | 25/8 | 1/9 | 8/9 | 15/9 | 22/9 | 29/9 | 6/10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| LM Briefing 24/7 |  |  |  |  |  |  |  |  |  |  |
|  | LM Briefing 31/7 |  |  |  |  |  |  |  |  |  |
|  |  | Labour Group 4/8 |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | SHMT 22/9 Housing Market Review |
|  |  |  |  |  |  |  |  |  |  | LMB 2/10 Housing Market Review |
|  |  |  |  |  |  |  |  |  | ALMO Expressions of interest 26/9/03 |
|  |  |  |  |  |  | Transfer Bid information expected September/October |

| 13/10 | 20/10 | 27/10 | 3/11 | 10/11 | 17/11 | 24/11 | 1/12 | 8/12 | 15/12 | 22/12 | 29/12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Strategy Consultation Events |  |  |  |  |  |  |  |  |  |  |
|  | SHMT 20/10 Housing Strategy |  |  |  |  |  |  |  |  |  |
|  |  | Directors CG 27/10 Housing Strategy |  |  |  |  |  |  |  |  |
|  |  |  | LMB 6/11 Housing Strategy |  |  |  |  |  |  |  |
|  |  |  |  |  | Scrutiny 17/11 Housing Strategy |  | Cabinet briefing 9/12 Housing Strategy |  |  |
|  |  |  |  |  |  |  |  |  | Cabinet 17/12 Housing Strategy |  |
|  |  |  | PFI Expressions of interest information |  |  |  |  |  |