Part 1 (OPEN TO THE PUBLIC)

REPORT OF THE CHIEF EXECUTIVE OF NEW DEAL FOR COMMUINITIES

LEAD MEMBER FOR HOUSING

FOR INFORMAL ON 3RD FEBRUARY 2009)

FOR FORMAL ON 17TH FEBRUARY 2009

THE LEADER OF THE COUNCIL (BRIEFING ON THE 9th FEBRUARY 2009)

TITLE: LOWER KERSAL ESTATE PHASE 3B ENVIRONMENTAL

IMPROVEMENTS, LOWER KERSAL.

RECOMMENDATIONS:

That the Lead Member for Housing gives authority for P. J. Casey (Land Reclamation) Ltd. to continue the Phase 3B Lower Kersal Environmental Improvements at numbers 8 to 40 Cheadle Ave, 9 to 31 & 18 to 40 Bradley Ave, 9 to 45 and 14 & 16 Kingsley Ave

That the Leader of the Council approves the funding to the sum of £362,880.00 in order to facilitate the completion of Phase 3B of the Lower Kersal Environmental improvements.

EXECUTIVE SUMMARY:

This scheme follows on from the success of the phases 1,2 and 3A as part of a rolling programme of environmental works across the Lower Kersal Estate.

The Leader of the Council and Lead Member for Housing will recall on 18th August 2008, and 2nd September respectively, approving Phase 3 of the Lower Kersal Environmental Improvements (for the sum of £495,019.04). These works covered the following properties: 9 to 45 Kingsley Avenue, 14 and 16 Kingsley Avenue, 2 to 40 Cheadle Avenue, 1 to 41 Cheadle Avenue, 2 to 40 Bradley Avenue, 1 to 31 Bradley Avenue. Since then works have continued apace, completing the sub phase known as Phase  3A in December 2008. Work is now underway with Phase 3B (the remaining sub phase), but extra funding is now required to complete these works.

This funding is necessary for the following reasons:

- The need to keep the contractor on site in order to avoid the cost of him demobilising;

- The inclusion of an extra 20 properties, along with other additional  works within the Phase 2 improvements (thus necessitating the virement of £249,590.29 from Phase 3); and

- The fact that the approved figure for the Phase 3 works (£495,019.04) was based on an estimate which has, subsequently, proved to be an underestimate.

BACKGROUND DOCUMENTS:

NDC Development Framework Document

NDC Project Appraisal Form – Lower Kersal Estate Environmental Improvements 2008/09

ASSESSMENT OF RISK: Small to Medium – within this phase of works (phase 3) the work to be undertaken does not include any road widening or engineering works and also there are no legal agreements to be made with owner occupiers or private landlords.

Where work to private properties is required, only a license to work on the property is needed. If this is not forthcoming the contractors can move to the next eligible property without detriment to the schedule.

There is a risk, however, that subject to further consultation, further funding may be required to complete work on properties within the remaining part of Phase 3. However, this is deemed to be a small risk.

SOURCE OF FUNDING: Phase 3 – Charlestown and Lower Kersal New Deal for Communities Housing and Physical Environment Budget Lower Kersal Environmental Improvements).

LEGAL IMPLICATIONS:

Contact Officer and Extension No: Norman Perry Land & Property Team 793 2325

Date Consulted: 26th January 2009

Comments:

Given that authority for extra expenditure was given previously in order to keep the contractor on site thus avoiding demobilising and remobilising costs I see no reason why the same reasoning cannot be used for the authorisation of further expenditure in the current circumstances. I cannot comment upon financial issues, but if the budget is available as mentioned above, then there seem to be no obvious legal reasons why this exercise cannot be repeated in an attempt to save costs in the long run.

However, given that there is a risk that further funding will be necessary to complete Phase 3 in addition to the amount currently being requested, there is a possibility of exceeding the amount budgeted for this scheme and there may be repercussions in the future. That however is something that is more properly dealt with under the heading of “Financial Implications”

FINANCIAL IMPLICATIONS: An allocation of £362,880.00 has been budgeted for this scheme.

Based on this budget figure, the expenditure for the project (including Urban Vision’s fees) will be as follows:

Budget allocation

| Breakdown | A Residual Funding from Previous Lead Member Approval of £495,019.04 | B Additional Funding Required 2008/09 | C Additional Funding Required 2009/10 | D Total Additional Funding Required | E Estimated Total Phase 3 costs (A + D) |
| --- | --- | --- | --- | --- | --- |
| Contract | £215,977.30 | £89,285.00 | £234,715.00 | £324,000.00 | £539,977.30 |
| Fees | £29,451.45 | £10,715.00 | £28,165.00 | £38,880.00 | £68,331.45 |
| Total Cost | £245,428.75* | £100,000 | £262,880 | £362,880.00 | £608,308.75 |

* represents the residual funding left for phase 3 once £249,590.29 was vired to Phase 2 improvements.

Contact Officer and Extension No: Nigel Dickens - 2585

Date Consulted: 26th January 2009

Comments: Above table amended to make explicit the overall cost of Phase 3

## COMMUNICATION IMPLICATIONS: The NDC will work with Salix Homes the City Council, Urban Vision and the Contractors, to ensure communications and publicity is prepared according to guidelines and that when the project is complete an evaluation report and satisfaction survey are completed.

VALUE FOR MONEY IMPLICATIONS: This scheme offers value for money as it builds on the success of the previous 2 phases, in respect that it is a partnership between the city council, NDC and the contractor. Urban Vision will project manage the scheme as this allows learning and best practice from previous schemes to be incorporated into future phases. This scheme is part of a continuous rolling programme of works across the estate and will ensure cost savings with materials and site plant and machinery. That is, the scheme offers continuity of work because the contractor can remain on site and there does not have to be a break in work between works currently being undertaken and the ultimate completion of Phase 3.  The anticipated unit cost of the proposed works is approximately £6000.

Negotiations with Urban Vision have ensured that a competitive fee structure has been formally agreed due to the programme of work over the next two financial years, this gives certainty over costs and fees for the overall project not only in terms of Urban Vision, but also the contractor partner.

This programme of works does not clash with any current or proposed plans for decent homes work on this estate. Salix Homes and their contractors (H T Forrest) are now completing the current phase of internal works on part of Winster Avenue, This would have been the last phase of decent homes works. However, in light of the recent decision to retain the homes, which were previously estimated for demolition, Decent Homes works to this new phase have commenced January 2009 and will be completed in April 2009.

CLIENT IMPLICATIONS: This latest scheme represents value for money for the New Deal Partnership. The scheme will also improve Council housing stock.

PROPERTY: It is proposed to include both Council owned and privately owned properties in the environmental improvements.

The proposed improvements will be maintained by Salix Homes and Council tenants where Council property is improved (this may have additional maintenance/revenue implications for Salix Homes)..

HUMAN RESOURCES: No additional staff are needed to deliver this scheme as it will be delivered by Salix Homes and Urban Vision staff.

CONTACT OFFICER:

NDC Lead Principal Officer (for client): Brian Enright 0161 607 8548

Urban Vision Project Manager: Cathy Mitchell 0161 779 6047

WARD(S) TO WHICH REPORT RELATE(S): Kersal

KEY COUNCIL POLICIES:

Salford Community Plan: The project will contribute towards the theme of “A city that’s good to live in”.

Salford City Council Pledges: This project complies with pledges 1, 2, 5 and 7.

Salix Homes Business Plan “Improving Neighbourhoods, making them better” and “Improving homes, making them Decent”

| 1.0 | Background |
| --- | --- |
| 1.1 | Phases 1 and 2 of the project were completed at the end of June 2008. This was followed by Phase 3A in October 2008. Phase 3B is now on site, and by mid February, it is anticipated that 26 of the 80 properties will be completed. However, due to a combination of 20 further properties being identified for improvements adjacent to Phase 2 (namely Nrs 2, 4, 6, 11, 12, 13, 15, 19, 21, 30, 32, 34, 38 & 44 Shirley Ave, Nrs 2, 4, 13, 28, & 30 Monsall Ave and Nr 132 South Radford St), and extra costs resulting from additional work consisting of additional gates, pedestrian path construction, fencing replacement and associated highways works in and around a number of the houses originally identified, it was necessary to vire £249,590.29 (inclusive of Professional Fees) from the £495,019.04 funding allocation for Phase 3. Not only did this funding improve local homes in need of improvement, it also ensured that the contractor (P Casey Land Reclamation Ltd) stayed on site, offering savings of approximately £10,000.00 in terms of him not having to demobilise operatives and the site compound, only to mobilise again for Phase 3 improvements. Similarly, in attempting to keep the contractor on site for start of Phase 3, and to maximise NDC spend prior to the end of the financial year 2008/09, an estimate was provided by Urban Vision, which was based on a survey that did not include all properties in the proposed Phase 3 improvements. Unfortunately, this estimate was not supplemented by a forecast of the likely cost of improving properties not included in the survey. The net result of the need to complete extra properties and extra work on Phase 2, along with the underestimate of the cost of completing Phase 3, is that it is now necessary to seek approval for further funding to complete the whole of Phase 3. This funding amounts to £362,880.00. It should be noted that further work has now been commissioned in order to determine the likely cost of completing Phase 4 and 5 and 6 of the estate wide improvements. Once this survey work is completed, a more accurate picture of the impact of these extra costs on these Phases (the latter phase being an additional phase resulting from the decision not to demolish 66 properties formally earmarked for demolition) will be known. The results of this and the effect on budgets, will be relayed to the Leader of the Council at a subsequent briefing. The properties that will be improved should this funding be approved are numbers 8 to 40 Cheadle Ave, 9 to 31 & 18 to 40 Bradley Ave, 9 to 45 and 14 & 16 Kingsley Ave - 59 properties in total. |
| 1.2 | The unit cost unit for the proposed improvements (including fees) is approximately £6,000.00. It is considered that this still represents value for money for this type of scheme. It should be noted, however, that the figure of £362,880.00 is itself an estimate based on information extracted from the phase 3A works. Urban Vision have allowed, however, (within this sum), for all remaining 59 Phase 3 properties, currently identified, to have the standard driveway, gates and drop kerb improvements. It is likely, therefore, that £362,880.00 will be sufficient to complete Phase 3. |
| 1.3 | In terms of the availability of NDC funding, the Charlestown and Lower Kersal Physical Environment Task Group supported the Phase 3 improvements at its meeting on 16th April 2008. Following this, the NDC Appraisal Panel approved the details of the scheme on 22nd May 2008. More latterly, the NDC Strategic Working Group approved the bringing forward of £100,000 of funding from the 2009/10 Delivery programme to cover the additional cost of works carried out by the end of this financial year. |
| 2.0 | ### Details |
| 2.1 | It is proposed that Phase 3B will continue the successful earlier phases 1, 2 and 3A. Work will include the construction of in-curtilage hard standings and lockable metal vehicle gates where possible. Where site and pedestrian safety issues are a concern, appropriate fencing will be provided; this is usually at junctions within the estate. Dropped kerbs will be constructed for existing and proposed hard standings. |
| 2.2 | Funding for this scheme will be as follows: - New Deal for Communities - £362,880.00 (Lower Kersal Environmental Improvements 2008/09 and 2009/10) |
| 2.3 | Previously, the standard sketch scheme consultation has been undertaken with all directorates of the City Council and external public agencies who may be affected. An updated plan (indicating Phase 2, Phase 3A and Phase 3B), is however, attached to this report |
| 2.4 | Also previously, the proposals have been viewed by the appropriate Planning Officer (within the Housing & Planning Department) and they have confirmed that planning permission will not be required. |
| 2.5 | P. Casey (Land Reclamation) Ltd, one of the Council’s partner contractors for landscape works will undertake these additional works given that they are the contractor currently on site. |
| 2.6 | This is a scheme to be implemented on a partnership basis (Urban Vision, Contractor, Salix Homes and Client – New Deal). In particular partnering will continue to bring the following benefits: - A long term relationship between the council and the contractor to deliver improvements over 4 year period. - Improved health & safety procedures - Genuine local employment & training - Continuous improvement & quality of work - Enhanced customer satisfaction with Customer Liaision Officers from Salix Homes. - Meeting equality and diversity requirements |
| 3.0 | Conclusion |
| 3.1 | It is important that the current momentum in the improvements on the Lower Kersal estate is maintained. Due to a combination of an additional 20 houses adjacent to the Phase 2 of the scheme being added, together with additional work being carried out on other properties on Phase 2, as well as what proved to be an underestimate being used for the whole of Phase 3, further funding is now being sought for the remaining part of Phase 3 B. Should this funding be granted, it will enable the contractor to stay on site and thereby save on demobilisation costs. |
| 3.2 | Approval is, therefore, sought from the Leader of the Council and the Lead Member for Housing to complete Phase 3B of the Lower Kersal Environmental Improvements . |

Tim Field – New Deal for Communities, Chief Executive