| Part 1 (OPEN TO PUBLIC) | ITEM NO. |
| --- | --- |

REPORT OF STRATEGIC DIRECTOR FOR SUSTAINABLE REGENERATION

THE LEADER OF THE COUNCIL BRIEFING ON 26 OCTOBER 2009

TO THE LEAD MEMBER FOR HOUSING ON 17 NOVEMBER 2009

TITLE: LOWER KERSAL ESTATE PHASE 5a ENVIRONMENTAL IMPROVEMENTS, LOWER KERSAL

RECOMMENDATIONS:

That the Lead Member for Housing gives authority for P. J. Casey (Land Reclamation) Ltd. to carry out the Phase 5a Lower Kersal Environmental Improvements at:  Kingsley Avenue; Stanton Avenue; Alsop Avenue; Winster Avenue; Beeston Avenue; Northallerton Rd (not all properties to be included)

That the Leader of the Council approves funding up to the sum of £575,144.00 for these Phase 5a works, conditional upon further approval being sought should the final Target Cost exceed this amount.

EXECUTIVE SUMMARY:

This scheme follows on from the success of the phases 1, 2, 3A, 3B (i) and 3B (ii) and the recent commencement of Phase 4, these being parts of a rolling programme (of 6 phases) of environmental works across the Lower Kersal Estate.

Phase 5a (please refer to Annexe 1) will seek to improve properties on the following streets: part of Kingsley Avenue; Stanton Avenue; Alsop Avenue; Winster Avenue; Beeston Avenue; part of  Northallerton Rd . Subject to Lead Members’ approval, these works are due to commence in January 2010. Work will be carried out on both Council stock and privately owned dwellings.

It is intended that a further Phase, 5b, will incorporate treatments to the cul–de-sacs of   Hassop and Hurdlow Avenues, and will be the subject of a further Lead Member report for approvals in the near future

BACKGROUND DOCUMENTS:

(Available for public inspection)

NDC Development Framework Document

NDC Project Appraisal Form – Lower Kersal Estate Environmental Improvements 2009-2011

KEY DECISION:	YES – posted on Forward Plan

DETAILS:

| 1.0 | Background |
| --- | --- |
| 1.1 | This project (Phase 5a) represents the latest phase of a 6 phase rolling programme of environmental improvements across the Lower Kersal estate Phase 3B, was completed end of June 2009. Phase 4, commenced in October 2009 and complete by January 2010. It is anticipated that this Phase 5a will commence at the beginning of January 2010 and be completed by the July 2010. A further sub phase (Phase 5b, which will include for improvements to Hassop Avenue and Hurdlow Avenue), will be the subject of a further Lead Member report in the near future. The improvements to these avenues have been delayed due to the need to undertake further consultation with local residents in regard to the scope of the proposed works. |
| 1.2 | Funding for the project will come from the NDC capital programme. Approval for this funding was agreed by the NDC Finance Sub Committee on 17th June, and the Council’s Capital Programme 2010/11. |
| 1.3 | It is proposed that Phase 5a will continue the earlier phases 1, 2, 3 (including the sub phase of 3B) and 4. As with these previous phases, the emphasis of the improvements will be to reduce the number of cars parked on the streets of the Lower Kersal estate. |
| 2.0 | Details |
| 2.1 | Work will include the construction of 106 in-curtilage driveway installations and lockable metal vehicle gates where possible – although not all properties will receive all of these improvements. Dropped kerbs will be constructed for existing and proposed hard standings. Improvements (where required) will be carried out on both Council and privately owned properties. |
| 2.2 | As indicated in paragraph 2.1, Lead Members should note that not all properties will receive the full menu of improvements, and not all properties will be improved on this phase. Certain properties will be excluded due to them either already having a driveway of a reasonable quality, or the frontage of these properties being too shallow to accommodate a standard driveway. The following street/avenues will, therefore be improved as part of these works: part of Kingsley Avenue; Stanton Avenue; Alsop Avenue; Winster Avenue; Beeston Avenue; part of Northallerton Road (not all properties to be included) |
| 2.3 | As with all phases, detailed consultation will be undertaken with residents. This will involve one to one meetings during which the improvements will be explained, and residents’ consent sought. |
| 2.4 | Funding for this scheme will come from the New Deal for Communities’ Capital Programme in 2009/10 and 2010/11 (£386,894.00), as well as the Council’s Capital Programme 2010/11(£188,250). |
| 2.6 | P. Casey (Land Reclamation) Ltd, one of the Council’s partner contractors for landscape works, will undertake these works. This firm has undertaken all the previous phases, and have proved to be reliable and, where needed, flexible in its work practices. |
| 3.0 | Conclusion |
| 3.1 | It is important that the current momentum regarding the improvements on the Lower Kersal estate is maintained. Commencing Phase 5a will reinforce NDC’s, the Council’s and Salix Homes’ commitment to improving the quality of life of residents on the estate. These improvements will also contribute towards the continuing transformation of the Charlestown and Lower Kersal area. |
| 3.2 | Approval is, therefore, sought from the Leader of the Council and the Lead Member for Housing to complete Phase 5a of the Lower Kersal Environmental Improvements. |

KEY COUNCIL POLICIES:

Salford Community Plan: The project will contribute towards the theme of “A city that’s good to live in”.

Salford City Council Pledges: This project complies with pledges 1, 2, 5 and 7.

Salix Homes Business Plan “Improving Neighbourhoods, making them better” and “Improving homes, making them Decent”

EQUALITY IMPACT ASSESSMENT AND IMPLICATIONS:-

The treatments, which will include construction of in-curtilage driveway installations and lockable metal vehicle gates where possible, dropped kerbs constructed for existing and proposed hard standings, will be carried out on both Council and privately owned properties, supporting equality and diversity across the area.

ASSESSMENT OF RISK:

Generally, the risk is deemed low to medium but this does not account for potential legal issues that might arise as a result of planned work to non Council owned land

Where work to private properties is required in terms of providing driveways and gates, only a license to work on the property is needed. If this is not forthcoming the contractors can move to the next eligible property without detriment to the schedule.

There is a risk that, subject to further consultation, additional funding may be required to complete work on properties within Phase 5a. However, this is deemed to be a small risk.

The implications in making this decision will allow the timely progression of a programme of environmental improvements across the estate which will enhance and improve the area.

SOURCE OF FUNDING:

Phase 5a– Charlestown and Lower Kersal New Deal for Communities Housing and Physical Environment Budget - Lower Kersal Environmental Improvements, Phases 5 to 6) and the Council’s Capital Programme 20010/11

LEGAL IMPLICATIONS Supplied by

Norman Perry Land & Property Team 793 2325

In this particular phase, no purchase of land will be necessary but access to privately owned land will be required. This can be done simply with the permission of the landowner. If any landowner does not consent, then the scheme can still proceed but of course no work will be able to be carried out on that property.

Provided that the Contractor is indemnifying the Council in respect of any claims resulting from his entry onto the land and for the work carried out, then the risk can be regarded as “low”.

FINANCIAL IMPLICATIONS Supplied by

Nigel Dickens – ext. 2585

Anne Lythgoe – ext. 8518

Peter Butterworth – ext. 8701

The expenditure for the project (including Urban Vision’s fees) will be as follows:

Budget Allocation

| Phase 5a | 2009/10 | 2010/11 | Total |
| --- | --- | --- | --- |
| Cost of Works | £180,000 | £333,521 | £513,521 |
| Fees | £21,600 | £40,023 | £61,623 |
| Total | £201,600 | £373,544 | £575,144 |

It was originally anticipated that £386,894.00 of the expenditure would be incurred in 2009/10 and as such the approved NDC Delivery Plan has budget provision for this amount. The slippage of the final contractor payments into 2010/11 does not give a financial concern.  This will be managed by either a corresponding slippage of NDC grant, or by utilising flexibilities across match-funded projects in the NDC programme in both 2009/10 and 2010/11. Therefore by managing the approved NDC and Council resources in 2009/10 as part of the overall regeneration programme in the NDC area, funding is available for the total scheme across the two financial years.

OTHER DIRECTORATES CONSULTED:

.

This report is also subject to a decision by the Leader of the Council

CONTACT OFFICER:

Salix Homes Lead Officer: Colin Goodall (for client) 0161 779 8994

NDC Lead Principal Officer (for client): Brian Enright 0161 607 8548

Urban Vision Project Manager: Cathy Mitchell 0161 779 60.

WARD(S) TO WHICH REPORT RELATE(S):

Kersal

Tim Field, New Deal for Communities, Chief Executive

Paul Walker, Strategic Director for Sustainable Regeneration