______________________________________________________________

REPORT OF THE DEPUTY STRATEGIC DIRECTOR OF HOUSING AND PLANNING

______________________________________________________________

TO THE LEAD MEMBER FOR HOUSING

ON 13th December 2007

______________________________________________________________

TITLE: Update of Salford’s Affordable Housing Programmes 2004-06 and 2006-08.

______________________________________________________________

RECOMMENDATIONS:  That Lead Member for Housing:

- Notes the progress made to date in the delivery of the 2004-06 and 2006-08 National Affordable Housing Programmes (NAHP), particularly those schemes that are currently at risk of not being delivered within Housing Corporation timescales.

______________________________________________________________

1. 	EXECUTIVE SUMMARY

1.1	This report provides the Lead Member with an overview of the delivery of the NAHP over the last two bidding rounds (2004-2006 and 2006-2008).

1.2	The report gives details of the two remaining 2004-2006 allocations, Richmond Hill / Broughton Tavern and Japan Street, that have not yet been delivered, the reasons for this and actions taken to ensure delivery in the future.

1.3	In April 2006 the Housing Corporation announced that its allocation to Salford within the 2006-2008 AHP would be £16,899,554.  Progress in delivering the programme to date is very encouraging with some schemes already completed and many nearing completion. Certain amendments have been made to the programme, meaning the total grant allocation has reduced to £15,008,554.  There are risks to two schemes, which are described in section 5, and action being taken to mitigate these risks is also outlined.

______________________________________________________________

BACKGROUND DOCUMENTS:

Lead Member for Housing report: Review of Salford’s Affordable Housing Programme 2004-2008 and planning for the 2008-2011 bidding round (June 2007).

______________________________________________________________

ASSESSMENT OF RISK:

The potential for not delivering the schemes allocated funding in the AHP 2006-2008 places future allocations to Salford for 2008-2011 at risk.

______________________________________________________________

SOURCE OF FUNDING:

Housing Corporation grant from their National Affordable Housing Programmes 2004-06 and 2006-08.

______________________________________________________________

LEGAL IMPLICATIONS:

Ian Sheard confirms that there are no comments from the legal viewpoint

FINANCIAL IMPLICATIONS:

Nigel Dickens confirms that there are no financial implications

## COMMUNICATION IMPLICATIONS:

## Councillors, senior staff and partner organisations need to be kept informed of those NAHP bids at risk of non-delivery.

VALUE FOR MONEY IMPLICATIONS:

By working pro-actively with partners and delivering schemes we would seek to obtain best value for money from the grant allocation received from the Housing Corporation.

CLIENT IMPLICATIONS:

Many of the schemes that have received an allocation are housing developments on Council owned land and/or within development agreements that the Council has with its private developer partners. Securing the grant allocated is intrinsically linked with the progress of master plans, site assembly and planning applications being delivered by the Council’s private developer partners or Urban Vision on behalf of the Council. Therefore, it is imperative that Housing Market Renewal officers are proactive in ensuring that plans/applications move forward at the agreed pace and specification otherwise there is a risk of losing funding.

PROPERTY:

Many of the schemes that have been allocated funding are housing developments on Council owned land or land/homes that the Council has or is in the progress of acquiring. Therefore, where the Council is underway with the acquisition it is imperative that this continues as programmed to secure the funding. In addition, it is important that the RSL and Urban Vision negotiate land/property values early in the process. As most of the developments are within current master plans/development agreements some discussion and negotiation has already taken place.

_____________________________________________________

HUMAN RESOURCES: Whilst delivery of schemes rests with the RSLs, Salford City Council is responsible monitoring the delivery of the National Affordable Housing Programme 2006-2008 AHP.

CONTACT OFFICER:

Stephen Simm: Strategy and Partnerships Team 0161 9228708

stephen.simm@salford.gov.uk

______________________________________________________________

WARD (S) TO WHICH REPORT RELATE (S):

Langworthy

Broughton

Kersal

Irwell Riverside

Irlam

Cadishead

Swinton North

Winton

Claremont

____________________________________________________________

KEY COUNCIL POLICIES:

Housing Market Renewal,

Draft Housing Strategy 2007-2010,

Neighbourhood Management

Salford Supporting People Strategy 2005-2010.

______________________________________________________________

DETAILS:

2.	2004-2006 Affordable Housing Programme

2.1	Salford was allocated a total of £9,862,233 in Approved Development Programme (ADP) funding (now National Affordable Housing Programme funding) to develop 294 homes in the 2004-2006 period.  By March 2007 £6,398,632 of the allocation had been secured for the development of 225 homes.

2.2	The reduction in grant secured was due mainly to the delay of several schemes in the HMR neighbourhood of Seedley and Langworthy. For further details please refer to Lead Member report ‘Review of Salford’s Affordable Housing Programme 2004 - 2008 and planning for the 2008 - 2011 bidding round (June 2007)’.

  - Two 2004-2006 schemes have been identified as at risk of non-delivery, but following suitable actions the schemes are expected to be delivered early in the new year.  Further details are provided below. Full details of all NAHP 2004-06 schemes can be found in Appendix 1.

  - Richmond Hill / Broughton Tavern (Irwell Valley Housing Association): Located on Blackfriars Road in the Chapel Street HMR neighbourhood, Richmond Hill is the former site of a nursing home and the incorporates the Broughton Tavern, a historic public tavern which has been derelict over the last few years.  The nursing home has been demolished and in its place will be 48 new-build apartments, which will be complemented by an extensive refurbishment of the adjoining Broughton Tavern, creating an extra 9 apartments. Mansell Construction is developing the properties. Irwell Valley received a Housing Corporation grant of £849,108; the total scheme cost will be £8,246,273.

    - The new development will be a combination of one, two and three bedroom apartments, some with roof terraces and all with balconies. Twelve of the higher value apartments will be sold outright, but the other forty-five will be sold on a shared ownership basis. Prices will start at less than £50,000 for a 50% share of a 1-bed apartment, with a rent payable on the remaining equity.

    - Properties were released for sale in spring 2007. To-date contracts have been exchanged on 13 properties and sales are preceding on 9 others. However, the scheme which was due to be completed in November 2007 has now been delayed until February 2008.  This was accountable to poor weather conditions over summer 2007 delaying the build programme.  The Housing Corporation is aware of the revised timescales. Irwell Valley plans a high profile launch of this flagship scheme potentially attended by the Secretary of State, Rt Hon Hazel Blears MP.

2.5  Japan Street (Space Housing Association): Japan Street is a proposed development of 6 four-bed houses in the Broughton Village HMR neighbourhood, and designed to cater specifically for the growing Jewish community in this area.

2.5.1  The delay in progressing the Japan Street scheme has arisen due to a worn dirt track at the site, which the City Council identified as a footpath. Space New Living was granted planning permission for the development of the six units by the City Council, on condition of a footpath closure order being obtained.  Space New Living had been in negotiations with the City Council over a contract sum for the development of the land, but pulled out of these negotiations until the issue of the footpath closure had been resolved.

    - A public inquiry was held on 17th October 2007 the outcome of which confirmed the footpath closure at Japan Street. There is a right of appeal to this decision but this is restricted to procedural error or a misuse of the relevant law. It is therefore unlikely to be successful should an appeal be lodged.

    - Space New Living has been in regular contact with the Housing Corporation over the Japan Street scheme, and has been permitted to retain the £555,317 of grant funding. Crucially the Housing Corporation had agreed to a start on site date of January 2007, without which Space New Living could be asked to return the allocation. The Strategy and Partnerships Team will continue to monitor the situation.

3.	2006-2008 Affordable Housing Programme

3.1	Salford was originally allocated £16,899,544 for the 2006-2008 AHP.  This comprised of £10,084,554 for schemes in 2006-2008, and £2,045,000 for reserve schemes – those that can be brought forward if other schemes in the Salford programme were to slip, or if there was under spend elsewhere in the North West region.  A further £4,770,000 was allocated for schemes in 2008-2011.

  - The Strategy and Partnerships Team collate bimonthly updates on the 2006-2008 programme.  Further details are shown below.

4	Progress in delivering the 2006-2008 NAHP

  - Progress to date with the 2006-2008 programme is very encouraging. Of the twelve confirmed schemes, ten have started work on site. Each of these is expected to complete within the timescales agreed with the Housing Corporation.  The Kimberley Street & Symonds Street, Hamilton Street, Lower Broughton Phase 4 and Devonshire Square schemes are already complete or at an advanced stage. Further details of progression with these schemes and others are given below.

  - Duchy Bank (Manchester Methodist Housing Association - Great Places Housing Group): The Duchy Bank scheme is located in the Seedley and Langworthy HMR Neighbourhood. The site incorporates 37 new build units, of which ten will be available for New Build HomeBuy through Manchester Methodist Housing Association. The affordable units will be two and three bedroom houses. Manchester Methodist received a grant allocation of £320,000, total scheme costs being £1,196,050. Bardsley construction started work on site in October 2006 and expect to be complete on 17th December in 2007.

  - Langworthy Churches (Previously Eccles New Road scheme -  Manchester Methodist Housing Association): Manchester Methodist submitted a bid to the Housing Corporation for a development of 24 two-bedroom and 6 one-bedroom apartments.  The site was in private ownership at the time the bid was made, and Manchester Methodist was only part way through negotiations with the owner to agree a price for the site.  After the Housing Corporation had approved the scheme as part of the Salford AHP, the owner of the site stalled on negotiations and claimed there was interest from other parties.

    - In May 2006, given the uncertainty over the future of the scheme, MMHA applied to the Housing Corporation to transfer the allocation to the Langworthy Churches scheme.  The Housing Corporation agreed to the change, and due to the lower overall cost of the Churches scheme, there was a reduction in the amount of grant funding secured (£1,550,000 as opposed to £1,644,000 for Eccles New Road).

    - The Langworthy Churches scheme will be a mixed-use development incorporating 16 two-bed and 6 one-bed apartments, the church, a community centre, a sports hall and a café.  Due to the substitution of the original scheme the timescales for delivery have been delayed. The scheme started on site in March 2007 (previously June 2006 - Eccles New Road) and will be completed by March 2008 (previously June 2007 - Eccles New Road).

  - Devonshire Square (Contour): This scheme is situated in the Higher Broughton Neighbourhood Renewal Area. Contour Housing Group made a successful bid to the Housing Corporation for £804,800 of grant funding to build 30 houses of New Build HomeBuy tenure. The build programme for this scheme has progressed quicker than expected with completion expected in February 2008. Total scheme costs are expected to be £4,251,194.  SCC is confident that the scheme will be completed on time, and is engaging with all partners to ensure that robust, joint marketing and promotional activities are in place for this scheme.

  - Lower Broughton Phase 1 (Contour): Located in the Lower Broughton Neighbourhood this scheme is a part of the first phase of the ‘New Broughton’ project, which has been developed over the past two and a half years in partnership with Countryside Properties. The project will provide a sustainable new community of over 3,500 mixed-tenure homes and a full range of community facilities and services.  Contour successfully bid for £3,520,000 of grant funding to build a mixture of two, three and four bedroom houses and apartments. A total of 92 affordable units for social rent have been completed and successfully handed over to residents.

  - Hamilton Street (Contour Housing Group) This scheme is situated in the Broughton Neighbourhood Renewal Area. The site includes the development of nine new build units of which 6 two bedroom houses will be offered for New Build HomeBuy. Contour Housing Group made a successful bid to the Housing Corporation for £168,500 of grant funding with total scheme costs are expected to be £740,269.  The development replaces cleared terraced stock previously owned by Irwell Valley Housing Association. Richardson Projects started on site in December 2006 and completed construction in December 2007. The first 7 properties have been handed over to Contour, the remaining 2 will be handed over week commencing 10th December 2007.

  - Chapel Street (Contour): Contour received an allocation of £110,000 from the Housing Corporation for five New Build HomeBuy units, which would have been part of a larger private development being led by Hightop Developments Limited.  However, soon after receiving the allocation, plans for the development by Hightop were withdrawn.

4.7.1	Since this time, Contour have reviewed a number of developments in the Chapel Street area but have been unable to secure a scheme.  This has mainly been due to high land values and the fact that developers have not been willing to give the required discounts as property in the area has been selling at full value.

4.7.2   Contour is currently proposing to use the Housing Corporation grant for this scheme (£110K) to fund an additional 3 Shared Ownership houses on the Hamilton Street scheme. Although this will result in the net loss 2 units (the original Chapel Street allocation was for five units) the total number of people the units are designed for will be the same (15 people). This change will also affect the level grant per unit - originally £22,000 per unit (110/5) now rising to £36,700 per unit (110/3). Contour are awaiting a decision from the Housing Corporation regarding this proposal.

4.8    Kersal High School (Contour) - Salford successfully secured three allocations for the Kersal High School site from the 2006-2008 AHP.  The bids were for a mix of housing for social rent and for shared ownership, as part of a wider development plan in the NDC area of Charlestown and Kersal.  The units were to be delivered through Contour Housing Association, the lead RSL for this part of the city, working in conjunction with the developer partner, Miller Homes.

4.8.1	In relation to the two allocations that have to be delivered within the 2007-2008 financial year (the five rented units, and the New Build HomeBuy phase 1), there have been delays caused by unforeseen planning and contractual issues between the council and the developer, Miller Homes.

4.8.2	A series of meetings has been held with the developer and they have now confirmed that the five rented units (originally due in August 2007) and the three New Build HomeBuy units (originally due in November 2007) will be completed by March 2008.  The remaining three New Build HomeBuy phase 2 units (due August 2008) will be completed on time.

4.8.3	It is essential that the March 2008 deadline is achieved for the delivery of the rented units and the first phase of the New Build HomeBuy units.  This has been made clear to the developer in a series of meetings between their representatives, the council’s HMR management team, and Contour Housing Group. The Housing Corporation has agreed to the deadline for the five rented units and the Homebuy phase 1 units being moved back to March 2008. The Strategy and Partnerships Team will continue to closely monitor the situation

4.9	Salford Phase 13 (William Sutton): Located in the Pendleton Neighbourhood Renewal Area this scheme will provide 6 two and three bedroom houses and 8 two bedroom apartments. All units will be available for New Build HomeBuy.  William Sutton was successful in securing £772,254 grant funding, total scheme costs being £1,438,352.

The scheme is located on the original site of the Tanners Green flats off Nursery Street. There were delays to the start of construction due to the diversion of a gas main and issues with access to the site prior to demolition. These have now been resolved, demolition complete and construction has begun on site. The construction period should take no longer than 52 weeks, with practical completion expected to be March 2008.

4.10 	Kimberley Street and Symonds Street (Space New Living): Kimberly and Symonds Street are located in the Broughton Village HMR Neighbourhood. This scheme was originally a reserve AHP allocation. The confirmed allocation was on Ackworth Road, which is located in the West Salford ward of Swinton North. This scheme proved unpopular with local residents and ward councillors For further details please refer to Lead Member report ‘Review of Salford’s Affordable Housing Programme 2004 - 2008 and planning for the 2008 - 2011 bidding round (June 2007)’.

    - Space identified two council-owned properties on Kimberley Street and one on Symonds Street, that were long-term voids in need of extensive refurbishment, and that were causing blight to the neighbourhood.  Lead Member approved the disposal of these properties to Space New Living HA on November 16th 2006.  Refurbishment on the properties was completed with work starting on site in January 2007. Kimberly Street became occupied by a tenant in May 2007 and Symonds Street in June 2007.  The grant allocation for these properties was £80,000, with the total cost of the scheme being £119,701. Both properties are of a social rented tenure.

  - Salford Women’s only accommodation (Manchester Methodist Housing Association): This supported accommodation scheme is specifically for resettling women who have been accommodated inappropriately in secure settings due to their health related offending past. Manchester Methodist, working in partnership with care provider ‘Imagine’ were successful in obtaining £692,000 of grant monies to build 8 two bedroom apartments that will specifically meet the needs of this client group. Total scheme costs will be £1,665,300. All apartments are for social rent.

4.11.1This scheme has suffered a number of delays; most recently the diversion of a BT telephone line on the site has caused delays to construction works.  All issues have now been resolved and works started on site in May 2007 (originally May 06) and are due for completion in March 2008.  The Housing Corporation have agreed to the revised timescales.

### 5.0	Schemes at risk 2006-2008 AHP

  - Of the approved schemes in the 2006-2008 AHP, two are considered to be at risk of not being delivered against Housing Corporation timescales.  Further details are provided below.

  - St Mark’s Lane (Manchester Methodist Housing Association): This scheme is situated in the Higher Broughton neighbourhood and lies adjacent to the Japan Street site referred to in section 2.5 of this report. Manchester Methodist made a successful bid to the Housing Corporation for £488,000 of grant funding with total scheme costs expected to be £1,075,200. The site includes the development of 8 three and four bedroom houses of which four are for New Build HomeBuy, the remainder for social rent.  The St Marks Lane scheme was due to start on site in July 2007 and to be completed in May 2008. However due to the sites close proximity to Japan Street, Space New Living were reluctant to progress work until the outcome of the Japan Street public inquiry was known.

    - This scheme is now been taken forward. A land valuation and site investigation are underway and Space is currently in the process of negotiating a price for and acquiring the land from Salford City Council. A planning application is due to be submitted in December 2007.  Space expect to start on site in March 2008. The Housing Corporation is familiar with the complexities of this scheme but has not formally agreed the revised start on site date of March 2008. Space New Living will meet with representatives from the Housing Corporation week commencing 10th December 2007 to discuss this scheme. The Strategy and Partnerships Team will continue to monitor the situation closely and take any further appropriate action.

5.3	Chapel Street (Contour): This scheme although considered at risk of non delivery is currently closely linked with Hamilton Street scheme. Therefore please refer to section 4.7.

6.0       Recommendations

6.1      The Lead Member for Housing is asked to:

- Note the delivery of the outstanding ADP 2004-06 schemes, specifically Japan Street (Space New Living) and Richmond Hill / Broughton Tavern (Irwell Valley).

- Note the positive progress made to date in the delivery of the 2006-2008 Affordable Housing Programme, and the actions identified to address those schemes that have been identified as currently at risk of not being delivered within Housing Corporation timescales.

Bob Osborne, Deputy Director of Housing and Planning

| Appendix 1 – Housing Corporation ADP 2004-2006 Secured |
| --- |
| Neighbourhood | Ward | RSL | Scheme | Total costs | Grant | No. of Units | New build / Rehab | Tenure | Type |
| Seedley and Langworthy | Langworthy | MMHG | Salford Re-improvements | £427,904 | £213,953 | 16 | Rehab | Rent | 16 x 2 / 3 bed houses (works to existing properties) |
|  | Langworthy | MMHG | Langworthy rehabs | £481,163 | £434,513 | 6 | Rehabs | Rent | 6 x 2 / 3 bed houses |
|  | Langworthy | MMHG | Alpha street phase 2 | £1,126,888 | £661,768 | 8 | New build | Rent | 8 x 2 / 3 bed adapted bungalows |
|  | Langworthy | MMHG | Improvement for Sale 1 | £66,751 | £20,000 | 1 | Rehab | Shared ownership | 1 x 2 bed house |
| Broughton Village | Broughton | Space | Salford re-improvements | £385,882 | £166,965 | 21 | Rehab | Rent | 21 x 2 / 3 bed houses (work to existing properties) |
|  | Broughton | Space | Salford re-improvements | £201,500 | £118,684 | 13 | Rehab | Rent | 13 x 2 / 3 bed houses (works to existing properties) |
|  | Broughton | Space | Winterford Road | £1,077,292 | £637,541 | 11 | New build | Rent | 8 x 2bed bungalows and 3 x 2bed wheelchair accessible bungalows |
|  | Kersal | Space | Japan Street | £840,379 | £555,319 | 6 | New build | Rent | x 4 bed houses |
| Pendleton | Langworthy | WSHA | Salford ph 11 | £651,834 | £277,506 | 7 | New build | Rent | 2 x 2 bed houses, 3 x 3 bed houses and 2 x 4 bed houses |
|  | Langworthy | WSHA | Salford ph 12 | £1,605,268 | £494,012 | 13 | New build | Rent | 1 x 2 bed bungalow, 3 x 2 bed houses, 5 x 3 bed houses 4 x 4 bed houses |
| Chapel Street | Irwell Riverside | IVHA | Richmond Hill / Broughton Tavern | £8,246,273 | £849,108 | 57 | New build & rehab | Shared ownership and sale | 48 x New Build HomeBuy & 9 sale |
|  | Irwell Riverside | IVHA | Springfield Lane (US) | £6,875,840 | £1,053,914 | 50 | New build | Shared ownership | 50 x 1 / 2 bed apartments |
|  | Irwell Riverside | IVHA | Carolina House | £738,263 | £248,321 | 6 | New build | Shared ownership | 2 / 3 bed houses |
| Supported accommodation | Irlam | St. Vincent’s | The Crescent | £248,040 | £78,966 | 2 | New build | Rent | 2 x wheelchair accessible bungalows |
|  | Cadishead | St. Vincent’s | Sussex Road | £292,500 | £199,789 | 2 | New build | Rent | 2 x wheelchair bungalows |
|  | Cadishead | St. Vincent’s | Hamilton Avenue | £513,630 | £319,051 | 4 | New build | Rent | 2 x wheelchair bungalows |
|  | Langworthy | MMHG | 81 Lower Seedley Road | £69,222 | £34,611 | 1 | Rehab | Rent | 1 x 4 bed house |
|  | Langworthy | MMHG | 94 Claremont Road | £69,222 | £34,611 | 1 | Rehab | Rent | 1 x 3 bed house |
| Total |  |  |  | £23,917,851 | £5,737,525 | 225 |  |  |  |

| Appendix 2 – Housing Corporation Allocations 2006-2008 (reserve schemes shaded grey, SOS = start on site, PC = practical completion) |
| --- |
| Neighbourhood | Year | Ward | RSL | Scheme | Total Costs | Grant | No. of Units | SOS | PC | New build/ Rehab | Tenure | Type |
| Seedley and Langworthy | 06/07 | Langworthy | MMHG | Urban Splash | £5,115,688 | £1,629,000 | 50 | 07/06 | 07/08 | Rehab | Newbuild homebuy (NBHB) | 25 x 2/3 bed houses |
|  | 06/07 | Irwell Riverside | MMHG | Duchy Bank | £1,196,050 | 3320,000 | 10 | 09/06 | 04/08 | New build | NBHB | 6 x 2/3 bed houses |
|  | 06/07 | Langworthy | MMHG | Eccles New Road | £3,736,576 | 31,644,000 | 30 | 06/06 | 06/07 | New build | 24 NBHB 6 rent | 24 x 2bed and 6 x 1 bed apartments |
|  | 07/08 | Langworthy | MMHG | Langworthy South East | £3,445,650 | £747,000 | 24 | 10/07 | 12/08 | New build | NBHB | 24 x 2/3 bed houses |
| Broughton Village | 07/08 | Kersal | MMHG | St. Mark’s Lane | £1,075,200 | £488,000 | 8 | 07/07 | 05/08 | New build | 4 NBHB 4 rent | 4 x 3/4 bed houses |
|  | 06/07 | Broughton | Contour | Devonshire Square | £3,403,164 | £804,800 | 30 | 08/06 | 09/07 | New build | NBHB | 30 x houses |
|  | 07/08 | Broughton | Contour | Clarence street phase 1a | £5,343,867 | £3,520,000 | 44 | 10/07 | 12/08 | New build | Rent | TBC |
|  | 08/09 | Broughton | Contour | Clarence street 1b | £6,951,117 | £4,640,000 | 58 | 10/08 | 08/09 | New build | Rent | TBC |
| Hill Top area | 06/07 | Broughton | Contour | Hamilton Street | £740,269 | £168,500 | 6 | 09/06 | 09/07 | New build | NBHB | 6 x 2 bed houses |
|  | 06/07 | Broughton | Contour | Yew Street | £615,920 | £206,000 | 6 | 10/06 | 09/07 | New build | NBHB | 6 x 2/3 bed houses |
| North Irwell Riverside | 07/08 | Kersal | Contour | Kersal High School Rent | £686,979 | £458,000 | 5 | TBC | 08/07 | Rent | Rent | 5 x 2/3 bed houses |
|  | 07/08 | Kersal | Contour | Kersal High School phase 1 | £496,180 | £112,000 | 3 | TBC | 11/07 | New build | NBHB | 3 x 2 bed houses |
|  | 08/09 | Kersal | Contour | Kersal High School phase 2 | £493,296 | £130,000 | 3 | TBC | 08/08 | New build | NBHB | 3 x 2/3 bed houses |
| Pendleton | 06/07 | Langworthy | William Sutton | Salford phase 13 | £1,438,352 | £772,254 | 14 | 11/06 | 11/07 | New build | Rent | 8 x 2 bed apartments 1 x 2 bed house 5 x 3 bed house |
| Chapel Street | 07/08 | Irwell Riverside | Contour | Chapel Street | £710,168 | £110,000 | 5 | TBC | 01/08 | New build | NBHB | 5 x 2 bed apartments |
| Claremont Village | 06/07 | Claremont | Harvest | Irlam Square | £835,319 | £210,000 | 7 | 11/06 | 09/07 | New build | NBHB | 7 x 2/3 bed houses |
| Supported accommodation | 06/07 | Swinton North | MMHG | Ackworth Road | £119,701 | £80,000 | 1 | 11/06 | 04/07 | Rehab | Rent | 1 x 4 bed house |
|  | 06/07 | Winton | MMHG | Salford women’s only accommodation | £1,665,300 | £692,000 | 8 | 05/06 | 05/07 | New build | Rent | 8 x 2bed apartments |
| Total |  |  |  |  | £38,068,856 | £16,899,554 | 312 |  |  |  |  |  |

# Text boxes

Part 1