| Part 1 | ITEM NO. |
| --- | --- |

REPORT OF THE HEAD OF HOUSING TO

TO THE LEAD MEMBER FOR HOUSING ON MAY 18TH, 2006

AND

THE LEAD MEMBER FOR COMMUNITY, HEALTH AND SOCIAL CARE.

ON, 16TH MAY, 2006

TITLE : Detailed delivery and management arrangements for the new Citywide Handyperson Service.

RECOMMENDATIONS :

- That the Lead Member for Housing and the Lead Member for Health and Social Care note the development of the Business Plan and delivery model for the new citywide handypersons scheme.

- That the Lead Member for Housing and the Lead Member for Health and Social Care authorise contracts to be signed with Swinton Community Business trading as Helping Hands, the selected partners.

EXECUTIVE SUMMARY:

This report makes recommendations further to those made in a previous report submitted 9th March 2006 (Housing) 11th March 2006 (CHSC), which identified the preferred partner to work with the City Council to develop and deliver a citywide handyperson scheme and the steps required to facilitate the establishment of such a service.

To support these recommendations this report provides further information regarding the key features of the scheme being proposed and a detailed action plan which provides the basis for the Business Plan for the new service.

Additionally, the report provides specific details of the plans for client eligibility and type of works which will be prioritised under the new scheme.

This report includes the steps being taken to protect the interests of clients of existing handyperson schemes during the transition to the citywide scheme.

BACKGROUND DOCUMENTS :

(Available for public inspection)

- 11th October 2004 Joint Report  of the Director of Strategy and regeneration, Director of Community and Social Services - “City wide Handyperson Service In Salford”

- 9th March 2006 Report of the Head of Housing to the Lead Member for Housing on March 9th, 2006  and the Lead Member for Community, Health and Social Care on, 11th March, 2006 – “Appointment of a partner organisation to provide a citywide handypersons service”

- Tender Documentation

ASSESSMENT OF RISK:

- The award is made to a small social enterprise, this award will be substantially larger than any contract they have previously managed; this risk is mitigated as follows:

- Their capacity to grow the service is underpinned by confirmation that the organisation has increased management capacity since securing preferred partner status.

- The service demonstrated the highest quality and a track record of 5 years delivering a similar service in Salford during tender processes.

- The initial stages of the contract are being controlled and monitored by the Housing and Planning Project Team, who are assisting the service to produce an appropriate business plan with key milestones and performance measures.

- A Contract Management Group has been established which is accountable to the Older People’s Partnership Board and Independent Living Partnership Board.

SOURCE OF FUNDING:

Funding for the service has been identified from a range of sources

- A provision of £250,000 exists within the Housing Capital Programme for 2006/07 to support the Citywide Handyperson Service.

- Existing Community Health and Social Care (Adult Commissioning) revenue funding for handyperson schemes in the City of up to £42,000 will be made available to support the new service.

- The Handyperson Service will also derive additional funding, e.g. external bids, for the provision of a range of services that will be the subject of an agreed charging policy.

COMMENTS OF THE STRATEGIC DIRECTOR OF CUSTOMER AND SUPPORT SERVICES (or his representative):

- LEGAL IMPLICATIONS				Provided by : Tony Hatton

Legal Services have been fully involved in the development of the formal contract with the preferred partner.

- FINANCIAL IMPLICATIONS			Provided by : Nigel Dickens

Provision exists within the Housing Capital Programme for 2006/07 to accommodate this scheme.

- COMMUNICATION IMPLICATIONS

The tender specification contained a clear requirement, reflected in the Business Plan that the preferred partner would work with the City Council’s Marketing and Communications Division to produce a comprehensive communications strategy for the Citywide Handyperson Scheme. This strategy is addressing, among other issues, the branding of the scheme including use of logos and livery, the promotion of the scheme to existing and potential clients, the promotion of the scheme to existing and potential commissioning bodies, the dissemination of good practice identified through the operation of the scheme through appropriate journals and magazines and procedures for responding to press enquiries.

4.  MONITORING OFFICER COMMENTS		Provided by: Pauline Lewis

Report approved.

PROPERTY (if applicable): Not applicable

HUMAN RESOURCES (if applicable): The workload associated with managing the contract with the preferred partner is built into the work-plan of the appropriate team within Housing Services.

The tender specification requires the preferred partner to address any TUPE issues arising from the impact of the establishment of the citywide services on existing local handyperson schemes.

CONTACT OFFICER : Clare Ibbeson		Tel No. 0161 922 8710

WARD(S) TO WHICH REPORT RELATE(S):

All wards

KEY COUNCIL POLICIES:

Older People’s Strategy

Better Care Higher Standards in Salford

Promoting Independence Agenda

Health Agenda – Falls Prevention and Delayed Discharge

Regeneration

Housing Environment – minor repairs

Economic – affordable services, jobs creation, training

Crime and Disorder

Social Inclsuion

Supporting People

Procurement Strategy

DETAILS (Continued Overleaf)

##### Background

  - Following a review of services to older and vulnerable residents in the City it was recognised that the establishment of a citywide handyperson service would have a significant positive effect on several of the Council’s themes and the Pledges. This view was endorsed by elected members.

  - In the financial year 2004/05 a funding structure was identified that would allow capital resources to be used to support the operation of a Citywide Handyperson Service and allow the development of such a scheme to be taken forward.

  - The City Council and its partners have worked to procure an organisation to deliver such a service, by creation of a tender specification in line with current strategic requirements. The tender process was completed in March 2006.

  - As a result of the tender process a report, “Appointment of a partner organisation to provide a citywide handypersons service”, was submitted seeking Lead Member approval of the partner selected through the tender process.

  - This report is submitted to provide the Lead Members for Housing and Community, Health and Social Care with the details of the ongoing management and stakeholder arrangements to be put in place to ensure the service achieves the objectives set for it. This report also provides a full draft of the contract that will govern the delivery of works funded by City Council resources.

  - This report also provides details of the steps taken to establish the Citywide Handyperson Service since March. This report also demonstrates that the Business Model for the new service is robust and in accordance with Council priorities and the need to protect the interests of the City Council and the clients of the handypersons service and guide and support the scheme’s development.

##### Development of Business Plan and Key Features of the Citywide Scheme.

  - Reports to Lead Member have previously indicated that the service will adopt a partnering approach to agree the business plan in order to integrate the new service fully into the Social Care, Health and Housing framework already available. The tender specification was, therefore, not overly prescriptive in the methodology for the selected partner in order to benefit from the potential that a new organisation and associated working practice would bring to a partnership.

  - The following section of the report clarifies the steps to be taken to realize agreement on achieving the priorities and maximising customer benefit and introduces the first draft of the Business Plan and actions arising that have been formed in agreement with the selected partner, Helping Hands.

  - A Contract Management Group has been established in line with the Council’s accountability and customer involvement requirements. It is made up of senior officers of the Council and the Primary Care Trust and a Service User Representative will be appointed via the User Development Scheme for Older and Vulnerable People.

  - The Contract Management Group will be responsible for monitoring the business and financial performance of the contract. It will also have the role of setting strategic steer on behalf of the Partnership Boards and to ensure that eligibility for capital funded handypersons tasks are targeted judiciously.

  - Additionally, an Advisory Group has been established and charged with supporting the new service to quickly develop to its broadest potential. The Advisory Group will create links to the service from Community Safety Unit, Affordable Warmth, Protection of Vulnerable Adults, Communications and Marketing, Occupational Therapy, Fire Officer, Age Concern and Adult Social Care Teams.

  - Service User Representatives, recruited via the User Development Scheme for Older and Vulnerable People will also attend this group

  - A key priority of the Advisory Group will be to build links with the Salford Home Improvement Agency, which will also be represented on the group, as first steps towards a seamless service approach that can be offered to older and vulnerable people for their home improvement, maintenance and repair needs.

  - Reports to Lead Member have previously indicated that work will be undertaken with Helping Hands on a range of practical issues, in line with the commitment to partnership approach specified in the tender process. A Draft Action Plan was provided at that time, outlining these issues.

  - The Draft Action Plan now forms the basis of the Business Plan for the new organisation. The current version of the Business Plan is available at Appendix 1.

  - The key areas of development in each area of the Business Plan were as follows, a summary of developments in each area is attached at Appendix 2;

    - Working Relationships

    - Operational Arrangements – confirming the model

    - Transfer of Undertakings

    - Marketing

    - Resource Requirements

    - Contract Monitoring and Evaluation

    - Financial Monitoring Framework

  - A draft set of Eligibility Criteria is available at Appendix 3 (Client Classification for Priority and Non-Priority Work). A draft Charging Policy is available at Appendix 4 (Helping Hands Pricing Structure). A first draft of Priority Works is available at Appendix 5 (Job Classification for Priority and Non-Priority Work). These will be reviewed and developed by Helping Hands and monitored by the Contract Management Group.

  - Reports to Lead Member have previously indicated that a comprehensive range of performance indicators will be developed that are consistent with the City Council Performance Management Framework and appropriately reflect the roles of the proposed service. These are set out in Section 6 of the Business Plan (Appendix 1).

  - Further, the Contract Management Group has the remit to review the measures and targets and to monitor performance particularly against customer satisfaction and has set itself a role to contact customers of the service directly and regularly to measure satisfaction and quality of service and to ensure continuous improvement.

  - The performance of the Service will be monitored and reported to the Lead Members on a regular basis.

- Next Steps

  - Officers will continue to work with and support the service. An officer of the Community Housing Projects Team has been appointed as a contract liaison officer.

  - The Contract Management Group will meet regularly to monitor performance, review targets and ensure customer satisfaction and continuous improvement. Reports will be forwarded to the Lead Members on a regular basis to reflect decisions and monitor performance.

  - The Advisory Group will meet bi-monthly to quickly develop the new citywide handypersons service to its broadest potential, creating the appropriate links which will guide the service strategically and securing referral routes to and from the service.

  - Contracts will be signed when approval to do so is granted by Lead Members. A contract letter (Appendix 6) has been drafted by SCC Legal Services which will commit the service to the assurances made within their original tender submission and SCC general terms and conditions.

  - Once contracts are signed staff offered under TUPE regulations for transfer to the new service will be relocated to Helping Hands to commence delivery of the new citywide handypersons service and clients will be welcomed to the new service by Helping Hands on behalf of Salford City Council.

- Conclusion

  - The Contract Management Group is satisfied that Helping Hands have worked in partnership with City Council representatives to develop an appropriate business plan that reflects agreed priorities, maximises benefits to customers and reduces dependence on public subsidy over time through the development of additional chargeable services and a clear charging policy.

  - Officers Council continue to be satisfied that the working partnership is sound and will realise the commitments made in Helping Hands’ tender submission and achieve the expected objectives for the new citywide handypersons service in a sustainable manner.

  - The service has commenced developing links through proper accountable channels, through Independent Living Partnership Board and Older People’s Partnership Board.

  - The Handyperson Service has commenced developing links to existing key services, in particular the Salford Home Improvement Agency and Salford Direct.

  - I therefore request that the Lead Member for Housing and the Lead Member for Health and Social Care approve the recommendations that

- They note the development of the Business Plan and delivery model for the new citywide handypersons scheme.

- They authorise contracts to be signed with Swinton Community Business trading as Helping Hands, the selected partners to deliver new citywide handypersons service.