| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- |

REPORT OF THE HEAD OF HOUSING SERVICES

TO THE LEAD MEMBER FOR HOUSING SERVICES

ON 23rd OCTOBER 2003

TITLE :	PROGRESS ON HOUSING STRATEGY WORKPLAN

RECOMMENDATIONS:

That approval is given to continue to develop the Housing Strategy in accordance with the work plan.

EXECUTIVE SUMMARY:

The development of a fit for purpose Housing Strategy is a priority for the Council. A previous work plan has been approved; this is a working document and is continually subject to amendments and additions.

In particular, the recently formed Housing Strategy Group (Salford City Council Officers) will review progress against the work plan as a regular agenda item.

Significant progress has been made in developing the structure behind the strategy. In addition to the well-attended Housing Strategy Group, the proposed staffing restructure of Housing Services is underway.

Salford’s Housing Partnership has also received approval. The Partnership is due to meet in November for the first time to discuss terms of reference.

BACKGROUND DOCUMENTS:

Housing Strategy Work Plan

Structure

ODPM Fit for Purpose Housing Strategy Guidance

ASSESSMENT OF RISK

The ongoing options appraisal process continues to significantly impact on the housing strategy. The delivery of options appraisal and the housing strategy are dependent on the recruitment of additional staff.

A critical part of the housing strategy will be to make significant links with major initiatives across the City, in particular HMRF, NDC and SRB 5. These links are beginning developed but again rely on the commitment of current staff.

THE SOURCE OF FUNDING IS

LEGAL ADVICE OBTAINED

N/A

FINANCIAL ADVICE OBTAINED

N/A

CONTACT OFFICER:

Gill Leng

WARD(S) TO WHICH REPORT RELATE(S)

All

KEY COUNCIL POLICIES

(4) WORK PLAN

OBJECTIVE ONE; TO UNDERSTAND OUR HOUSING MARKETS AND NEEDS

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Develop detailed market information including: - | PL/Mhe/MH/PH |  |  |
| Housing Demand Study | Mhe/PL/GL |  |  |
| Finalise | Mhe/MH | Draft end August Presented to Core Strategy Group 25/9/03 |  |
| Dataset interrogation/analysis to inform: - |  |  |  |
| Stock Options Appraisal Demand for NPHL stock on area basis | Mhe/CM | Initial Asset Appraisal framework Aug03 |  |
| Development of older persons accommodation | MH /CM | Draft Independent living study Sept03 - |  |
| Development of 04-06 ADP bids Information to support housing mix/tenure for all schemes | AH/MD | Anticipated November Bid Submission |  |
| Development/remodelling housing in NDC Demand for all tenures in NDC area | Mhe/MD |  |  |
| Development of housing in SRB 5 Demand for all tenures in SRB area |  |  |  |
| Development of housing in Salford Central; incl. HMRF areas not mentioned above and Chapel Street |  |  |  |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Stock condition in public and private sectors – comparison of anecdotal information and stock condition surveys | JW/AA/HS |  |  |
| Health information – SP strategy development |  |  |  |
| Homelessness – links to research completed as Homelessness Strategy |  |  |  |
| Other specific needs issues – income, overcrowding etc. |  |  |  |
| Housing Moves Survey | Mhe | Due to go out October. Findings before Xmas |  |
| Quality of Life study | Cexecs/MH |  |  |
| CURS/sub-regional intelligence and analysis | Mhe/JR |  |  |
| Other demographic, economic and other intelligence – development of indicators for early warning system | Mhe/MH/PH |  | Statistical Information Group Planning Information Group |
| Development of 2001 census information | Mhe/MH/JR | Analysis software not out yet (sept) |  |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Development/format of regular market information briefings: - | Core Housing Strategy Group | Uni. Of Salford proposal on hold until HNS finalised and internal information considered. | £9,000 |
| Area Plan development Develop Swinton Area Housing Plan Framework | MD/CM | Circulation w/b 13th October |  |
| Early warning system development | PH/Mhe | Delayed by HMRF development but CHSG priority |  |
| Arcview 8 Licences and training | GL/JW/Planning | Demo and meeting to discuss IT implications 5th November 2003 | £10,000 (poss. impact on IT systems) |
| Investigate Consumer Information system (Mosaic etc) | Mhe/GL | Ongoing | Cost implications |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Other need/demand analysis: - | PL/CHSG |  |  |
| Identify gaps in needs information, in partnership with Supporting People | Mhe/JC |  |  |
| Homelessness research | Janice/MHe | Homelessness Action Plan – implementation team in place |  |
| Cross boundary issues, to be identified from HNS/CURS initially | Mhe/MH |  |  |
| Analysis of demand for: - |  | November |  |
| Older persons accommodation: - NPHL RSLs Others | GL/MH/MD | Information identified and requested from RSLs and NPHL by |  |
| Social rented general let: - NPHL RSLs | CM/MD |  |  |
| Private rented | Mhe/MH |  |  |
| Owner-occupation Shared ownership Other | Mhe/MH |  |  |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Housing Strategy Consultation and Involvement Plan: - | MH/NB | Map of housing related consultation undertaken across the City |  |
| Identify housing related consultation across City: - |  |  |  |
| RSLs |  |  |  |
| Supported housing, in conjunction with Supporting People Strategy Development |  |  |  |
| NDC |  |  |  |
| SRB 5 |  |  |  |
| Broughton |  |  |  |
| SRB 3 |  |  |  |
| Liverpool Road |  |  |  |
| Ordsall |  |  |  |
| HMRF |  |  |  |
| Pendleton/CABE |  |  |  |
| Chapel Street |  |  |  |
| NRAs: - Weaste, Duchy, Charlestown & Kersal |  |  |  |
| Communities of interest (BVR recom.) |  |  |  |
| Links to best practice and other consultation initiatives in City |  |  |  |
| SRB5 Good practice in Community Involvement – framework |  |  |  |
| Consultation Network |  |  |  |

OBJECTIVE TWO: 	MANAGING THE HOUSING MARKET AND WIDENING CHOICE

The Enabling Function – how will Salford ensure that housing need and demand priorities are met?

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Monitoring, and enabling effective delivery of services to, Council owned housing and tenants: - |  |  |  |
| Weekly monitoring meetings with NPHL | KS |  |  |
| Stock options appraisal involvement | PL |  |  |
| Quarterly information provided to HS by NPHL to inform sustainability/market analysis including non-decency targets and progress. | TBA |  |  |
| Initiative enabling meetings chaired by Housing Strategy: - |  |  |  |
| NDC | DV/JC/BE |  |  |
| SRB | TBA |  |  |
| Broughton | DV |  |  |
| HMRF | TBA |  |  |
| LSP (Floor target monitoring) |  |  |  |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Monitoring, and enabling effective delivery of new, Housing Association developments |  |  |  |
| RSL programme meetings including: - Development Delivery of decent homes Management issues | AH |  |  |
| Evaluate joint commissioning/partnership arrangements with RSL’s Central West | TBA |  | RSL resource |
| Initiative enabling meetings chaired by Housing Strategy: - |  |  |  |
| NDC | DV/JC/BE |  |  |
| SRB | TBA |  |  |
| Broughton | DV |  |  |
| HMRF | TBA |  |  |
| Development of dynamic stock condition database (Liverpool Asset Mgt. Project) |  | Dave Cooper providing information to AA |  |
| Review and develop process to ensure delivery of supported housing priorities of Council and partners e.g. PCT | JC/PL |  |  |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Enabling access and choice for residents: - |  |  |  |
| Complete choice based lettings proposal | TBI | Principle to October Conclusion by 04 | Cost implications of choice based lettings to be evaluated as part of exercise |
| Carry out review of access to housing and housing related services by BME communities and other minority groups | PL/ MH |  |  |
| Links to Peer Group 4 |  |  |  |
| SRB 5 initiatives – Building Community Cohesion |  |  |  |
| Maintaining the private sector |  |  |  |
| HMR prospectus approval/delivery team in place | KS | October | HMRF |
| Commence review of housing renewal strategy and policy | EJW/JC ? | September ? |  |
| Other tool development (as appropriate):- |  |  |  |
| Home ownership schemes |  |  |  |
| Equity release |  |  |  |
| Accreditation/licensing |  |  |  |
| Home SWAP |  |  |  |
| HMOs |  |  |  |
| Enforcement policy development |  |  |  |
| Empty property strategy |  |  |  |
| Financial assistance policy |  |  |  |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Monitoring and enabling private sector residential development | Planning |  |  |
| UDP Review |  |  |  |
| Local development frameworks |  |  |  |
| Developing capacity to influence tenure |  |  |  |
| Ensuring quality and sustainability |  |  |  |
| UDP | Planning |  |  |
| Design and lifetime homes; | RSL/KS & DEvans/BWhitmarsh |  |  |
| CABE | RO |  |  |
| RSL Programme meetings |  |  |  |
| Promotion of Egan principles/partnering across all sectors/establish Developers Forum | GL to lead with support from KS/TBI RSL/Planning-DC/NRHL | October/November |  |
| Develop an appropriate vehicle to ensure stakeholder involvement at a strategic level | KS |  | RSL resource |
| Terms of reference for ‘Partnership’, including decision-making and commissioning role in relationship to other structures e.g. Supporting People CB | KS |  |  |
| Finalise structure for strategy development and delivery |  | Structure proposal approved by GONW/LMB |  |
| Promote Partnership internally and externally |  |  |  |

OBJECTIVE 3: MEETING VULNERABLE PEOPLE’S HOUSING AND HOUSING RELATED SUPPORT NEEDS

To develop and deliver a choice of suitable accommodation and housing related support to enable all residents to maintain an independent lifestyle. The Supporting People Strategy will develop priorities in conjunction with Housing through the Core Strategy Group; both strategies will identify Supported Housing schemes and services; SP revenue and Housing Capital.

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Links to Homelessness Strategy and Action Plan | Janice/MHe | July completion Attendance at Homelessness Forum Implementation Group mtgs |  |
| Supporting People Strategy | Joe Coogan | August – initial discussion |  |
| Needs |  | August |  |
| Consultation |  |  |  |
| Strategic links to other health and care providers including: - |  |  |  |
| Domestic Violence; |  |  |  |
| Learning disability -. |  |  |  |
| Links to Asylum Seeker action and priorities/NASS |  |  |  |
| Direct links to health and care plans and priorities including: | Jean/Joe |  |  |
| Children and Young People Strategy; |  |  |  |
| Community Care Plan; |  |  |  |
| Older People Strategy |  |  |  |
| Health Inequalities Strategy (if not in SP strategy) |  |  |
| Health and well being etc |  |  |  |
| LIFT/SHIFT (advice related); |  |  |  |
| Sure Start /Connexions (advice related) |  |  |  |

OBJECTIVE 4: INVESTING IN SALFORD’S HOUSING STOCK

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Council owned stock |  |  |  |
| Complete HRA Business Plan: | Graham Moody |  |  |
| Context; |  |  |  |
| Asset Appraisal and Management Plan; |  |  |  |
| Housing stock condition; |  |  |  |
| Non decency; |  |  |  |
| Resources needed; Energy efficiency; |  |  |  |
| Capital programme performance; |  |  |  |
| Financial Profiles etc; |  |  |  |
| Complete Financial Models | Graham Moody | September |  |
| Option Appraisal process and/update/options analysed and decisions taken |
| Expressions of interest | KS | September |  |
| Partnering arrangements and finalisation – complete Partnering Plan | KS | September |  |

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Identify investment needs in the private sector: - | EJW | September | ? £ ? |
| Context; |  |  |  |
| Housing Renewal Strategy |  |  |  |
| Stock condition |  |  |  |
| Non decency/unfitness |  |  |  |
| Anticipating HHSR |  |  |  |
| Energy Efficiency |  |  |  |
| Disability |  |  |  |
| Identify investment needs in the RSL sector: - | AH/GL | September | RSL/SCC |
| Business Plans |  |  |  |
| HMRF Impact |  |  |  |
| Asset Appraisal |  |  |  |

OBJECTIVE 5: SUSTAINING NEIGHBOURHOODS AND COMMUNITIES

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Ensure Housing Services is engaged in effective structures to ensure housing objectives and priorities are based on informed decision making and enable involvement of wider Council and community |  |  |  |
| Link to Living Environment (LSP Theme) developed – Salford Partnership | PH/Marie Lindars |  |  |
| Link to NDC Structure | GL/JC/NDC |  |  |
| Link to HMRF Structure | ?? |  |  |
| Link to Community Committees and Action Plan development |  |  |  |
| Develop Neighbourhood Management model - delivery Salford First IGP Bid | KS | October |  |
| Links to community safety/ASB/cross tenure ASB Initiative |  |  |  |
| Develop arts in regeneration initiative |  | March 2004 |  |
| Construction training/employment academy |  | HMRF - May 2004 |  |
| Community finance development and linkages |  | March 2004 |  |
| Continue to deliver & maintain Early Warning System | PH/Mhe |  |  |
| Education – links to primary school review, PFI developments, catchment area information |  |  |  |
| Environment |  |  |  |
| Community Cohesion | PL/Steve Thompson |  |  |

OBJECTIVE 6: RESOURCES

| TASK | LEAD/SUPPORT | MILESTONE | RESOURCES |
| --- | --- | --- | --- |
| Links to corporate Capital Strategy/Asset Strategy | KS/MB | September |  |
| Identify resource opportunities within all regeneration funding in City | GL/CM/KS | September |  |
| Housing Capital Programme (public/private) | GL/JW | September |  |
| ADP | AH/GL | September |  |
| Other resources e.g. Planning | GL | September |  |
| Review capital available to Council for housing – policy and practice e.g. RTB receipts and other capital receipts |  |  |  |