|  | ITEM NO. |
| --- | --- |

# REPORT OF THE HEAD OF HOUSING SERVICES

To the Lead Member for Housing Services

On:	Thursday 24th March 2005

TITLE: Re-Tender of Independent Tenant Advisor – Housing Options

## RECOMMENDATIONS:

## Lead Member is recommended to: -

- Consider the details of the ITA Project Cost variance February 2004 to January 2005 and approve the consequential overspend as outlined in the main report.

- Approve the interim arrangements for ITA support.

3.	Approve the re-tendering for the position of an ITA to -

- Support the development of locally-focussed solutions post May 2005 where transfer of Private Finance Initiative schemes are being developed

- Support the process of review of the Tenant Compact

- Explore the opportunities for an Independent Community Advisor role in supporting tenants and residents in regeneration areas to consider mid to longer-term impact of housing change.

EXECUTIVE SUMMARY:

Lead member will be aware that TPAS were appointed as Independent Tenant Advisor to the Housing Options Steering Group in February 2004.

This report outlines the need to re-tender the Independent Tenant Advisor role and seeks approval for TPAS to provide ITA support prior to a new appointment being made.

BACKGROUND DOCUMENTS:

TPAS Indicative Project Costs 11th August 2004

Salford ITA Project Cost Variance

Recommendations to HOSG – ITA Appointment

TPAS – ITA Projected Costs 3rd February 2005 – June 2005

ASSESSMENT OF RISK:

Low

THE SOURCE OF FUNDING IS:

Housing Options Budget – Housing Revenue Account Capital Programme

LEGAL ADVICE OBTAINED:

N/A

FINANCIAL ADVICE OBTAINED:

Report seen by Principal Group Accountant.

CONTACT OFFICER:

Pat Greenwood

Tel 0161-922-8779

e-mail – pat.greenwood@salford.gov.uk

WARD(S) TO WHICH REPORT RELATES:

ALL

KEY COUNCIL POLICIES:

Housing Strategy Statement 2004-2007

Stock Options Appraisal 2004 - 2005

LINKS TO PARTNERS IN SALFORD THEMES: Enhancing Life theme

LINKS TO CABINET PRIORITIES AND PLEDGES:

LINKS TO HOUSING STRATEGY PRIORITIES: Bringing all homes to Decent Standard. Provide a greater choice of homes in all our communities.

LINKS TO PERFORMANCE:  Securing Decent Homes will be a major performance issue for the City Council

EQUALITY IMPACT ASSESSMENT: No. Immediate implications. An Equality Impact Assessment is planned for the Stock Options consultation process. An Equality Impact Assessment will be undertaken as part of the review of the Tenant Compact.

### DETAILS OF REPORT

- Background

1.1 TPAS were appointed by the Housing Options Steering Group in February 2004 as Independent Tenant Advisor. They have worked with the HOSG since this time and their work has included –

- Providing guidance, training and advice throughout the Housing Options Review process

- Supporting and advising the HOSG

- Validating consultation material and methodology

- Providing their own newsletter

- Working with consultants on financial assessment

- Holding their own public meetings

- Communicating with Community Housing Task Force with and on behalf of the HOSG and

- Attending meetings and drop in sessions organised by the Housing Options Team.

1.2  In the original expression of interest, projected costs were in the region of £25,000 to £35,000.  In August 2004 Lead Member for Housing Services approved a revised programme of indicative costs to the value of £79,405.00.  The actual costs for the period February 2004 to January 2005 will be £85,412.99.

2.0   Details of Overspend

2.1 The Indicative Programme outlined detailed costs of £79, 405 (August 2004).  Some of the areas and amount of work detailed on this document are at variance to the projected costs. The actual cost up to the beginning of Phase 3 will be  £85, 412.99. This is an overspend of  £6007.99.

2.2  Although some areas of work detailed on the Indicative Costs have not been fully completed (such as the production of one Newsletter instead of two) the amount of extra work has meant a net increase in overall costs.

- Interim Arrangements for ITA

3.1   It is likely that a new lead ITA could not be in place until July 2005. In order to allow continuity, it is recommended that the existing ITA, TPAS maintain their role at this crucial stage.

3.2   Details of costs From 3rd February 2005 to June 2005 are estimated at £45, 977.50 - the contract will be closely monitored to ensure that only work up to an agreed amount is undertaken. TPAS will need to keep Housing Services informed as soon as possible if there will be any changes to the estimate given for this period.

4.0   Outline Programme for re-tendering lead ITA role

  - In the future, depending on the outcome of the process, any transfer, local housing company or Private Finance Initiative solutions would require an Independent Tenant Advisor. This could be one lead ITA or a consortium who would work closely with tenants to provide independent advice, validate and oversee the process. It is considered important that ITA support, including any training and advice, is available to tenants as early as possible in the process as possible.

4.2	From June 2005, The City Council is intending to review its Tenant Participation Compact in partnership with customers, New Prospect Housing Limited and other partners. It is considered beneficial to build in specialist Independent Tenant Advisor support to ensure transparency of process and ensure that customers can have a clear involvement and say on what a future Tenant Participation Compact will best serve the future needs.

  - An issue arising in the course of consultation in regeneration areas, has been the need at times for independent validation of what the Council and partners are saying to tenants and residents. It has been suggested that an Independent Community Advisor role might assist in supporting tenants where masterplanning or activity is taking place. At this stage, the role of an ITA would be to scope out how this Independent Community Advisor role might work in practice.

  - In the meantime, it is proposed to commence a re-tendering process for a lead ITA that would take on the above main roles

4.5 Set out below is an outline of the potential process and outline programme for re-tendering of the ITA role.

4.6 Good practice and the need to work in compliance with the Contractual Standing Orders of Salford City Council means that it is essential that a robust audit trail is established in connection to such appointments.

4.7 It is suggested that a minimum of three invitations to tender are invited by first advertising in an appropriate journal for an Independent Tenant Advisor. A selection panel would involve members of the Housing Options Steering Group and the Lead Member for Housing.

4.8  Prior to the appointment of an ITA, attached guidance notes will be closely referred to as part of the process.

  - Set out below is the indicative projected timescale.

-     Approval by Housing Options Steering Group – 9th February 2005

- Approval by Lead Member – 24th March 2005

- Advertising and expressions of interest – April/May

- Tender documents received – May

- Shortlisting and interviews – June

- Financial implications

5.1  The budget allocation for stock options in 2004/5 is £600,000.  This covers the costs of various consultants, agency staff and consultation events.  Based upon latest estimates, this budget is over-committed for 2004/5, excluding the additional costs of TPAS for the period February 2005 - March 2005.  A potential overspend against the budget provision has been flagged up in monthly HRA budgetary control reports to lead member.  The additional commitment for the work of TPAS in February 2005 – March 2005 will increase the risk of an overspend.

5.2 The budget allocation for stock options in 2005/6 is currently £500,000.  Currently, it is unclear what the level of commitment will be against this budget.  Initial views are that this budget will be under severe pressure, however, a consultant from Price Waterhouse Coopers (PWC) is to advise on the likely call on this budget.

5.3 The financial implications of the extension of the TPAS contract and the re-tendering of the lead ITA role must be fed into future discussions with PWC.  At the earliest opportunity, the overall commitments against the budget must be clarified.