| PART 1 | ITEM NO. |
| --- | --- |

REPORT OF THE STRATEGIC DIRECTOR HOUSING AND PLANNING

TO THE LEAD MEMBER FOR HOUSING

ON 29th March 2007

TITLE: Stock Options Delivery – External Support

RECOMMENDATIONS:	That the Lead Member notes the budget requirements and receives further reports throughout the year.

EXECUTIVE SUMMARY:	To support the effective implementation of the Stock Options Appraisal Investment Strategy and the HRA Business Plan 2005 – 2035, it has been viewed essential to procure a suite of external advisors to support the delivery process. This report forms part of the ongoing monitoring of the implementation process.

BACKGROUND DOCUMENTS:

- Lead Member for Housing Report 26th May 2005 – Consultancy Procurement for Stock Option Appraisal Implementation

- Report to the joint Lead Member for Housing and Customer and Support Services on 28th December 2005 and subsequent update reports - Stock Options Delivery – External Support

ASSESSMENT OF RISK:	The appointment of specialist support will help to ensure we are able to deliver long-term investment for the current local authority owned stock. However, failure to monitor expenditure and instigate appropriate actions based on findings could lead to a significant call upon the HRA balances, with these possibly going below the recommended level by the Audit Commission.

SOURCE OF FUNDING:	Housing Revenue Account 2006/07, 2007/08 & 08/09 – Stock Option Delivery Budget, Capital Programme and recovery of Transfer costs.

COMMENTS OF THE STRATEGIC DIRECTOR OF CUSTOMER AND SUPPORT SERVICES (or his representative):

- LEGAL IMPLICATIONS				N/A

- FINANCIAL IMPLICATIONS			Provided by: Nigel Dickens

There is current provision within the HRA through the utilisation of balances.  However, consideration of the potential impact to the current resources that have been set aside needs to be appraised in line with the Stock Option Project.

PROPERTY (if applicable): N/A

HUMAN RESOURCES (if applicable): N/A

Communication implications:

Internal Communications – N/A

External Communications – N/A

Marketing and Promotion – N/A

CONTACT OFFICER :	Simon Ashworth (0161 922 8793) simon.ashworth@salford.gov.uk

WARD(S) TO WHICH REPORT RELATE(S): ALL

KEY COUNCIL POLICIES: Housing, Planning and Regeneration

DETAILS (Continued Overleaf)

- Monitoring

- Appropriate systems have now been established to monitor expenditure in relation to Stock Options Delivery, between the Option Delivery Team and Finance.  Individual costs centre have been established for the following areas:

  - Housing Options Team

  - Change Management

  - Common Service Provider

  - Public Finance Initiative

  - Local Housing Company

  - Arms Length Management Organisation

  - Staffing

- A brief summary of the expected project costs at this point in time through to the establishment of the new organisations and PFI contract is outlined below.

- As announcements are made and timetables become firmer together with functions and tasks to be undertaken, then the figures quoted below can be refined.

| Budget Areas | Total Budget £ | £ 2006/07 | £ 2007/08 | £ 2008/09 | £ 2009/10 |
| --- | --- | --- | --- | --- | --- |
| Housing Option Team | 576,850 | 392,350 | 179,000 | 5,500 | 0 |
| Change Management | 293,100 | 177,100 | 116,000 | 0 | 0 |
| CSP | 502,150 | 104,150 | 398,000 | 0 | 0 |
| PFI | 2,468,325 | 557,325 | 1,566,000 | 225,000 | 120,000 |
| Transfer | 2,384,175 | 711,175 | 1,673,000 | 0 | 0 |
| ALMO | 1,256,000 | 501,600 | 754,400 | 0 | 0 |
| Staffing | 3,190,000 | 1,990,000 | 1,200,000 | 0 | 0 |
| Total | 10,670,600 | 4,433,700 | 5,886,400 | 230,500 | 120,000 |

- Outlined in the table below is a breakdown of headline expenditure for each budget area identified in the summary table above.  The information has been brought together following discussions with the various project leads and forecasts made in relation to the expected implementation timetable and contracts already approved.

|  | £ Total Budget | £ 2006/07 | £ Actual Spend 06/07 |
| --- | --- | --- | --- |
| Housing Options Team | 576,850 | 392,350 | 380,059 |
| Change Management | 293,100 | 177,100 | 139,006 |
| CSP | 507,150 | 104,150 | 92,743 |
| PFI | 2,473,325 | 557,325 | 487,884 |
| Transfer | 2,384,175 | 711,175 | 684,236 |
| ALMO | 1,246,000 | 501,600 | 453,283 |
| Staffing | 3,190,000 | 1,990,000 | 1,611,149 |
| Total | 10,670,600 | 4,433,700 | 3,848,361 |

- It should be noted that the Housings Options Team is already close to its budget provision for the financial year; this is the result of expenditure being charged to this cost centre, which should have been charged to other budget heads where the funds are available to cover the expenditure. An exercise to reallocate the incorrectly coded expenditure will be undertaken during the next reporting period.

###### Strategy for Funding Implementation Costs

- As indicated above the possible lifetime project costs identified are £10,670,600 and these will need careful monitoring.

- It must be remembered that these costs cover the current financial year 2006/07 for all the above functions, 2007/08 for transfer, PFI and staffing implementation costs and 2008/09 for PFI.

- The table below indicates a possible course of action for funding the costs:

|  | £ |
| --- | --- |
| Indicative Costs | 10,670,600 |
| Less Possible Transfer Set up Costs Recovery | 1,000,000 |
| Less Possible Capitalisation of Stock Condition Surveys | 1,000,000 |
| Requirement from HRA Resources | 8,670,600 |
| Provision in 2006/07 HRA Budget | 2,500,000 |
| Provision in 2007/08 HRA Budget | 2,650,000 |
| Provision in 2008/09 HRA Budget | 350,000 |
| Requirement from HRA Balances | 3,170,600 |

- The current level of HRA balances is £3.8m and if the above scenario arose then this would leave balances at £0.6m during 2008/09. An exercise is currently underway to review the future anticipated costs and work required, this could mean that some will reduce given the launch dates of the new organisations.

- When this level is compared to the Audit Commission recommended level of 3%, which in 2006/07 would be £2.7m based on the current structure of the HRA. However, after transfer the size of the HRA would be substantially reduced and based on the thirty year HRA Business Plan a 3% level of balances would be approximately £1.3m by 2008/09.

- If the funding requirement for the implementation of the Stock Options process reached the predicted £10.67m then HRA balances would be below the level recommended by the Audit Commission.

3. 	Recommendations

3.1 	That the Lead Member notes the budget requirements and receives further reports 	throughout the year.