| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- |

REPORT OF

THE HEAD OF HOUSING SERVICES

TO HOUSING LEAD MEMBER on 30th JUNE 2005

TITLE: PUBLIC SECTOR CAPITAL PROGRAMME 2004/05 OUTTURN and 2005/06 LATEST POSITION

RECOMMENDATIONS:

- That Lead Member notes the final outturn of the programme for 2004/05 and the current position for 2005/06 and receives further monthly reports throughout the year.

EXECUTIVE SUMMARY:

This report gives the details of the final position for the 2004/05 Public Sector Capital Programme and the current one for 2005/06.

BACKGROUND DOCUMENTS:

(Available for public inspection)

Approved capital programme 2004/05 and 2005/06

NPHL Monitoring Data

Financial Information from SAP

ASSESSMENT OF RISK:

Failure to monitor the programme could result in significant overspends or under utilisation of resources, this will have an impact upon decent homes standards.

THE SOURCE OF FUNDING IS:

Not applicable as the report is commenting on the financial position.

LEGAL ADVICE OBTAINED:

Not required for this report.

FINANCIAL ADVICE OBTAINED:

Report prepared by the out stationed Principal Group Accountant for Chief Executive’s.

CONTACT OFFICER:

Nigel Dickens 0161 793 2585

WARD(S) TO WHICH REPORT RELATE(S):

All

KEY COUNCIL POLICIES:

COUNCIL CAPITAL BUDGET 2004/05 and 2005/06

DETAILS (Continued Overleaf)

- Background Information

  - The Council has approved a Public Sector Capital Programme of £21.8m for 2004/05 and £19m for 2005/06 and it is the responsibility of NPHL to manage and monitor this on behalf of the Council.

  - During the last year officers from both NPHL and the Council have been working together to develop a more robust system for the monitoring of schemes and the programme and this is reflected in the final position for 2004/05.

  - This was to avoid the year end position for 2003/04 where the programme had underspent by £2.7m as has been previously reported to Lead Member, it will be recalled that these resources have been carried forward.

  - These arrangements have been submitted to previous Lead Member meetings where presentations have been made by colleagues from NPHL and it has been accepted that there are good systems in place to monitor the programme.

- Details of Report

  - Final Position for 2004/05

    - The original approved resources by the Council for 2004/05 Public Sector Capital Programme were £21.8m, this reduced to £21.4m due to the rephrasing of a grant funded scheme.

    - The final outturn was expenditure of £21.7m which is a minimal overspend of £0.3m or 1.4% of the programme.

    - It is of credit to all involved that the final position was so close to the available resources and demonstrates that the level of over-programming adopted during the year was correct and that the monitoring procedures work.

    - It is expected that this slight overspend will be carried forward and the treatment of this will be dealt with in the report on the Private Sector Capital Porgramme.

  - Actual Position as at 31st March 2005

    - There are a total of 68 elemental scheme surveys, which have been undertaken since the beginning of May 2004. Each of the 68 scheme surveys has now been completed. The surveyors within NPHL have carried out the elemental scheme surveys. Any properties subject to either tenant refusal or no response are being visited further by the customer liaison officers of both NPHL and the partners.

    - There are 67 partnering schemes now on site (99% of the decent homes programme), with the remaining 1 scheme (1%), scheduled to start on the programme in September / October 2005.

    - The four partners were undertaking work in their respective geographical areas as follows:

Wates (Eccles), (Worsley & Little Hulton):

- Lancaster Rd, Full Central Heating

- Newlands, Bathrooms/Full Rewires/Kitchens

### Liverpool Rd, Kitchens/Electrical Upgrades

- Higson Ave & Peel Green Rd - Kitchens/Bathrooms/Rewires

- Astley Rd, Kitchens/ Electrical Upgrades

- The Avenues, Roofing/Repointing/Cavity wall ties

- Peel Green Phase 1, Repointing/Cavity wall ties

- De Traffords/Moorfield, Bathrooms

- Mees Square, Bathrooms

- Albert St, Kitchens/Bathrooms/Electrical Upgrades

- Worsley Rd. North, Roofing/Bathrooms/Rewires

- Bridgewater Rd, Bathrooms

- 53 – 67 Manchester Rd, Kitchens

- Mitchell St., Kitchens

Bramalls (Salford South):

- Moss Meadow, Bathrooms/Electrical upgrades

- Southgarth, Bathrooms/Full Rewires

- Tootal, Heating/Electrical upgrades/Kitchens

- Light Oaks Rd, Electrical upgrades

- Duchy, Electrical upgrades

- Edgehill Rd, Full Rewires/Repointing/Roofing/Cavity wall ties

- Devon Close, Kitchens

- Cressington Close, Kitchens

Whites (Swinton):

- The Valley Estate, Prior to Paint and Full Central Heating

- Worsley Rd, Kitchens/Partial rewires

- Manchester Road South, Partial Rewires/Kitchens

- Parkfield & Moorfield, Bathrooms

- Agecroft, Kitchens/Electrical Upgrades

- Mossfield, Electrical Upgrades

NPHL Maintenance Division (Swinton, Salford North, Eccles):

- Beehive Estate, Prior to Paint

- Albion Stadium, Prior to Paint

- Canterbury Gardens, Prior to Paint

- Lower Broughton 4, Electrical Upgrades

- North Clifden Lane, Kitchens/Electrical Upgrades

- Floral Court, Bathrooms/Full Rewires

- Kersall Cell, Heating/Electrical Upgrades

Pre-Partner Contractors (Swinton, Worsley, Eccles):

- Wardley Est., Partial Rewires

- Temple Drive, Electrical Upgrades

- Dudley Rd. & Cumberland Dr., Heating

- The Meadows, Heating

- Baines Ave, Roofing

- Crossfields, Roofing

- 1 – 5A Warren St., Roofing

    - Out of the 67 schemes on site, 63 schemes (94% of the total schemes) have to date been completed, obviously some of these works have now been completed in 2005/06. The remaining schemes range from 50% to 96% complete. The completed schemes are as follows:

- Moss Meadow, Electrical upgrades (21 Properties)/ Bathrooms (1 Property) - Bramall

- Light Oaks Rd, Electrical upgrades (6 Properties)  - Bramall

- Edgehill Rd, Rewires/Roofing/Repointing & Cavity Ties (16 Properties) – Bramall

- Southgarth, Bathrooms (70 Properties) / Rewires (77 Properties) – Bramall

- Duchy, Electrical Upgrades (261 Properties) - Bramall

- Tootal, Electrical Upgrades (199 Properties), Kitchens (119 Properties), Heating (207 Properties) - Bramall

- Devon Close, Kitchens (5 Properties) - Bramall

- Cressington Close, Kitchens (13 Properties) - Bramall

- Mitchell St, Kitchens (22 Properties) – Wates

- 53-67 Manchester Rd, Kitchens (5 Properties) – Wates

- De Traffords, Moorfield, Bathrooms (20 Properties) – Wates

- Newlands,  Bathrooms (74 Properties)/ Rewires (92 Properties)/ Kitchens (17 Properties) – Wates

- Lancaster Rd, Heating (145 Properties) – Wates

- Albert St, Kitchens (35 Properties), Bathrooms (38 Propties), Electrical Upgrades (18 Properties)– Wates

- Peel Green Ph1, Cavity Ties (154 Properties) - Wates

- The Avenues, Roofing/Repointing/Cavity wall ties (50 Properties) – Wates

- Liverpool Rd, Kitchens (10 Properties)/Rewires (14 Properties) – Wates

- Astley Rd, Kitchens (37 Properties) – Wates

- Worsley Road North, Rewires (30 Properties), roofing (60 Properties), Bathrooms (47 Properties) – Wates

- Higson Ave/Peel Green Road, Kitchens (8 Properties)/Rewires (39 Properties), Bathrooms (3Properties)  - Wates

- Mees Square, Bathrooms (32 Properties) - Wates

- Bridgewater Road, Bathrooms (41 Properties) - Wates

- Worsley Rd, Kitchens (105 Properties), Rewires (110 Properties) – Whites

- Agecroft, Kitchens/ Electrical Upgrades (23 Properties) – Whites

- Parkfield/Moorfield, Bathrooms (86 Properties) - Whites

- The Beehive, Prior to Paint – (245 Properties) NPHL DLO

- Kersall Cell, Heating (44 Properties), Electrical Upgrade (48 Properties) – NPHL DLO

- Lower Broughton, Electrical Upgrades (108 Properties) – NPHL DLO

- Albion Stadium, Prior to Paint (117 Properties) – NPHL DLO

- Canterbury Gardens, Prior to Paint (123 Properties) – NPHL DLO

- Floral Court, Rewires (79 Properties), Bathrooms (61 Properties) – NPHL DLO

- North Clifden Lane, Kitchens (51 Properties), Electrical Upgrades (76 Properties) – NPHL DLO

- Wardley, Partial Rewires (28 Properties) – Pre-Partner Contractor

- Temple Drive, Electrical Upgrades (68 Properties) – Pre-Partner Contractor

- The Meadows, Heating (51 Properties) – Pre-Partner Contractor

- Dudley Rd. & Cumberland Ave. (64 Properties) – Pre-Partner Contractor

- Baines Ave, Roofing (22 Properties) – Pre-Partner Contractor

- Warren Street, Roofing (12 Properties) – Pre-Partner  proe

- Crossfields, Roofing (35 Properties) – Pre-Partner Contractor

    - For the schemes listed above as they have now been completed and reported for 2004/05 they will not feature in future reports as these will focus on progress for the 2005/06 programme.

  - Initial Level of Over-Programming for 2005/06

    - The original approved resources for the 2005/06 Public Sector Capital Programme are £19m. It will be seen from the report on the Private Sector Capital Programme that it is recommended that these are not altered as a result of the final position for 2004/05.

    - This has now been revised to £19.9m due to the extra care scheme that has been funded by the Department of Health.

    - Schemes and programmes have been developed at £21.9m giving an over-programming level of £2m. Whilst this is a lower level than that adopted during 2004/05 it is considered sufficient given the way working relationships with Partners have been developed and the ability to bring schemes forward if required.

  - Actual Position as at 31st May 2005

    - There are a total of 49 elemental schemes surveys to be undertaken for the 2005/06 Programme.

    - There are 31 scheme surveys currently being undertaken of which 11 have been completed.

    - There are 17 partnering schemes now on site (35% of the decent homes programme), with the remaining 32 scheduled to start throughout the remainder of the year. As this report has given details of the schemes for 2004/05 then fuller details for 2005/06 projects will be given in next month’s report.

    - Of the schemes currently on site 1 has already been completed with the remainder ranging from 0% to 83% complete. The one completed scheme by Bramall is an Electrical Upgrade to 33 Properties on Park Road.

    - As at 31st May 2005 the actual expenditure incurred was £1.2m or 6% of the available resources and there are further certified payments in the process of being paid that will increase this to £2.4m or 12%.

- Conclusions

  - NPHL have developed a good system for monitoring the projects from both an operational and financial perspective and the information produced is a good management tool as demonstrated in the final outturn for 2004/05.

  - The programme for 2005/06 will fully utilise the budget due to the level of over-programming adopted and this will require monitoring and managing during the course of the year.

- Recommendation

  - That Lead Member notes the final outturn of the programme for 2004/05 and the current position for 2005/06 and receives further monthly reports throughout the year.