# Area for Improvement:	Home Care Services

| Measurable Improvement Targets | Baseline | 2002/03 | 2003/04 | 2004/05 | 2005/06 | 2006/07 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 1 April 2000 Commissioning. Proportion of market Share: In-house 51% External 49% Market capacity problems within Domiciliary care provision in the Irlam/Cadishead and Broughton areas. In-house Provider. Quality of Service (No systematic approach to recording this information until April 2002) Service Users to receive annual Quality Review | Projection of Proportion of market Share: In-house 38% External 62% To ensure an adequate supply of Domiciliary Care provision to meet identified needs. 90% | In-house 30% External 70% 100% | In-house 30% External 70% 100% | In-house 30% External 70% 100% | In-house 30% External 70% 100% |
| Measurable Improvement Targets | Service users to receive specified information on Service Service users satisfied with care received New homecare packages to receive risk assessment prior to service commencing 1st April 2000 Implement National Minimum Standards. 38% % of staff to hold NVQ Level 11 or equivalent as a minimum: 0.5% b) Cost and Efficiency Reduction of non-productive time: (no systematic approach to recording this information at 1/4/00) Total = 32% | 95% 80% 75% 60% 5% 29% | 100% 85% 85% 80% 16% 28% | 100% 90% 90% 95% 27% 26% | 100% 95% 95% 96% 38% 25.8% | 100% 98% 99% Dependent upon meeting NVQ standards 50% 25.7% |

| Actions to Achieve the Targets | Commencing | Reason for Improvement | Responsible Officer | Resources |
| --- | --- | --- | --- | --- |
| Achievements (action already undertaken) | Commissioning. During 2000/2001 a major programme of out-sourcing service provision was undertaken, in particular provision of shopping and cleaning service were transferred to external providers. Resulting in a change in the proportion of market share at 1 April 2001 to: In-house 42% External 58% Proposed development of block contract for Irlam and Broughton area Consultations with domiciliary providers have taken place. This has resulted in a re-alignment of services to adequately meet local identified needs. Capacity concerns resolved through localised recruitment within the independent domiciliary care sector | April 2000 and ended in July 2000 Nov 01 | The provision of domestic care services via in-house services was very expensive. Placing this contract with the independent sector enabled a reduction in unit cost and enabled a higher rate of payment by the service users To ensure an adequate supply of domiciliary care provision to meet locally identified needs. | J Clark/ E Murphy G.Currie. | Staff time for assessment of individual care packages. Contract Team time for tendering process. Home care staff time working with new providers to manage the transfer. Contract Team time to monitor transfer arrangements and implementation of new service. Staff input from Contracts and Review Unit. |
| Achievements (action already undertaken) | 2. In-house Provider. Quality of Service. The implementation of Caretime, the home care module of Carefirst, the Authority’s new Service User information system. Re-structure of Service and reallocation of managerial and supervisory responsibilities Implementation of regular Supervision on an individual and group basis for all staff Initial review completed of current performance against the draft National minimum Standards. | May 2001 October 2001 October 2001 January 2002 | To improve information and planning systems to enable a more efficient use of resources. To enable tasks to be carried out at appropriate levels and enhanced business management capacity. To meet the requirements of the Best Value principles and a key quality control mechanism To implement improvements to the delivery of the Service. | Janet Senior Sheila Woodtownend Janet Senior Janet Senior Janet Senior | Staff time for training, updating information transfer from previous system. Additional IT equipment. Staff time to plan and implement changes. Personnel issues. Staff time. Staff time to review, plan and implement procedures. |
| Achievements (action already undertaken) | The adoption of local P.I.s developed in conjunction with the District Auditor (Agma Benchmarking Group) Cost and Efficiency. Outsourcing of some service provision in 2000/01 to downsize the Service. This resulted in the need to re-align staff groups to reduce travel time and wasted time elements of non-productive time. Electronic systems set up to record non-productive time on an area basis for comparison with set targets. The implementation of the Attendance Management Policy. This has already resulted in a reduction in short term sickness levels | April 2002 July 2000 April 2000 July 2001 | To compare performance and processes with other Local Authorities to improve service delivery. To meet efficiency savings and concentrate in-house resources on the more vulnerable in line with a higher unit cost. To provide more accurate management information in a cost effective manner Citywide. To deliver a consistent approach to monitoring and reducing sickness levels. | Janet Senior Rob Blackstone Janet Senior Janet Senior | Staff time Staff time for managing the project. Personnel issues. Staff time from Home Care and Finance. Software for PC’s Staff time. |
| Achievements (action already undertaken) | Review and reallocation of managerial and supervisory responsibilities Systems set up to discuss all non-productive time with staff during group and individual supervision sessions. This has resulted in reduction of non-productive time to 29.4% at 1st April 2002. | October 2001 January 2002 | Roles and responsibilities clarified and identified tasks are completed at appropriate levels. To raise staff awareness of unit cost and their role within it. To reduce non-productive time and remain competitive | Janet Senior Janet Senior | Staff Time Staff Time |
| Short-term Short-term | 1. Commissioning. To hold a workshop between commissioners/purchasers and internal home care providers to establish what areas of the service work well, where there are potential weaknesses, to review the commissioning arrangements with Salford Home Care. To review current commissioning and consider alternative contracting approaches for domiciliary care provision within the independent sector. This to actively involve independent sector providers and be part of the ongoing review of commissioning arrangements – initially by sending out a questionnaire to all providers about current arrangements and how these can be improved. Then to call a small focus group to take issues forward. | May 2002 July 2002 | Home care service need a clear focus for service development. Currently there are mixed messages about their long-term future. To review contracting arrangements to develop commissioning to more effectively manage the social care market. Current spot purchase arrangements do not guarantee work to providers but does enable freedom of choice and a range of providers. 33 currently registered – hard to monitor but transfer to block contracts would reduce the number of providers and mean changes for services users. | J Clark/ E Murphy J Clark/ G Currie | Manager’s time. Staff time to facilitate the workshop. Staff time to gather information on current patterns of use. Contracts Team time for consultation. Staff time to gather information on current patterns of use. Staff time for benchmarking and comparison. |
| Short-term | 2. In-house Provider Quality of Service To set up systems to ensure Initial Visits, Quality Reviews and Risk Assessments are completed within agreed timescales and recorded on Caretime To establish reporting system from Caretime to regularly monitor performance To set up systems to collate information for local P.Is. To implement remaining and additional functions of Caretime To examine alternative methods to achieve NVQ target. | April 2002 June 2002 July 2002 July 2002 October 2002 | To improve the monitoring of service delivery and minimise accidents. To deliver improved management and performance information To measure performance against other Local Authorities. To further improve information and planning systems for quality assurance and best use of resources. To achieve National Minimum Standards and improve quality of service delivery | Janet Senior Janet Senior Janet Senior Janet Senior Sheila Woodtownend Janet Senior Sheila Dawson | Staff time. Staff time. Staff time. I.T. equipment. Staff time. Staff time.for training and implementation |
| Short-term | Cost and Efficiency To produce monthly area summary sheets detailing levels of non-productive time for comparison with set targets. Workshop to be held to formulate commissioning strategy for in-house Home Care Service. To start to plan and develop in –house Service to meet the strategy. | May 2002 May 2002 | To give Managers accurate and timely information to manage and reduce non-productive time. To focus Service to enable effective workforce planning. To reduce wasted time and to assist with the development of the training pathway for Home Care Assistants | Janet Senior Julia Clark Eve Murphy | Staff time. I.T. equipment. Finance assistance. Staff time. Workshop facilitation |
| Medium-term Medium-term | 1. Commissioning. None 2. In-house Provider. Quality of Service To review all management information systems. Establish assessment resources for NVQ Further review of performance against National Care Standards. To review and develop benchmarking information. Cost and Efficiency Examine alternative methods to achieve NVQ targets To systematically use the information provided as a working tool to effectively manage and reduce non-productive time in line with targets set. To provide a Service as defined by the Commissioning Strategy. Establish assessment resources for NVQ and develop Training Pathway for all staff. | April 2003 April 2003 June 2003 July 2003 October 2002 April 2003 April 2003 April 2003 | To check if systems are providing correct and relevant data to inform and improve service To move towards a qualified workforce To progress towards implementing all Standards Improve performance in comparison to other Local Authorities. To develop consultation process with service users and staff. To plan to achieve National Minimum Standards Reduction of unit cost and remain competitive. In-house Service is focused on areas that will attract a higher unit cost. To move towards a qualified workforce and meet training targets. | Janet Senior Sheila Woodtownend Janet Senior Janet Senior Janet Senior Sheila Woodtownend Janet Senior Sheila Dawson Janet Senior Janet Senior Sheila Woodtownend Janet Senior | Staff time Staff time Staff time Staff time. Staff time Staff time Staff time Staff time |
| Long-term | Commissioning. Future actions will be dependent on decisions made within the ongoing review of commissioning arrangements for home care. Enter into new contracting arrangements. In-house Provider. Quality of Service. To continually monitor and evaluate the service delivery and ensure that standards for the service are met. To continually monitor, evaluate and plan to ensure non-productive targets are met. | 2003 April 2004 April 2004 | To ensure an adequate supply of domiciliary care provision to meet locally identified needs. To ensure equality of service delivery and performance measured against the Care standards. To achieve reduced unit cost for the Service. | J Clark/ E Murphy Janet Senior Janet Senior | Contracts time to formulate alternative methods – cannot be achieved within existing resources. Staff time. Staff time. |