# Area for Improvement:	Sheltered Housing - Develop More Flexible Services And Increased Choice For Service Users

| Measurable Improvement Targets | Baseline | 2002/03 | 2003/04 | 2004/05 | 2005/06 | 2006/07 |
| --- | --- | --- | --- | --- | --- | --- |
|  | One level / type of service available Intercom checks only available 5 days Few Service Standards or Performance Indicators to measure performance of service Good information on sheltered housing across providers Limited information on warden service for customers/ potential customers Customer involvement/ consultation adhoc with no specific strategy for elderly services to consult | Pilot flexible area team structure and intensive, customised warden service Draft service standards /performance indicators in place to measure performance of redesigned service Improve warden call technology at 5 sites across the City | Range of service options available inc 7 day intercom checks and customised, intensive warden service Service users have clear information about the service offered. This to be available in a range of languages/ formats on demand and in diverse / accessible settings Support plans in place for all tenants and reviewed at least annually / as required | Service accredited to Centre of Sheltered Housing studies Code of Practice Develop joint providers forum to share good practice and resources e.g relief staff | Allocations to sheltered schemes promote use as community care resource | All sheltered sites have updated warden call technology Smart home technology has been introduced at selected sites |
| Measurable Improvement Targets | Joint Forum set up of all providers of sheltered housing in Salford established - successful marketing events organised/joint brochure produced |  | Performance monitored and reported on regularly through new area team structure. Strategy in place to consult service users / stakeholders on regular basis. There is a strategy in place to maximise the use of sheltered housing stock across providers |  |  |  |

| Actions to Achieve the Targets | Commencing | Reason for Improvement | Responsible Officer | Resources |
| --- | --- | --- | --- | --- |
| Achievements (action already undertaken) | Tenants consulted via questionnaire Staff consulted on draft proposals Feasibility study undertaken in conjunction with management services Draft plan completed and submitted to DMT for consideration | All completed |  | K.Micklewright |  |
| Short-term | Finalise details of redesigned warden service Draw up detailed financial / staffing plan Finalise service options/ charges Draw up draft service standards for redesigned service Establish scope / charges for intensive warden services (in conjunction with Social Services) Consult staff/ service users / Social Services/PCT on redesigned warden service / proposed service standards | March 02 May 02 June – Aug 02 | With view to introducing more flexible service, taking views of staff tenants into account | K Micklewright K Micklewright/ Warden Services Managers | Staff time within Elderly Services / accountancy 2.5 days for staff meetings/ focus groups 14/15 days for scheme meetings Further discussion with Social Services on appropriate forums / mechanisms |
| Medium-term Medium-term Medium-term | Upgrade warden call equipment at 5 schemes across the City Pilot new area team structure for warden services and intensive warden service With view to introducing City wide from April 2003 Establish sheltered housing forum to ensure service user involvement and develop consultation strategy for new service e.g scheme meetings, newsletters etc. to ensure ongoing service user involvement Establish staff working group to review procedures / manuals (ongoing) to review training needs to finalise service standards to produce service welcome pack / information for tenants including information on service standards Agree support plans with all sheltered housing tenants Agree performance monitoring strategy to monitor agreed service standards Draft plans to utilise any vacated warden properties and present to DMT / Lead Member. Investigate potential for handyperson service / management arrangements within this context Introduce redesigned warden service City wide together with agreed service standards / performance monitoring strategy Development of joint providers forum to share good practice and resources e.g relief staff | April 02 – 03 During 2002/3 in line with financial plan Sept 02 Sept 02 To complete objectives by end March 03 Nov 02 Nov 02 Nov 02 April 03 April 03 | To improve warden call technology and services to tenants To promote greater choice and more flexible service Promote customer involvement To promote clear procedures/service standards for staff ; promote training opportunities;to improve information for service users To promote choice To ensure agreed service standards are effectively monitored and achieved To promote best use of resources in line with community care /PCT objectives To promote flexibility and improved service to better meet diverse needs together with evidence of improved service to service users and other stakeholders To maximise resources / develop best practice | K Micklewright M Reid (Electrical Surveyor) K Micklewright K Micklewright /Warden Services Managers K. Micklewright/ Warden Services Managers Warden Services Managers K. Micklewright K. Micklewright K. Micklewright K. Micklewright K. Micklewright/ Warden Services Manager | Maintenance budgets (agreed) See staffing / financial plan Staff time to resource 2 monthly meetings Management /warden staff time for regular monthly meetings Resources to update manual Management time for audit Training resources ( to be costed) Time of managers/ staff working group Design / print costs for welcome pack Warden staff time 1 hr / tenant / annum Management time to investigate opportunities and write report ( 1 week) Link handyman scheme with proposals for Home Improvement Agency Refer to detailed financial / staffing plan for resource information Managers/ staff time to monitor standards and report on ( ongoing) Examine potential for using existing resources more cost effectively |
| Long-term | Investigate sources of funding for IT equipment at sheltered schemes Develop strategy to promote best use of sheltered housing stock across providers Complete full procedural review to achieve accreditation to Centre of Sheltered Housing Code of Practice by end 2004 Complete rolling programme to improve warden call equipment at schemes with introduction of smart homes technology at selected sites to enhance upgraded warden call systems Review allocations procedures / processes for sheltered housing to promote use as community care resource (in consultation with Social Services) | Timescales to be linked with Supporting People charging policy and Single Assessment Process | In line with national /local priorities e.g. e. government, intranet. To improve communication with dispersed staff Promote opportunities for tenants To promote best use of sheltered housing as community care resource To provide evidence of improved service To improve warden call technology and consequently services To promote best use of sheltered housing resources | K. Micklewright /Warden Services Managers Supporting People Team K. Micklewright M Reid K Micklewright K Micklewright Social Services | To investigate potential for lottery/European funding £700 for accreditation to Code of Practice £100 pa to maintain First year resources agreed – to bid for resources for subsequent years. To bid for PCT resources for smart homes technology Management time to develop procedure/ process |