# Area for Improvement:	CARE ON CALL

| Measurable Improvement Targets | Baseline | 2002/03 | 2003/04 | 2004/05 | 2005/06 | 2006/07 |
| --- | --- | --- | --- | --- | --- | --- |
|  | 3000 users connected to service ( Aug 2000) 24 hour Control Centre but operates across split site Staff work call out from home with limited capacity out of hours Few Performance Indicators in place to measure performance of service ( as at 2000) Limited information for customers on service ( leaflet only as at 2000) | 4000 users connected by end March 2003 Expansion of staffing to address capacity issues out of hours Pilot flexible area team structure Performance Indicators in place to measure performance of Control Centre service, with effective management/ monitoring systems | Ongoing expansion of service. Target: 300+ ( net) increase per annum 24 hour Control Centre operating from single site Staffing and service capacity out of hours increased Service has diversified role i.e. crime prevention e.g. lone worker monitoring /domestic violence and call handling for Health and Social Services projects e.g.Rapid Response, no replies | Ongoing expansion of service. Target: 300+ ( net) increase per annum | Ongoing expansion of service. Target: 300+ ( net) increase per annum | Ongoing expansion of service. Target: 300+ ( net) increase per annum |
| Measurable Improvement Targets |  | Service users have clear information about the service offered. This to be available in a range of languages / formats on demand Customer forum established for consultation | Service accredited to Association of Social Alarm Providers Code of Practice ( end 2003) |  |  |  |

| Actions to Achieve the Targets | Commencing | Reason for Improvement | Responsible Officer | Resources |
| --- | --- | --- | --- | --- |
| Achievements (action already undertaken) | 24 hour monitoring and emergency response service launched Sept 2000 Marketing undertaken to expand service by over 700 users ( net) 3 Housing Association contracts successfully negotiated ( Henshaw’s, Booths and Sp@ce) Control Centre refurbished to meet Association of Social Alarm providers standards Pilot project set up with Hope A&E – rapid access to community alarms Expansion of project supporting EPICS and trial alarm installed at the Limes Staff procedure manual produced 2001 Customer welcome pack developed 2001 Customer survey undertaken 2001 Annual Report produced 2001 Care on Call calendar produced to feedback survey results 2001/2 Performance Indicators developed to measure performance of service (piloting 2001/2) | All completed | Improvements as proposed in 3 year Business Plan | K.Micklewright | Already agreed |
| Short-term Short-term | Expand staffing in line with financial plan to introduce waking night shift Consult staff /service users/ Social Services/PCT on redesigned warden service / proposed service standards Review marketing plan / opportunities for 2002/3 Review services/charges with housing association customers. Conduct satisfaction survey Audit service against ASAP standards to identify areas for improvement Review draft service standards and performance indicators, monitoring and reporting mechanisms in accordance with ASAP standards, Supporting People quality measures. | Feb 02 ( target date end June 02) May 02 (complete by end Aug 02) June 02 June 02 July 02 | With view to introducing improved Control Centre Service and quicker response to calls out of hours To enable expansion of service in line with Business Plan targets To evaluate satisfaction with current services / potential for development Evidence of service performance and improvement | K Micklewright/ (Care on Call Manager) K Micklewright (Care on Call Manager) K Micklewright (Care on Call Manager) K Micklewright (Care on Call Manager) K Micklewright (Care on Call Manager) K Micklewright (Care on Call Manager) | Staff time within Elderly Services / accountancy 2.5 days for staff meetings/ focus groups 14 days for scheme meetings Time for meetings with Social Services / Health See Business Plan Management time to review current performance monitoring arrangements |
| Medium-term Medium-term | Increase Care on Call staffing and pilot new area team structure for warden services with view to introducing City-wide with effect from April 2003 Pilot annual visits for all customers to update Control Centre records and monitor satisfaction with service with view to introducing City-wide with effect from April 2003 Establish customer forum to involve service users/ staff in implementation of review proposals Establish staff working group to review procedures / manuals (ongoing) to review staff training needs to review welcome pack Review opportunities for Care on Call to diversify call handling role in line with Business Plan proposals: Continue to participate in PCT /Social Services initiatives relating to development of 24 hour services Aim to develop action against Crime project to target problems associated with harassment, domestic violence etc. Aim to develop lone worker monitoring service for council /private sector employees provided demand/ cost effective Once new service model established, develop joint providers forum to share good practice and resources e.g relief staff. Proactively promote Care on Call as 24 hour monitoring and staffed response service across tenures | During 2002/3 in line with financial plan Pilot 2002/3. Implement wef April 03 Sept 02 (ongoing) Sept 02 (complete by end March 03) Ongoing since Sept 00 Ongoing Nov 02 Nov 02 With view to implementing projects during 2003/4 April 03 | To promote flexibility and improved service to better meet diverse needs To meet ASAP standards and improve accuracy of information held Promote customer involvement To promote clear procedures/service standards for staff; improve training opportunities To update information for service users To achieve diversification of service in line with Business Plan objectives To maximise resources and develop good practice | K Micklewright Care on Call Manager / Supervisor K Micklewright Care on Call Manager/Warden Services Managers K Micklewright Care on Call Manager/Supervisor K Micklewright Care on Call Manager | Refer to detailed financial / staffing plan for resource information Pilot to assess impact on staffing resources Staff time to resource 2 monthly meetings Management /warden staff time for regular meetings Resources to update manual Training resources ( to be costed) Management time Warden Services Managers / Staff working group time To be costed in line with requirements of individual projects and incorporated into charges Management time to research opportunities, meet with potential partners, write report(s) as necessary With view to maximising resources across providers Management time to resource two monthly meetings |
| Long-term | Implementation of Action against Crime project /lone worker monitoring project Achieve accreditation to Association of Social Alarm Providers Code of Practice | 2003/04 Target for accreditation 31st Dec 2003 | In conjunction with other agencies in line with local objectives | K Micklewright/ Care on Call Manager K Micklewright/ Care on Call Manager | To be costed in line with requirements of individual projects and incorporated into charges ASAP membership subscription £600 p.a ( costed into Business Plan). Cost of formal assessment |

AB/PB

23 April 2002