Minutes of meeting Tuesday 26 September 2006

# Irlam Council Offices, Astley Road, Irlam

Present:	Ursula Sossalla-Iredale (Chair)		- Neighbourhood Manager

Chris Trueblood				- Community Development

Holly Preston				- Ranger

Steve Taylor				- Environmental Services

Tom Broad				- Prince’s Park Garden Centre

Lynn Brown				- Salford Youth Service

Anthony Lord				- Salford Youth Service

Tina Antal				- Chief Exec’s Office

Sue Ness (Minutes)			- Administration I&C

Apologies:	Cllr Joe Kean / Steve Jones / Helen Ball / Ann Cavanagh / George Gilbody /

Reita Sheehy

|  | Action |
| --- | --- |
| INTRODUCTIONS Ursula welcomed Lynn Brown and Anthony Lord to the meeting. They have replaced Abby Prince and Steve Dyson |  |
| MINUTES OF LAST MEETING (27.6.06) / MATTERS ARISING Matters arising: Page 1 : Tennis Courts – Junior Football team have been using courts for practise on a trial basis and was being monitored. Update needed from George Gilbody of present situation. Meeting suggested between Irlam Pool, PPGC and Holly to confirm the times of who is responsible for the opening and closing of the courts. Times to be displayed on the board Page 4 : Skips – Ursula informed the group that she is not now responsible for the booking of skips. Going back to the previous system DVD;s – copies available of the ICY DVD. It was suggested the showing of the DVD’s at the next meeting which could be at The Edge Minutes accepted as a true record. | George Gilbody / Steve Taylor Colette Urmston / Tom Broad / Holly Preston |
| PRINCE’S PARK – ongoing work updates General Maintenance – Steve Taylor Containers – there are 5 containers in the park. Meeting with Irlam Rangers taken place regarding encouragement to the re-location of their 2 containers to near PPGC. Irlam Rangers expressed concerns about transporting the generator and nets. Tom Broad suggested their team could make a trolley to transport the generators in safety. There is also concern of health and safety issues that flammable materials, i.e. petrol, is being stored in one of the containers, so should be moved away from the other containers. Steve to write to Dominic Clark to explain the situation when the health and safety check has been done No planning permission is needed to re-locate containers if no plumbing etc is involved No contract has ever been raised re the containers Bike Pod – The purpose of this pod was for the cycling projects. Pod should now be removed, as access has not been possible due to a key not being available. Holly Preston and Paul Finch to write to the cycling projects Memorial Garden – Design being decided. Mosaic being created and should be, hopefully, completed by November Entrance Way – Some trees (possibly 6) need to be felled to encourage new planting. Many of these trees have not been maintained Will need to inform the community committee and suggested an artists sketch be done to show the vision of the entrance £500 for the planting of new trees has been donated to the Friends Group by Tesco. It could be possible to start work on the entrance in November Congratulations to the Environmental Services who have won a national award for their Ground Maintenance Service Team UPS After being re-assured, the ants on the George Thomas railings are still not painted Part of the railings have been repositioned – Holly to check with Ian Worsley on the responsibility of re-painting these railings The £3000 pledged by UPS will have to be ‘rolled over’ due to being over subscribed. Caroline Lightfoot did not apply for the $11,000 bid – situation complex George Thomas Playground – Holly Preston and Helen Ball Work underway and should be completed in approximately 3 weeks. Art work possibly will take a little longer An opening ceremony is being discussed BMX Skate Park Painting of gate – gate been relocated – Steve Jones to update as no response has been received from e-mails sent Drainage – Date is needed for work to be done It was suggested that one of the BMX users need to ring call centre to report problem and to get a log number Boundary Road Playground – Railings still need painting. This is on the PPGC agenda and will be done this year Pool Developments No update received from Wendy Walker – please update for next meeting Prince’s Park Garden Centre – Tom Broad Toilets – Will be delivered by November and will be available for use when PPGC is opened for the immediate future Café - £200,000 has been identified. Tom in dialogue with Ken Whittick to move this forward with the whole plan for the Garden Centre Friends’ of Prince’s Park A new member has now joined the group and has shown willing to do the Friends’ web-site As stated under 3a, £500 from Tesco Store (Irlam). £500 from the Tree Council with 25% from Salford Council for tree planting Action plan created at last meeting – group training to be Community Tree Inspectors Youth Shelter The Edge youth workers have started building relations with the young people who use the ‘band stand’ which they use as a youth shelter It is positive that a plan of work can be done with the young people and have identified a possible site at the rear of the BMX Park. They have also shown an interest in building their own shelter instead of a custom made structure. They have also been asking for litter bins | Steve Taylor Holly Preston Steve Taylor Holly Preston / Ian Worsley Steve Jones Tom Broad Wendy Walker |
| CADISHEAD PARK – Holly Preston 72 questionnaires were completed by the local residents Landscape Architect has costed blocks of work : Using Community Centre as a temporary ranger base Football pitch re-location Lighting for footpaths and new electrics in the bowling pavilion New enhance on Liverpool Road Remove old toilet block and football changing room and build replacements on back of community centre Footpath improvements The cost would be £1,229,346 which excludes any contamination of land and buildings. Surveys need to be carried out. Also consulting with other council departments |  |
| RANGER ACTIVITIES – Holly Preston The Bat Watching walk was attended by 23 people School groups are still booking Stepping Stones walks to continue to January 2007 The Buggy Walks with the PCT to launch as 4 individual events The Fishing Pegs funding bid to Awards for All has been submitted Dog Training has started again in Cadishead Park on a Sunday Clean-up of the allotments in Prince’s Park which was organised through the Mormon Helping Hands was attended by over 200 volunteers and was very successful |  |
| IRLAM LIBRARY PLANTING SCHEME – Steve Taylor Steve to submit a comm..comm. budget form for funding for planting the area | Steve Taylor |
| ANY OTHER BUSINESS The old river course land ownership – the council does not own this land. Copies of the legal planning agreements to identify maintenance issues need to be obtained Irlam Rangers – a representative from this group needs to attend this meeting on a regular basis |  |
| DATE / TIME / VENUE OF NEXT MEETING Date: Tuesday 21 November 2006 Time: 10:30 am Venue: TBC |  |