POST OFSTED ACTION PLAN

MONITORING REPORT

October 2002

## City of Salford, Education & Leisure Directorate

# Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 1 In order to provide schools with greater financial autonomy: a) Consultation with schools on fair funding should lead to a greater level of delegation of resources. Aggregate Inspection Grade 4 | Lead Person/s Monitoring: Jill Baker, Director Of Education and Leisure, Deputy Director, Education and Leisure, Bob McIntyre, Head Of Finance. |
| --- | --- |
|  | Monitoring and Evaluation Strategy Termly meetings of the School Funding Review Group (comprising representatives of primary, secondary and special school Headteachers, Governors, Councillors, and Trade union officials) to consider services currently delegated to schools and the proposed delegation of further services. Monitoring of Section 52 budget statements by the School Funding Review Group. Wider evaluation of proposals agreed at the School Funding Review Group to take place through programmed meetings with Headteachers. Review of delegation of resources via Leadership Team and Scrutiny Committee meetings. Monitoring and Evaluation through the Education Development Plan. |
| Strengths A commitment has been made to raise the level of delegation in the next financial year (Para 32) |  |
| Weaknesses Spending not entirely linked with Council/LEA priorities. Concern about level of delegation and effectiveness of deployment of funds (Para 32). However this judgement does not standout when compared with other LEA's inspected. |  |
|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| 1.1 | Increased delegation of resources. Consideration of delegation of resources for community use. Reduction of small schools factor in the funding scheme. | March 2002 | Level of delegation 86% by April 2000. (1999/2000 figure was 77% for comparison) | The level of delegation for 2002/2003 remains at 87%. The small schools factor has been reduced to its minimal level. Primary schools will get £3,600 and Secondary schools £11,000 small school allowance. Resources for community use have been delegated to Community Committees. | DfEE Guidance on the Financing of Maintained Schools. Best Value Performance Plan Directorate Service Plan. |
| 1.2 | Further review of delegated areas in the light of the SEN Commission report. | April 2003 | Agreement on funding options for SEN by 2001. Implementation of options requiring no policy change March 2001. Those requiring policy change March 2002. | As a result of initial consultation, Headteachers asked to widen the scope to include methodology for delegation, funding currently delegated and new funding for delegation. Further consultation is now in process to include AEN/SEN resources. | SEN Commission Report Behaviour Support Plan Education Development Plan Best Value Performance Plan |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 2 To raise standards of attainment: Maximise the delegation of the IAS budget to schools, particularly in relation to training and curriculum support; Target support and challenge schools to raise the quality of teaching at Key Stage 3, particularly in relation to literacy and numeracy; Develop a vision and strategy for ICT which is shared with schools and; Focuses on curriculum support to schools to raise standards of attainments in ICT and other subjects through ICT: Provides a clear training strategy which enables teachers to meet the government's targets for skill and expertise. Aggregate Inspection Grade 4 | Lead Person/s Monitoring: Judy Edmonds, Acting Deputy Director, Education and Leisure, Anne Hillerton, Assistant Director, School Improvement, Richard Dodd, Senior Inspector-Advisor, Jane Austin, Excellence in Cities Co-ordinator |
| --- | --- |
|  | Monitoring and Evaluation Strategy Monitoring via level of buy-back by schools, and level of participation by teachers Monitoring via the requirements of DfEE and the LEA Key Stage 3 Pilot Plan Evaluation of strategy development via schools/officers forum Monitoring via OFSTED report and Inspector-Adviser visits Annual review of pupil attainment in ICT Review of progress against EDP targets Monitoring via EiC strand group Monitoring and Evaluation through the Education Development Plan. |
| Strengths The LEAs support for Literacy is sound with training rated as satisfactory to good. Progress in raising standards in Numeracy is good. There are pockets of good practice in ICT. |  |
| Weaknesses Results at Key Stage 3 and 4 are below the national average. |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 2.1 | Training and additional curriculum support and guidance to be offered to schools on an individual buy back basis specified annually. This will include support for the development of ICT. |  | Positive evaluation and feedback from headteachers | A satisfaction survey concerning Inset offered by the Inspection-Advisory Service was completed in the Summer term. Feedback was very positive. The Inspector-Adviser for ICT and one Advanced Skills Teacher are working with staff in primary schools. The SLA offered to schools indicates that to date all Primary schools have bought into the service. | Education Development Plan, Standards Fund Information Booklet for Schools, ICT Development Plan |
| 2.2 | Secondary schools will take part in the national pilot for KS3 in literacy and numeracy and have been invited to take part in the Science and Transforming Teaching and Learning in foundation subjects. All schools will have specific Key Stage 3 targets. Excellence in Cities has specific targets which are indicated in the EDP. Attention will be given to bridging the transition from primary to secondary schools. |  | Excellence in Cities targets reached. Outcomes linked to evaluation framework for national KS3 project. Successful outcomes from KS3 project pilot schools. IAS will focus on Key Stage 3 in all schools during review visits. | Actions are detailed in EDP 2. Trialled Literacy and Numeracy strands. Identified departments needing intensive support. Consultants working with these schools. Trialled Science and Teaching and Learning in Foundation Subjects strands. Identified departments needing intensive support. Consultants working with these. Leading Teachers programme in place. TFL Consultants working on cross-curricular initiatives with twenty departments to improve teaching and learning including the use of assessment. Trialled ICT units during Summer term 2002. Currently trialling Modern Foreign Languages Framework (2002-2003). LEA focussing on raising academic transition with Key Stage 3 Strategy 2002-2003, especially in core subjects. Key Stage 3 Results English L 5 –54% Target L 5 – 68% English L 6 – 19% Target L 6 – 26% Maths L 5 – 60% Target L 5 65% Maths L 6 – 33% Target L 6 – 34% Science L 5 – 56% Science L 6 – 19% No targets for Science for 2002 English results fell at both Levels 5 and 6 from 58% to 54% at Level 5 and from 26% to 19 % at level 6. This performance leaves Salford at 14% below the level 5 target and 7% below the level 6 target. Results in Maths improved for the third year running to 60% at level 5 and 33% at level 6. We remain 5% below the level 5 target and 1% below the level 6 target. Science results fell back slightly by 1% at level 5 to 50% and by 3% to 22% at level 6. There were no targets for Science. | Education Development Plan, Excellence in Cities Implementation Plan KS3 Pilot Plan |
| 2.3 | A framework for evaluation of ICT practice will be developed. This will be in discrete subject areas and across the curriculum. Links will be made between schools via lead teachers, City Learning Centres and Beacon schools. |  | Service Level Agreement with schools on curriculum support. Focus review by Inspection Advisory Service on school visits. | Because of the Best Value Review of the School Improvement Service, the ICT framework for development of ICT practice has been put on hold. The Education Broadband Project has begun to be implemented and all schools will benefit from Internet access by November 02. Briefings for schools arranged for Autumn Term and communication links have been established. | Education Development Plan, Excellence in Cities Implementation Plan ICT Development Plan. |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 3 To improve the management and governance of schools: Share school evaluation reports with governors to assist them in their role of evaluating the work of schools; Complete and distribute an audit instrument for governing bodies to enable them to complete a self-evaluation of their effectiveness as detailed in the Education Development Plan; Act swiftly to fill LEA governor vacancies within a stated timescale and encourage all Governors to play a full and equitable role. Aggregate Inspection Grade 4 | Lead Person/s Monitoring: Lynn Wright, Assistant Director, Resources, Anne Hillerton, Assistant Director, School Improvement. |
| --- | --- |
|  | Monitoring and Evaluation Strategy Feedback from termly governing body meeting via minutes and Link Officer attendance Evaluation of the training provided for governors Evidence of effectiveness provided via OFSTED reports Review of progress via Leadership Term and Scrutiny Committee processes Feedback from school visits by Inspector-Advisers and OFSTED, and from termly governing body meetings via minutes and Link Officer attendance Direct feedback for governors identifying gaps in their knowledge/expertise Evaluation of the training programme for governors Review of progress via Leadership Team and Scrutiny Committee processes. Monitoring of vacancy levels on a weekly basis by Lead Member and Deputy Lead Member for Education Monitoring and evaluation through the Education Development Plan |
| Strengths Governors are generally well supported by the LEA, over 95% of schools buy into Governor Training. (Para 67). |  |
| Weaknesses Governors do not as yet receive all the information available on their school's effectiveness. |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Revised schools governors' self-evaluation Framework. | September 2002 | New Schedules implemented during academic year 2000/2001 | Framework revised to include new Terns of Reference regulations and Ofsted Inspection Framework. In order to link in with IAS revised Framework for Headteacher training; the launch has been re-programmed for December 2002. | Managing for Success, Education Development Plan |
| 3.2 | Inspection and Advisory Service reports to Governors to be revised to take account of the new Ofsted model. | Ongoing | New Schedules implemented during academic year 2000/2001 | Reporting schedule is under ongoing review in order to provide Governing Bodies with useful information. The Inspection -Advisory Service reviews the process and makes amendments to make the information more meaningful for Governors. They will suggest areas for discussion and follow up with the school. The timing of when visits take place, when reports are prepared and when they are sent to Governing Bodies is to be reconsidered, although the timescales are difficult to reconcile because of externally imposed conditions. | Managing for Success, Education Development Plan |
| 3.3 | Training to be offered to governors on the use of the revised models | September 2001-September 2002 | Training modules receive positive evaluation | First pilot training course for Governors takes place December 2002. | Managing for Success, Education Development Plan |
| 3.4 | Marketing and Communications exercise to be undertaken to promote the filling of vacancies with a target of less than 7.5% of post vacant overall during the year. | September 2001 | Target to be met by September 2001 Monitoring of attendance and follow up action. | Monitoring of attendance and follow up action in place. Roles within Governor Service Team are evolving. A named person has responsibility for monitoring of vacancies. The percentage of vacancies fluctuates from term to term and has ranged from 5% - 8.4%. | Managing for Success, Education Development Plan |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 4 In order to improve levels of service management: Service team plans should be reviewed to state clearly their contribution to targets in key corporate and educational fields and include costs and measurable and realistic success criteria: Schools should be provided with a clear definition and specification for each service; details of costs; and methods by which the service is to be monitored and evaluated. Aggregate Inspection Grade 4 | Lead Person/s Monitoring: Lynn Wright, Assistant Director, Resources, Anne Hillerton, Assistant Director, School Improvement |
| --- | --- |
|  | Monitoring and Evaluation Strategy Annual Review of the Directorate's service planning process by the Strategy Team Regular review of service plan via Scrutiny Committee Half yearly monitoring of progress against service team plans by Leadership Team Monthly review of progress by individual service teams. Review of approach to service specification by School Funding Review Group, the Services to Schools Group, and the Best Value Review of 'Services to Schools' Monitoring and evaluated through the Education Development Plan |
| Strengths The monitoring of performance relating to service plans is well managed (Para 78) |  |
| Weaknesses Although team plans adopt a common format, they vary considerably in quality. Some are poor. |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 4.1 | Team plans and Service Level Agreement with schools to include information on costs and to clearly state their contribution to Corporate and Directorate Objectives. | September 2002 | A robust planning process. Subject to evaluation by Best Value Review. | The Service Plan 2001/02 went to Scrutiny in early October 2002. Monitoring of 2002-2003 is ongoing. The half-yearly report will go to Scrutiny in December via Leadership Team. Extensive work is underway on reviewing planning processes within the Directorate. A Schools Forum will be established Autumn 2002 to complement the work done by the School Funding Review group. There are several significant recommendations arising from the Best Value Review of services to schools. These are: A brokerage arrangement to be established A programme of investment be developed to enable services to compete effectively with other providers Consideration to be given to the means by which central costs borne by the services which are passed on to customers through the SLA are distributed SLA documentation to be reviewed Continuous maintenance and development of Services to Schools group Continuous maintenance and development of the SLA group | Corporate Plans. Directorate Plans, Best Value Review Plan, All Team Plans |
| 4.2 | Review the Services to Schools Directory to include targets and evaluation criteria. Where services are not delegated, a set of standards will be published. | April 2002 | Evaluation by schools showing improvement on a year by year basis. | Services to Schools Directory Revised to include service standards and in schools by April 2002. Further work has been undertaken on improving communications and relationships with schools as a result of the Best Value Review, as detailed under 4.1 | Corporate Plans. Directorate Plans, Best Value Review Plans, All Team Plans |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 5 In order to improve the effectiveness of special educational provision: Develop an SEN and Inclusion Policy which is underpinned by the principles of early identification and intervention; Draft, in consultation with schools, a detailed, long-term SEN strategy Develop transparent and equitable criteria for allocating resources to pupils and develop monitoring and evaluation arrangements for stages 3-5 of the Code of Practice. Aggregate Inspection Grade 5 | Lead Person/s Monitoring: Judy Edmonds Assistant Director, Access, Inclusion and Development |
| --- | --- |
|  | Monitoring and Evaluation Strategy Develop an SEN and Inclusion Policy which is underpinned by the principles of early identification and intervention; Draft, in consultation with schools, a detailed, long term SEN strategy Review SEN funding with a view to increasing the amounts delegated or devolved to schools; Develop transparent and equitable criteria for allocating resources to pupils and develop monitoring and evaluation arrangements for stages 3-5 of the Code of Practice. |
| Strengths There are examples of very good initiatives, for example, the development of barrier free and language provision I primary schools with enhanced resources provides excellent examples of inclusive education. |  |
| Weaknesses There is no up to date SEN policy or overall strategy for the development of Special Education. (Para 87). SEN provision is expensive: too much money is spent on a highly centralised service resulting in low cost provision. (Para 98). |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 5.1 | Act upon the outcomes of the SEN Commission. Draft policy document subject to consultation September 2001. |  | Recommendations of SEN Commission effectively implemented and positively evaluated. Draft Policy document in place. | Director engaged a consultant to develop SEN Policy and Strategy May 2002. Policy and Strategy re-drafted. Consultation completed September and Policy and Strategy will go to Cabinet for approval 8th October. Detailed Action Plans drawn up to accompany the Strategy. | Best Value Performance Indicators Education Development Plan Behaviour Support Plan |
| 5.2 | Consultation with schools regarding further delegation of SEN resources. | April 2003 | Recommendations of SEN Commission effectively implemented and positively evaluated. | This cross-references to 1.2 The LEA sought information on national best practice regarding the delegation of SEN resources. As a result of this the decision was made to revise the formula for allocation of Additional Needs/SEN resources, based on a variety of indicators rather than Free School Meals. The SEN Funding Group was established to consider the basis for delegation of SEN resources. Work is ongoing and formal consultation papers will be ready for the consultation period November – December 2002. . | Best Value Performance Indicators Education Development Plan Behaviour Support Plan |
| 5.3 | To review the Education Welfare Service and implement to outcomes of the review. | September 2001 | Effective implementation of the outcomes and positive evaluation. | Review of Education Welfare Service completed and outcomes implemented. | Best Value Performance Indication Education Development Plan Behaviour Support Plan Crime and Disorder Strategy Quality Protects Management Action Plan Best Value Performance Plan |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 6 In order to maximise the resources allocated to education: In consultation with the Dioceses, complete the review of primary places as a matter of urgency; Take urgent action to significantly reduce the number of surplus places in the secondary sector; Reduce the level of support provided by the small school protection factor. Aggregate Inspection Grade 6 | Lead Person/s Monitoring: Jill Baker, Director of Education and Leisure, Judy Edmonds, Assistant Director, Access, Inclusion and Development |
| --- | --- |
|  | Monitoring and Evaluation Strategy Monitoring of performance against Best Value Performance indicators relating to surplus places: Evaluation of the outcomes of the School Review which is currently taking place Analysis of places by denomination Monitoring and evaluation of strategies by the School Organisation Committee Evaluations of funding proposals by Cabinet and Council Ongoing analysis of school places Ongoing analysis of school funding and how it is directed. School Funding Review Group and feedback from consultation with schools on development of the financial scheme. Monitoring and evaluation through the Education Development Plan. |
| Strengths In the primary sector, a two-part review of surplus places has taken place and is now being implemented. (Para 100). |  |
| Weaknesses There is an unacceptable level of surplus places in Salford schools. (Para 99). |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 6.1 | Agree with the Dioceses a commitment to publish a consultation document leading to a School Review | Previously January 2001 – now September 2002 | Reduction in the number of surplus places year on year, so contributing to the City's target (see below). | The Diocesan boards are not currently considering a city-wide review. Some action is being considered with two central Salford RC schools and three Little Hulton RC schools. | Education Development Plan, Asset Management Plan, School Organisation Plan, Class Size Plan |
| 6.2 | Consult upon a review of secondary schools |  | Reduction in the number of secondary schools. | Secondary school review of surplus places completed. The PFI bid is still in process. Procedures have started with DfES to arrange physical alterations following the review. | Education Development Plan, Asset Management Plan, School Organisation Plan, Class Size Plan. |
| 6.3 | Monitor schools with surplus places greater than 16% moving to action at 20% |  | Reduction in surplus places to an overall level of 8% in the City as at September 2003. | Primary Review. - Still on target. An options consultation began September 02 and will be completed December 02.Final options go to the School Organisation Committee in August 2003.1st phase will be strategic decisions, 2nd phase will be the investment programme. | Education Development Plan, Asset Management Plan, School Organisation Plan, Class Size Plan. |
| 6.4 | Consult upon the reduction of the small school factor in funding formula |  | Reduction in the small schools factor incrementally over three years. | This cross-references to 1.1 The small schools factor has been reduced to its minimal level. Primary schools will get £3,600 and Secondary schools £11,000 small school allowance. | Education Development Plan, Asset Management Plan, School Organisation Plan, Class Size Plan |

Monitoring and Evaluation of LEA Post Ofsted Action Plan

| Recommendation 7 In order to improve the condition of school buildings: Increase the level of investment in school building maintenance, including the use of public-private partnerships; Make the priorities for investment transparent and agree them with schools; Review procedures to ensure that health and safety issues in schools are dealt with within an appropriate timescale. Aggregate Inspection Grade 6 | Lead Person/s Monitoring: Jill Baker, Director of Education and Leisure, Judy Edmonds, Assistant Director, Access, Inclusion and Development |
| --- | --- |
|  | Monitoring and Evaluation Strategy Monitoring of performance against Best Value Performance indicators relating to surplus places: Evaluation of the outcomes of the School Review which is currently taking place Analysis of places by denomination Monitoring and evaluation of strategies by the School Organisation Committee Evaluations of funding proposals by Cabinet and Council Ongoing analysis of school places Ongoing analysis of school funding and how it is directed. School Funding Review Group and feedback from consultation with schools on development of the financial scheme. Monitoring and evaluation through the Education Development Plan. |
| Strengths Condition surveys of schools have been carried out and have identified a need for investment of £37 million in the top two priority categories and £48 million in the third. (Para 106). |  |
| Weaknesses The history of poor stewardship has had a serious impact on schools. There are substantial problems with the condition of a number of school buildings. |  |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 7.1 | Using the outcome of the school places review and the evidence of the Asset Management Plan, develop positive responses to reduce the number of schools with accommodation difficulties | Linked to the School Places Review | Measures of accommodation suitability show improvement year on year. | Results of Primary Review will take out some poor accommodation which will reduce the maintenance backlog Using schools devolved funds and seed challenge funding to bring about better responses to some of the accommodation issues Salford continues to explore development opportunities with the private sector to facilitate school access issues, focussing on Primary Review solutions. | Asset Management Plan. School Organisation Plan. Education Development Plan |

|  | Action | Date By | Published Success Criteria In Action Plan | Progress Statement | Links With Code of Practice and other Planning Documents |
| --- | --- | --- | --- | --- | --- |
| 7.2 | PFI initiatives to be continued alongside other bidding strategies the process of bidding to be subject to consultation with schools. |  | Measures of accommodation suitability show improvement year on year. | PFI bid has been resubmitted and is on the reserve list. DfES has notified the LEA that the reserve list is not being supported and the LEA will have to bid again. DfES have allocated capacity support money alongside programme of works undertaken out of targeted capital funds. | Asset Management Plan. School Organisation Plan. Education Development Plan. |
| 7.3 | Develop a more robust system to identify health and safety issues and timescales for response. |  | Monitoring shows health and safety issues are identified and dealt with within agreed timescales. | The Directorate has appointed a full-time Health and Safety Co-ordinator in addition to existing corporate support. The Health and Safety Policy has been revised and sent to schools. Briefing sessions have taken place. Schools have received first procedures audit, which has identified some concerns. Officers are arranging cluster seminars for issues arising from the audit. Officers are undertaking practical school walk around procedures. Generic guidance on risk assessments is being produced. A separate stakeholder group with Primary and Secondary school representatives has been established. | Asset Management Plan. School Organisation Plan. Education Development Plan. |