Salford LEA Post OfSTED Action Plan

# Monitoring and Evaluation Arrangements

| Action | Lead Personnel | Timescale | Resource implications | Monitoring arrangements | Evaluation |
| --- | --- | --- | --- | --- | --- |
| Formal review of progress against planned actions by Leadership Team | DEL | Quarterly from March 2004 | Officer time – 1 day per member of Leadership Team per quarter | Director ensures that formal reviews take place according to planned timetable | Evidence of progress towards meeting success criteria set out in Action Plan reported to Leadership Team and critiqued by peer review/analysis |
| Outcomes of formal reviews written as a progress report to be submitted to Lead Member | DDEL | Quarterly from March 2004 | Officer time – 1 day per quarter | Deputy Director ensures that progress report derives from review and critique and is delivered to Lead Member | Progress on impact of actions reported on. Reports are concise, analytical, focused on success criteria and evidence based |
| Lead member presents progress reports to Scrutiny Committee | Lead Member for Education | Bi-annually from March 2004 | Officer time – 1 day per six months | Scrutiny Support Officer ensures that the meetings are scheduled and take place Lead Member for Education ensures that Scrutiny Committee are informed of progress against planned actions | Feedback from Elected Members on the quality and impact of actions. Leadership Team considers feedback from Elected Members and reviews/amends actions as necessary in order to optimise positive impact and achieve success criteria |