Salford LEA Post OfSTED Action Plan

Timeline

| Strategic Priority | March 2004 – May 2004 | June 2004 – August 2004 | September 2004 – November 2004 | December 2004 – February 2005 | March 2005 – May 2005 |
| --- | --- | --- | --- | --- | --- |
| Strategic Planning and Resources | Training for service plans Develop database of service plans Develop local performance indicators Quality assure Service Action Plans 5 year indicative budgets supplied to schools Agree data sharing protocol with schools Review progress against plans | First round of monitoring of plans and targets to identify and address slippage Team Leader & school teams established for Grounds Maintenance Grounds Maintenance Mowing frequency reviewed Grounds Maintenance annual satisfaction survey Develop target setting procedures with schools to include specific groups | 5 year indicative budgets including carry forward Annual review of performance data of schools Sharing of best practice between schools Report on school performance to stakeholders | Grounds Maintenance Annual performance review to schools Data profiles for schools established Agree with schools the annual data analyses | Rolling Service Level Agreements introduced for Grounds Maintenance |
| Integrated Services | Establish School Organisation Group Task group of School Improvement Service and Inclusion and Access and established and joint protocols agreed Re-establish regular meetings of Connexions Partnership including Youth Service Connexions Manager and Head of Youth Service consult on the production of annual plans | Establish minimum management entitlements/ responsibilities Include EWOs as part of annual internal review of schools Include attendance review as part of autumn term school visit agenda Establish more regular pattern of Connexions and Youth Service Management | Evaluate the pilot project of School Improvement Service and Inclusion and Access Division joint working arrangements Develop the strategic role of Forums Develop the SCC Group Possible establishment of an Action Learning set in conjunction with Revans Institute | Refine data sharing protocols and mechanisms between SIOs and EWOs |  |
| Special Educational Needs, Inclusion & Access Curriculum, Governance and Teacher Development | Review monthly PI monitoring Revise paperwork for provision of CSSD stat assessment advice Develop protocol with PCT for medical advice within stat timescales Quarterly monitoring & analysis of PI data with the PCT Increase liaison with Parent Partnership/SENCOs to ensure attendance at medical appointments Revise correspondence for parents to emphasise importance of medical appointments Complete guidance on the graduated response by publishing criteria document for schools Ensure admission criteria for Notschool.net provision is have been shared with all stakeholders Performance targets amended to ensure appropriate provision for excluded pupils Draft Behaviour Strategy amended following internal consultation and then circulated to all stakeholders for consultation Feedback from consultation used to inform the Behaviour Policy Agree a protocol for the “pilot managed move” initiative with given schools an initiative and monitor and evaluate the progress Develop an electronic recording system listing all child protection training available Report to governing bodies regarding operation of race policies SIOs to include race issues on the agenda for autumn term visits to schools Equalities checklist to be prepared and sent to schools Transfer of the Governor Services Team to the School Improvement Service Review and evaluate NQT induction and initial CPD Review and evaluate new headteacher induction programme Identify from schools the most pressing CPD needs Establish positive relationships with appropriate training providers, including those within the established brokerage | Provide SENCO training on SSE Establish programme for monitoring SEN budgets Ensure all pupils who are excluded from school receive provision within 15 school days Ensure all excluded pupils have an appropriate IEP Publish Behaviour Policy as part of LEA Inclusion Strategy Produce draft guidance document for schools on managing behaviour and following consultation amend accordingly Provide a programme of in-service training on Behaviour Management Agree a common referral for support related to SEBD in mainstream Develop a replacement for the Pupil Placement Panel Review EMTAS school resource allocation procedures Determine core purposes/duties of EMTAS with the steering group linked to SIS Evaluate EMTAS service delivery and funding arrangements in comparable LEAs identifying and learning from best practice Recruit and appoint an educational child protection officer to promote and monitor practice in schools Evaluation of the scheme for reporting of racist incidents with schools Review content of termly SIS agendas with schools Develop quality assurance systems of Records of School Visits Review and evaluate communication processes between SIS and governing bodies Target governing body link officer support in inverse proportion to success Work with schools to develop and up to date database of teacher vacancies Define and publish the core activities provided for the induction of newly appointed Headteachers Establish electronic systems for targeting, booking, tracking and evaluating CPD Publish CPD activities to schools Develop a charging policy for LEA brokered CPD that supports schools in achieving Best Value Create and publish a comprehensive calendar of events to ensure CPD can be planned without conflicting priorities and seasonal overload | Publish and distribute guidance document on managing behaviour Review PRU staff deployment in order to provide outreach/ reintegration and support Provide documentation and briefings on criteria for dealing with SEBD for all stakeholders Train EMTAS staff on the use of performance data Officer to be appointed to work with schools to promote equal opportunities issues Possible revision of reporting racist incidents procedures Develop feedback loops between governing bodies, SIOs and Governor Services Provide first set of annual training for governors on the interpretation and use of data Review and evaluate recruitment and selection of NQTs Broker support for new Headteachers via CEL and other providers Include an evaluation of headteacher induction as part of additional time allocation to relevant schools | Review PRU provision and referral structures Develop materials to support schools in building their own capacity around dealing with the learning needs of ethnic minority groups and individuals Involve EMTAS staff in SIOs annual target setting visits with relevant schools Work with EMTAS Steering Group to determine funding and organisational arrangements from April 2005 Rationalise funding streams in line with core and additional activities of EMTAS Establish quality assurance mechanisms in relation to externally provided CPD | Establish monitoring and evaluation processes to assess the impact of EMTAS support on pupil inclusion, learning and achievement Link the work of EMTAS with Directorate and Corporate anti-racism and inclusion priorities Broker support for schools with advertising vacancies Further develop links with HE and CEL promoting access to CPD at all levels |