Template Community Safety/LAA Action Plan

Note: the abbreviation STA denotes that the action has been recommended from the Strategic Threat Assessment

| Objective 1: Helping all our communities feel safer |
| --- |
| Action | How/what activity? | Lead Agency/Officer | Timescales (when achieved by) | Indicative costs | National indicator (Bold if in LAA) |
| Prevention |  |  |  |  |  |
| Preparing a localised action plan for each neighbourhood which reflects local needs and priorities | Annual Community Action Plan development process | Neighbourhood managers | Annually in April Complete | CHS directorate Mainstream Budgets | NI 3, 4 |
| Report to communities regularly on performance including perception | The Pilot Dashboard of indicators in Ordsall and Langworthy is in place and funded by URC. CDRP to consider options for resourcing further roll out. | Anna Macdonald Hughes | March 2011 | URC have funded the Ordsall and Langworthy pilot. CDRP to consider options for further roll out. | N 4, 5, 17 195 |
| Further engaging with the community, empowering them to determine local priorities and solutions | Neighbourhood Managers and Inspectors to engage with and develop local consultations with the community | Neighbourhood managers | PACT Meetings Developed Complete. | CHS directorate | NI 3, 4 |
|  | Senior officers of the CDRP/LCJG to hold ‘face the people’ sessions | Don Brown | Held Annually in September Complete | £1,000 | NI 3, 4 |
| Improving the street scene by tackling litter, dog fouling, graffiti and other blight, and repairing and improving street lighting, furniture and CCTV. | ECT, PCSOs, PAs report problems and issue FPNs to offenders for dog fouling, litter, graffiti. | Phil Morton GMP Stuart Collins | Ongoing activity | ES GMP UV Mainstream Budgets | NI 5, 17, 195 |
|  | Work with street lighting managers to upgrade lighting in vulnerable locations to BSEN 13201 | Stuart Collins, Urban Vision | Ongoing development programme. |  | NI 15, 16, 17 |
| Working with communities to make vulnerable locations safer | LPDGs to conduct local problem solving engaging communities via PACT’s and appointing a local community member to each LPDG | Neighbourhood managers/ Local Inspectors | Pacts established in all areas and community representative now sitting on each LPDG. Complete | Mainstream Budgets | NI 15, 16, 17 |
| Building a safer environment by ‘Designing Out Crime,’ where the design of physical structures can deter criminal activity. | A crime impact statement to be provided on every significant planning application with the help of GMP. | Stephen Kearney | System in place January 2010 Complete | Mainstream Budgets | NI 15, 16, 17 |
|  | Protocol agreed with Salford Development Control, Urban Vision and planners, ensuring Secure by Design principles are considered at the design stage. | Stephen Kearney | System in place Sept 2009 Complete | Mainstream Budgets | NI 15, 16, 17 |

| Action | How/what activity? | Lead Agency/Officer | Timescales (when achieved by) | Indicative costs | National indicator (Bold if in LAA) |
| --- | --- | --- | --- | --- | --- |
| Working with ex-offenders and those at risk of offending to help them become good citizens | Engage prisoners during sentence, gain commitment to change, prepare individual action plan to obtain employment on release. | Back to Work in Salford team. | Complete process in place. | £165,000 | NI 2, 18, 30 |
|  | Establish a restorative justice project with Kirkham prison to enable offenders to carry out community work, linking with CPB & YOS. | Stewart Williams | In place Com-plete | Mainstream budget | NI 2, 18, 30 |
|  | Target offenders or those at risk of offending with one to one mentoring support - enable signposting to other agencies. | Susan Puffett | In place Complete | £40,000 LAA | NI 2, 18, 30 |
|  | Continue to support the one stop shop for women offenders or those at risk of offending. Deliver one to one support and activities to reduce their offending behaviour. | Susan Puffett Together Women’s Project. | Complete | £5,000 | NI 2, 18, 30 |
|  | Identify those young people at risk of becoming offenders and provide extra support involving LPDGs | BEST team. YOS | System in place Complete | Mainstream Budgets | NI 19, 111 |
|  |  |  |  |  | NI 19, 111 |
|  | Restructure the reoffending task groups and create two new groups Youth Crime & offenders in the community. | Susan Puffett Annette Anderson Damian Dallimore | Introduced Sept 2009 Complete | Mainstream Budgets | NI 16, 17, 18, 19 111, 115 |
|  | Continue close partnership working between the YOS Prevention team, to provide a wide range of projects and activities to reduce re-offending. | Susan Puffett | Youth Crime Group established Complete | Mainstream Budgets | NI 19, 111 |
|  | Develop restorative justice training and YRD pilot. | Susan Puffett Pauline Copeland | Training has taken place and rolling programme in operation Complete | 3,500 | NI111 |
|  | Engage ‘hard to reach’ groups and provide support to enable them to become employed by Salford Council. | David Horsler David Timperley | Futures Fund created and in place Complete | Mainstream Budgets | NI18 |
|  | Engage offenders in training for work with the construction agencies. | David Timperley | Complete | Mainstream Budgets | NI18 |
|  | Continue to target the top 50 PPO’s. | Annette Anderson | Ongoing supervised by PPO Task Group Complete | Mainstream Budgets | NI30 |
|  | Develop an integrated offender management system | Annette Anderson | Still being developed September 2010 |  | NI 30 |
|  | Engage those offenders released on license or with community sentences with reparation projects chosen by the community. | Carol Johnson | System introduced via LPDG and Community Committee’s Complete | Mainstream Budgets | NI 18, 30 |
|  | Schools and Colleges: Engage with schools and colleges to ensure appropriate delivery of awareness sessions surrounding domestic abuse, drugs and alcohol, bullying, ASB and crime and personal safety keeping LPDGs informed | Julie Chapman Don Brown Hilary Pollard (substance misuse education consultant) | Best Team taken over this role Complete | Mainstream Budgets | NI 1, 2, NI18 NI19 |
| Increasing the opportunity for communities to provide information and intelligence to reduce community tensions (PSA 26) | Establish key individual networks. | Supt Wilkinson | Established in all neighbourhood areas, complete | Mainstream Budgets | NI 1, 2, 3, 4 |
|  | Work with the Loan Shark team and encourage community members to provide information. | Susan Puffett | Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
|  | Develop the role of third party Hate Crime Reporting Centres to include tension monitoring | GMP/Shaun Clydesdale | Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
| Ensuring transparent decision making and resource allocation processes to safeguard community cohesion (PSA 21) | Establish a reporting system for CDRP meetings which clearly identifies the decision-making process and consultation with all interested parties. | CDRP Chairs | Adopted within minutes. Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
| In partnership with the community identify people who intend to cause the community harm/ Implement and deliver the national Prevent strategy locally | Utilise when appropriate representatives of Independent Advisory Group identify individuals who intend to cause the community harm. | Supt David Wilkinson | Strategy Implemented Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
|  | Establish a multi-agency Prevent Task Group (task and finish) to support the development of Prevent work locally and build capacity with partners around the Prevent agenda. | Sup. Wilkinson/Shaun Clydesdale | Task Group Established Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
| Identify the location and numbers of new and emerging communities in Salford. STA - | Commission within the next Strategic Threat Assessment - June 2009. | Nigel Preston | CDRP Strategic Threat Assessment June 2009 Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
| Increase awareness/confidence of criminal justice system/sentencing among community. | Sentencing Event | Court Community Justice Communication Manager – 0161 834 9457 | BI-ANNUAL events established Complete | Courts Budget | NI 1, 2, 3, 4 |
| Community Justice Newsletter for community members – October edition to be distributed to every household/business in Eccles (16,200 copies). | Community Justice news has now been included in the quarterly community newsletters, information being supplied by the courts and police. | Court Community Justice Communication Manager – 0161 834 9457 | Quarterly Community Newsletters published. Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
| Recognition of staff/volunteers. | Justice Awards Annual applications made for staff to attain awards. | LCJG CDRP MEMBERS | ANNUAL nominations submitted in August Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
| Discussion on all policing and criminal justice issues. | Independent Advisory Group | Police | Ongoing – bimonthly meetings Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
| Address emerging diversity issues and updating Diversity Action Plan. | GMP Diversity Action Group | GMP Diversity Action Group | Ongoing – bimonthly meetings Diversity Action Plan created and monitored by group. Complete | Mainstream Budgets | NI 1, 2, 3, 4 |

| Action | How/what activity? | Lead Agency/Officer | Timescales (when achieved by) | Indicative costs | National/ local indicator number |
| --- | --- | --- | --- | --- | --- |
| Intervention |  |  |  |  |  |
| Informing the community about how we are performing | Deliver the Marketing and Communications Strategy. Prioritise CDRP/LCJG activities. | Sue Hill/Roselyn Baker | Life in Salford now published monthly to every household. Complete | £120,000 | NI 5, 17 |
|  | Publish regular performance information using various media. | Sue Hill/Roselyn Baker | Quarterly Community Newsletters Complete | Mainstream Budgets | NI 5, 17 |
|  | Develop a reporting mechanism on performance to Community Committees and local groups. | Jim Bonworth CSU | In place September 2009 Complete | Mainstream Budgets | NI 5, 17 |
|  | Support and develop Third Party Reporting Centres | GMP/Shaun Clydesdale | Centres Established Complete | Mainstream Budgets |  |
|  | Improve information sharing and intelligence on hate crime across partners | Shaun Clydesdale/ GMP | Co-Ordination Group now established Complete |  |  |
| Holding annual public meeting with senior officers of the CDRP/LCJG attending to discuss community priorities | Allow and publicise an annual CDRP Executive Group meeting to allow public attendance, where senior officers can be held to account. | Kevin Mulligan Barbara Spicer | Held Annually September Complete | Mainstream Budgets | NI 4 |
| Conducting ongoing public consultations to update priorities in this plan | Conduct local surveys of public concerns. | Roselyn Baker | Annual Places Service. Ongoing Complete | Mainstream Budgets | NI 4 |
| Supporting victims and witnesses, improving their safety and security and helping them through the criminal justice system | Provide emergency accommodation for families escaping domestic violence. | Dawn Redshaw | 14 units in place but a recent needs assessment January 2010 indicates we are 40 places short. Housing group addressing. Sept 2010 |  | NI 15, 32, 34 |
|  | Agree an enhanced protocol for delivering the Sanctuary scheme. | Dawn Redshaw IDAAS/Housing Support | Protocol established Complete | Mainstream Budgets | NI 15, 32, 34 |
|  | Support women victims of DA and all the referrals from MARAC by contact and assistance from a caseworker. | IDAAS/Womens Aid | Domestic abuse caseworkers in place and funded. Complete | £245,000 | NI 15, NI 32, NI 34 |
|  | Enhance the provision of victim support services in hotspot areas by increasing volunteering in these areas. | Victim Support and Witness Service | Extra volunteers recruited and trained Sept 2009 using government grant. Complete | £40,000 H.O Funding | NI 6, |
| Providing better quality information about how offending is being addressed and how offenders are being brought to justice | Through CDRP publications promote and explain the role and function of Salford’s criminal judicial services. | Nigel Preston | Community Newsletters established September 2009 Complete | £18,000 from Local Criminal Justice Funding Home Office. Then to be mainstreamed. | NI 4 |
|  | LCJG to be consulted at the time of the Commissioning process for the Strategic Threat Assessment | Nigel Preston | Conducted Bi annually January and July Complete | Mainstream Budgets |  |
| Promote cohesion and reduce tension in our communities | CDRP and LCJG partners to attend community events promoting their roles. | Don Brown | Process Established with joint representation at public meetings Complete | £3,000 | NI2 NI21 |
|  | Develop hate crime reporting by engaging with our vulnerable communities. | Sean Clydesdale | Reporting Centres Established and staff trained July 2009 Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
| Welcoming and working effectively with people and communities newly arrived to Salford. | Improve engagement with migrant communities (migrant workers and refugees) | Neighbourhood Managers/ Shaun Clydesdale | Rainbow Haven project established to support vulnerable migrants. Welcome Pack developed and distributed. Successful bid to Migration Impact Fund to support community-focused ESOL provision and neighbourhood based integration activities. Complete | Mainstream Budgets | NI 1, 2, 3, 4 |

| Developing a Safer Schools Partnerships Model to build good relationships between the police, children and young people (PSA 14) | Work with schools in Salford to establish more partnerships. | Deborah Keelan | Partnership established in every school Complete | Mainstream Budgets | NI111 |
| --- | --- | --- | --- | --- | --- |
| Working with our older citizens to improve their confidence and address their crime, disorder and antisocial behaviour priorities (PSA 23) | Link in with ‘Wellbeing Strategy’ and implement the Door step crime action plan. | Susan Puffett | Action Plan implemented to be finalised by March 2010 | £1,000 | NI138 |
|  | Establish a ‘crucial crew’ event in each community area to promote partnership activity. | Geoff Akroyd | Every year 6 pupil in Salford now attends a Crucial Crew event each year. Complete | Fire service budget | NI 1, 2, 3, 4 |
| Develop intergenerational work to encourage greater understanding between older and younger residents. | Deliver intergenerational projects. | Pauline Copeland | Partnership work with Age Concern in delivering intergenerational projects is in place. Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
| Ensuring that our neighbourhood teams take account of the concerns of the children and young people in their action planning (PSA 13) | Reflect issues identified by youth forums within community plans. | Neighbourhood Managers | Forums established and plans updated Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
|  | Develop youth forums based and co-terminus within Community Committees. | Lesley Craven | Forums Established Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
| Increasing safety on public transport | Deliver appropriate interventions through Salford GMPTE crime reduction group. | Damian Dallimore | Salford Reducing Crime on Public Transport Group established and delivering reduction programmes. Complete | Mainstream budget | NI 1, 2, 3, 4 |

| Enforcement |
| --- |
| Detecting hate crime and dealing appropriately with offenders | Implement Operation Toast to target perpetrators of hate crime. | Police Hate Crime Unit | Operation Toast funded and implemented Complete | £30,000 | NI 1, 2, 3, 4 |
| Identifying offenders and using interventions and enforcement to stop their anti-social behaviour | LPDGs to problem solve individuals causing concern | Neighbourhood Managers and Inspectors | Problem solving taking place and recorded in LPDG Minutes each month Complete | Mainstream Budgets | NI 21, 27 |
| Using police powers to arrest offenders and bring them to justice | Increase the amount of police enforcement activity, targeted in ASB hot spots via the PDG process. | Neighbourhood Police Inspectors | Operation Brocade established Salford wide Complete | Mainstream Budgets | NI 21, 27 |
| Ensuring with our partners in the Local Criminal Justice Group that we are delivering an effective, transparent and responsive criminal justice system (PSA 24) | Link the LCJG into the CDRP by joint attendance | Peter Lawrence | Joint attendance established Complete | Mainstream Budgets | NI 1, 2, 3, 4 |
|  | Ensure magistrates are in attendance at LPDGs | Peter Lawrence Nigel Preston | All LPDG’s now have Magistrate members Complete | Mainstream Budgets | NI 1, 2, 3, 4 |

| Objective 2: Reducing crime |
| --- |
| Action | How/what activity? | Lead Agency/Officer | Timescales (when achieved by) | Indicative costs | National/ local indicator number |
| Prevention |
| Evaluate the impact of regeneration and redevelopment on crime and disorder STA | Strategic analyst to conduct evaluation in next Strategic Threat Assessment | Strategic Analyst | December 2008 Complete | Mainstream Budgets | N1 15, 20 |
| Providing personal and home safety to individuals and vulnerable groups | Ensuring the effective use of all media opportunities. | Sue Hill | A CDRP Marketing group has been launched in March 2009 to identify and promote media opportunities. Complete | Mainstream Marketing budget | NI 15, 20 |
|  | Identify and involve all partners to provide a target hardening service. | Stephen Kearney | A forensic property marking scheme involving Selecta DNA and Smartwater has been introduced in Winton and Irwell Riverside, this is being further rolled out during 2010 Ongoing | £126,000 from CDRP reward grant | NI 15, 16 |
|  | Deliver target hardening projects to vulnerable groups (e.g. fire risk assessments, distraction burglary projects) and in hot spot locations STA | Geoff Akroyd GMPA team LPDG Chairs | This is currently being delivered via SNAP’s during 2010. Ongoing | £20,000 | NI 16, 33 |
| Use all of our powers, including health and safety legislation and utilise legislation available to all our partners to reduce violent crime |  |  |  |  | NI 15, 20 |
|  | Develop a localised violent crime action plan and set up a thematic sub-group of the PDG. | Roselyn Baker | A violent crime strategy was introduced in September 2008 and an action plan developed. Monitored by the violent crime sub group. Ongoing | £20,000 from TVCP | NI 15, 20 |
|  | Enforce licensing conditions and target offenders | Licensing responsible authorities group | Group is established and work is ongoing. | Mainstream Budgets | NI 15, 20 |

| Reducing first time entrants into the criminal justice system | Target ‘at risk’ children and promote restorative justice approaches and implement new approaches. | Youth Offending Service | All officers trained in Youth Restorative Disposal, we are now a pilot for RJ intervention for all ages for minor offences Aug 2010 | Mainstream Budgets | NI 111 |
| --- | --- | --- | --- | --- | --- |
|  | LPDGs to work with Childrens Services to action plan at risk individuals | Neighbourhood Managers and Inspectors | LPDG practice is established via monthly meetings. Complete | Mainstream Budgets | NI 111 |
| Reducing offending by adults and young people | Implement restorative justice projects | Susan Puffett | RJ has now been introduced and is operating throughout the City. Complete | £3,500 | NI 18, 19, 111 |
|  | To provide diversionary opportunities and signpost support packages for young people in conjunction with LPDGs | Damian Dallimore | Street based teams are on target to deliver 138 sessions in 2009/10; Challenge and support project offers a range of support opportunities for young offenders. April2010 | £100,000 | NI 18, 19, 111 |
| Ensuring that our rehabilitation of offenders strategy addresses the needs of socially excluded adults (PSA 16) | To ensure our PPO and pathways schemes are fit for purpose. | Susan Puffett | The rehabilitation of offender pathways have been evaluated by the partnership and reformed into four pathways including one for PPO. Complete | Mainstream Budgets | NI 18, 19 |
|  | Develop training packages that upskill offenders, equipping them with necessary life skills, e.g.mentoring projects, TWP. | Susan Puffett | Skills for life and Salford college now run courses for ex offenders in the community. Complete | Mainstream Budgets | NI 18, 19 |
|  | Provide a mentoring scheme, ensuring offenders have access to housing and finance provision. | Susan Puffett | Now have 44 mentors provided by Salford Foundation. There is partnership support to increase this to 50. August 2010 | £25,000 10/11 | NI 18, 19 |
| Helping businesses to create business watch schemes | Economic Development Unit and PCSOs to set up business watch schemes. | Joanne Hall | ED continue to support Northbank business watch and Quaywatch. We are currently considering supporting a new radio scheme for Eccles. Aug 2010 | Mainstream Budgets | NI 16 |
| Providing crime prevention and security advice to businesses | Rationalise the crime reduction adviser/economic development surveyor roles. | Police/ Economic development Stephen Kearney | Joint visits are now undertaken with GMP CRA’s and Economic Development. Complete | Mainstream Budgets | NI 16 |
|  | Implement a property marking scheme, pilot in Winton June 09 | Stephen Kearney | The property marking scheme was implemented in Winton with 1,070 households in Eccles marked. Complete | £10,000 | NI 16 |
| Intervention |  |  |  |  |  |
| Advising and protecting victims and witnesses of crime | Promote and support the Witness Outreach Service, Domestic Abuse Advisory Scheme, etc. | Susan Puffett | These services have been publicised in Life in Salford, Community Magazines and at public events such as the garden party. Complete | Mainstream Budgets | NI 32 |
|  | Housing agencies to provide Sanctuary scheme to domestic abuse victims. | Salix City West Homelessness | Scheme Introduced and functioning Complete | Funded by Salix and City West | NI 32 |
| Working with our Local Criminal Justice Group partners to ensure that sanctions against offenders reflect the concerns of our communities | Ensure proper bail conditions and violent offenders to be tagged. | Kevin Mulligan | Conditions now monitored by police/court users group Complete | Mainstream Budgets | NI 4, 5 |
|  | Promote/publicise community payback schemes. | Peter Lawrence | Schemes publicised in Life In Salford, LPDG’s and Public Mettings Complete | Mainstream Budgets | NI 4, 5 |
| Establish An acquisitive crime sub group of the PDG (STA) | PDG to form an acquisitive crime sub group | Stephen Kearney | Group Established October 2008 Complete | Mainstream Budgets | NI 15, 16 |
| Targeting prolific offenders | Review PPO strategy to align with new LAA. |  | Scheme reviewed in January 2009 now being linked into Integrated Offender Management scheme Complete | Mainstream Budgets | NI 30 |
| Commission research in respect of housing tenure across the city STA | Strategic analyst to conduct research as part of STA 2008 | Strategic Analyst | Produced in December 2008 Complete | Mainstream Budgets | NI 15, 16 |
| Improving information sharing and intelligence | Develop Community Intelligence | Don Brown | In January 2009 Partner and Community Together forums have been developed in every Ward. Complete | Mainstream Budgets | NI 4, 5 |
|  | Develop a co-ordinated CCTV strategy for the city. | Don Brown | In August 2009 a computerised GIS system was introduced, a new ‘state of the art’ control room was opened in January 2010 with partnership protocols to access data. Complete | £500, 000 | NI 15, 16 |
| Reducing robbery, burglary and vehicle crime in respect of businesses | Develop the security provisions for vulnerable businesses. | Economic Development Unit. | Between April 2009 and January 2010 236 business security audits undertaken 64 grants awarded amounting to £66K 79 buildings secured Process now in place to maintain action Complete | £66,000. | NI 15, 16 |
|  | Conduct targeted police operations. |  | Ongoing | Mainstream resources | NI 15, 16 |
| Reducing crime against schools and other public buildings | Promote and encourage take up of the Safer Schools Award. | Debbie Keelan | Award scheme in place since May 2009 Complete | £3,000 | NI 15, 16 |
|  | To adopt SBD as a mandatory condition on all L/A new builds/refurbishment schemes. | Urban Vision | Scheme in place Complete | Mainstream Budgets | NI 15, 16 |
|  | Further develop University Campus Watch. | Campus Watch co-ordinator | Campus watch introduced in partnership with University Security and Police. Complete | Mainstream Budgets | NI 15, 16 |
|  | To implement a friends scheme, e.g. friends of Swinton Church. | Neighbourhood Managers and Inspectors | Friends scemes being introduced via LPDG’s and PACT meetings. March 2011 | Mainstream Budgets | NI 15, 16 |
| Evaluate all implemented initiatives and disseminate good practice STA | Strategic Analyst to carry out as part of STA | Strategic Analyst | Takes place in Bi Annual STA’s January & July Complete | Mainstream Budgets | NI 15, 16 |

| Enforcement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Running targeted policing operations against robbery, burglary, vehicle crime and arson |  |  |  |  |  |
|  | Implement a Market Reduction Approach to tackle the onward sale of stolen goods. | Stephen Kearney Insp Errington Ron Pennington | Joint Police/Trading Standards visits taking place. Visits to check for Smartwater marked items to be developed by March 2010 | Mainstream Budgets | NI 16 |
|  | Increase the overall number of detections for domestic burglary, violent crime, vehicle crime, criminal damage and hate crime. | Insp Errington to Update | Year to date (Feb 2010) all detection rates have increased see CDRP monitoring report. Ongoing | Mainstream Budgets | NI 15, 16 |
| Identifying crime hotspots with partnership resources | Undertake directed monthly crime pattern analysis | Partnership analysts | Monthly analyses now produced for PDG Ongoing Complete | Mainstream Budgets | NI 15, 16 |
| Prioritise the top 10 neighbourhood beats as identified in the STA July 2008. | LPDG’s to prepare partnership action plans for beats in their neighbourhoods. | Neighbourhood Inspectors | LPDG action plans now produced and ongoing Complete | Mainstream Budgets | NI 15, 16 |
| Using our trading standards powers to target the stolen goods market | To undertake frequent inspections at dealers premises. | Trading Standards | Joint visits with Police and Trading standards now taking place. Complete | Mainstream Budgets | NI 16 |
| Intervening early to reduce alcohol related violent crime | Develop an alcohol enforcement strategy. | Ron Pennington /Licensing responsible authorities group | Responsible Authorities meetings provide a co ordinated approach to enforcement in licensed premises Complete | Mainstream Budgets | NI 15, NI 39 |
|  | Undertake under age alcohol test purchases. | Trading Standards | Programmed test purchasing exercises carried out on an ongoing basis Complete | Mainstream Budgets | NI 15, NI 39 |
|  | Promote safe and responsible drinking with use of banning orders and alcohol disorder zones where appropriate. | DAAT/police | Ongoing process established via PDG/LPDG’s Complete | Mainstream Budgets | NI 15, NI 39 |
| Develop a violence against women strategy. STA | Produce Strategy and an Implementation Group answerable to the CDRP. | Don Brown | Draft Strategy Prepared by Sub Group to be completed by June 2010 | Mainstream Budgets | NI 15, 32 |
| Running specialised operations to tackle domestic abuse and hate crime | Police targeted operations, DVEC | Supt Wilkinson | Targeted Operations taking place under the supervision of the TCG and PDG Ongoing | Mainstream Budgets | NI 15 |
| Targeting repeat incidents of domestic abuse and hate crime and supporting and protecting victims | All Partners to support the MARAC process and train frontline officers | CSU | MARAC introduced and officers trained, a new common assessment framework is being introduced. Ongoing March 2011 | Mainstream Budgets | NI 15, 32 |
|  | Violent offenders to be electronically tagged | GMP & G4S | System in place Jan 2009 Complete | GMP Budget |  |
|  | Ensure that homes and names are flagged and risk assessed and clearly marked for response. | GMP Supt Anderson Violent Crime Group | Police and partners developing a system August 2010 | Mainstream Budgets | NI 15, 32 |
|  | Continue to pro-actively investigate hate crime | Police hate crime unit | Investigations taking place, led by the police Hate Crime Unit. Ongoing | Mainstream Budgets | NI 1, 15 |

| Objective 3: Effectively tackling anti-social behaviour together with the community |
| --- |
| Action | How/what activity? | Lead Agency/Officer | Timescales (when achieved by) | Indicative costs | National/ local indicator number |
| Prevention |  |  |  |  |  |
| Providing positive activities for young people, particularly in the evenings, at weekends and during the school holidays | Deliver Targeted Youth Support and Integrated Youth Support Services. | Lesley Craven | Ongoing to March 2011 | Mainstream Budgets | NI 17, 57 |
|  | Ensure enforcement and diversionary activities are coordinated through the Brocade steering group. | Damian Dallimore | This activity is now coordinated through the YCAP steering group Complete | Mainstream Budgets | NI 17 |
|  | Evaluate the impact of the Youth Service secondment post and identify funding to extend the post beyond 08/09. | Damian Dallimore | Post funded until March 2011 from ABG and mainstreamed from CSD budget thereafter April2011 | ABG £35,000 | NI 17, 21, 23, 24, 25, 110, 115 |
| Providing detached youth workers in most neighbourhoods across the city to engage with young people | Develop integrated approaches to address youth related issues, e.g. Targeted Youth Support and IYSS. | Lesley Craven | CSD has set up a Team Around the School at each high school in the city, with level 3 youth workers based in high schools to help deliver TYS Complete | Mainstream Budgets | NI 17 |
|  | Examine why youth provision is underused in some hotspots and make recommendations for improvement. | Lesley Craven | Youth task groups are now running in every neighbourhood in Salford, giving young people a say on the type and times of provision in their area Complete | Mainstream Budgets | NI 17 |
| Encouraging responsible behaviour through an Environmental Education and Awareness initiative | Evaluate current response times to reports of environmental crime and set targets for improvement. | Ron Pennington | % of reported incidents of fly tipping responded to within 5 days- 2009/10 Q1 94%, Q2 97%, Q3 93% Current targets are reviewed on an ongoing basis but are considered appropriate. March 2011 | Mainstream Budgets | NI 17, 5 |
|  | Environmental education officers to provide appropriate environmental education programmes across the city. | Envirocrime team Phil Morton | Crucial crew delivered education programme to all junior schools. High school assembly programme implemented. Community events attended throughout year March 2011 | Mainstream Budgets | NI 17, 5 |
|  | Develop the role and function of the Park Rangers Service. | Wayne Priestley with CSU | 10 rangers are in post and fully funded until March 2011. Within the Environment Directorate Business Plan they are tasked with park protection and public engagement including youth diversion activities. March 2011 | ABG £250000 | NI 17, 5 |
|  | Review performance against graffiti clean up targets, including offensive graffiti. Proactively target private properties and persuade owner to pay for grafitti removal | Ron Pennington | % of offensive graffiti responded to within 48 hrs- 2009/10 Q1 96%, Q 2 93%, Q3 94%. % non offensive graffiti responded to within 5 days- 2009/10 Q1 94%, Q2 91%, Q3 94% Agreement reached with two major companies to remove graffiti from their property April 2010 | Self funding | NI 17, 5, 195 |
| Using ‘Secure by Design’ principles to design out anti-social behaviour and criminal damage | SBD principles to be adopted. | Urban Vision | Protocols now in place in respect of planning permission Complete | Mainstream Budgets | NI 17 |
| Addressing the public’s perception of anti-social behaviour | Develop regular comprehensive and robust approaches to monitoring and evaluating ASB intervention and enforcement activity across the city. | David Walsh | Quarterly reports to CDRP Exec Complete | Mainstream Budgets |  |
|  | Set up an interactive intranet webpage to present neighbourhood based ASB statistics for each LPDG | David Walsh | Greater Manchester Police now have this facility on their website. Complete | Mainstream Budgets |  |
|  | Share good practice in tackling ASB across neighbourhoods | Diana Martin | This is now a routine activity within the LPDG process. Complete | Mainstream Budgets |  |
| Encourage the responsible retailing of age restricted goods. | Roll out of the Responsible Retailer scheme | Ron Pennington | Have the bottle to say no campaign now in place Complete | Mainstream Budgets |  |
| Using overt surveillance systems (cctv) to intervene early in incidents of anti-social behaviour | Ensure that incidents of low level ASB are captured and shared with partners through the MASG. | Graham Smith / Warren Carlon | New CCTV Control room is now operational and images are being captured. Complete | Mainstream Budgets |  |
| Promoting responsibility and consideration between all our citizens | Develop new forums to work more closely with all hard to reach groups and hold regular customer involvement sessions promoting the function of the CDRP and the LCJG | David Walsh /LPDGs | Resident forums now in place and annual garden party serviced. DVD produced to promote CDRP activity. Complete | Reward grant £5000 |  |
|  | Integrate ASB issues into the ‘Safer Schools Partnership’ | Julie Cunningham | Each Salford School now has a nominated police liaison officer who deals with any referred ASB issues Complete | Mainstream Budgets |  |
|  | Deliver a safer schools award scheme. | Debbie Keelan | Award scheme in place since May 2009 Complete | Reward Grant £1000 |  |
| Intervention |  |  |  |  |  |
| Providing support for families and children who are involved in anti-social behaviour which affects the broader community | Ensure Assfam use dispersed tenancies when required | Paul Goodwin | In Place Complete | Assfam/Mainstream Budgets |  |
|  | Use family group conferencing to address ASB problems | Paul Goodwin | In Place Complete | Assfam/Mainstream Budgets |  |
|  | Deliver parenting support to families involved in the Assfam project | Paul Goodwin | In Place Complete | Assfam/Mainstream Budgets |  |
| Running test purchasing operations to detect the sale of alcohol to under 18s | Carry out partnership activities with community safety, GMP, Dept. for work / pensions, Customs and Excise, etc. to target underage sales of alcohol | Ron Pennington | Scheme in place and operational Complete | Mainstream Budgets | NI 39 |
| Through the Youth Offending Service, offering an assessment and appropriate intervention to a young person who is at risk of offending | Deliver a Challenge and Support project in Salford | Damian Dallimore / Tom Healy | Project commenced December 08 Complete | £250,000 over 3 years (DCSF funded) | NI 17, 21, 23, 24, 25 |
|  | Examine the use of CAF and extend training to officers across the city | YOS | Training rolled out complete Dec 2010 | Mainstream Budgets |  |
| Offering parenting support to parents of young people identified as behaving in an anti-social manner | Increase the use of parenting contracts / orders issued to parents of young people that are known to be repeat offenders of ASB | John Gill Julie Mackenzie | Process in place and evaluated in Strategic Threat Assessment December 2010. | Mainstream Budgets |  |
|  | Launch the parenting strategy for Salford | Jane Middleton | Strategy Being Developed Sept 2011 | Mainstream Budgets |  |
|  | Offer parenting contracts to parents of young people at the ABA stage of the ASB warning route keeping LPDGs informed | David Walsh | Scheme In Place Complete | Mainstream Budgets |  |
|  | Develop a clear referrals process for parenting support | John Gill | Parenting support officers take referrals from LPDGs and neighbourhood officers. Process Complete | Mainstream Budgets |  |
| Identifying hotspot areas for anti-social behaviour to allow for targeted responses | Commission quarterly analysis to identify seasonal trends in anti social behaviour and predict where and when increases are expected | Damian Dallimore | Process is now done monthly for PDG Complete | Mainstream Budgets | NI 17 |
|  | Coordinate proactive partnership activity to quell any anticipated rise in anti social behaviour, including ASB-focused letter drops, leafleting, poster campaigns, local publicity. | Damian Dallimore | Coordinated activity taking place via SNAPS and Local Neighbourhood Justice Project April2010 | £12,000 Tackling not tolerating fund | NI 17, 21, 23, 24, 25 |
| Identifying potential targets, such as at risk properties or vehicles and rubbish and refuse bins left lying around and swiftly implementing remedial action to prevent arson occurring | Manage SNAP’s operations in key hotspots across the city | Damian Dallimore | SNAP’s process funded until March 2011 | CDRP Reward Grant £50,000 |  |
|  | Coordinate Firefly and Fire Team courses for NEET young people (or those at risk of becoming NEET) | Jeff Akroyd | Scheme in place and funded until March 2011 | CDRP Reward Grant and Fire Service Budget £35000 |  |
| Address bullying behaviour with children. Link it to criminal activity. Encourage children to report bullying behaviours hence the reporting of crime at an early age. | Anti Bullying and domestic abuse policy in every school and college. Sessions and workshops for all years starting in primary school. | Judy Shorrocks. Community Safety Unit. | Schools being visited complete by March 2011 | Mainstream Budgets |  |

| Enforcement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Using tools and powers such as warnings, acceptable behaviour agreements, dispersal orders and antisocial behaviour orders to deal with specific individuals and groups who are behaving anti-socially | Ensure that housing providers and partners use warnings, acceptable behaviour agreements, possession, injunctions, dispersal orders and antisocial behaviour orders against known perpetrators | David Walsh | System in place and functioning Complete | Mainstream Budgets |  |
| Seizing nuisance off road vehicles | Use covert surveillance equipment to monitor off road offenders at hot spot locations | Steve Meaton | System in place via LPDG’s Complete | Mainstream Budgets |  |
|  | Seize vehicles ridden in parks and open spaces where warning signage is erected | Police | Complete | GMP Budget |  |
| Enforcing our alcohol designated places order in those parts of the city affected by alcohol related disorder | Ensure that signage is in place across all hotspot areas of Salford | David Walsh | Complete | £4000 |  |
|  | Carry out test purchase operations in hotspots across the city | Ron Pennington | In Place Complete | Mainstream Budgets |  |
|  | Improve the alcohol warning system | David Walsh | System reviewed and improved Complete | Mainstream Budgets |  |
| Improving detections of offenders and increasing convictions | Identify subjects for further investigation, intervention and ASBO application through internal and external consultation | GMP | Now routine LPDG Process Complete | Mainstream Budgets |  |
|  | Monitor all applications and existing orders – ensure arrests are made and track breaches of orders. | GMP | Now routine LPDG Process Complete | Mainstream Budgets |  |
|  | ASBO coordinators to attend LPDGs to pick up referrals for enforcement action | GMP | Now routine LPDG Process Complete | Mainstream Budgets |  |
|  | Identify potential premises for closure orders | GMP | Now routine LPDG Process Complete | Mainstream Budgets |  |
| Using all our powers to enforce against environmental crime offenders including on the spot penalty notices and overt and covert operations | Review performance against graffiti clean up targets, including offensive graffiti | Ron Pennington | 2009/10 % of offensive graffiti responded to within 48 hrs- Q1 96%, Q 2 93%, Q3 94%. % non offensive graffiti responded to within 5 days- Q1 94%, Q2 91%, Q3 94% Agreement reached with two major companies to remove graffiti from their property April 2010 | Self funding |  |
|  | Evaluate current response times to reports of environmental crime and set targets for improvement. | Ron Pennington | 2009/10 % of reported incidents of fly tipping responded to within 5 days- Q1 94%, Q2 97%, Q3 93% Current targets are reviewed on an ongoing basis but are considered appropriate April 2010 | Mainstream Budgets |  |
|  | Continue partnership working with Salix Homes and ASBO teams to tackle antisocial domestic noise | David Walsh | Routine Partnership Activity Complete | Mainstream Budgets |  |
| Proactively investigating and prosecuting perpetrators of environmental crime such as fly tipping | Deliver environmental crime programme, to include publicity and prosecution efforts with reduction targets for dog fouling, fly-tipping, graffiti, and litter | Phil Morton Ron Pennington | 3500 fpn’s issued for enviro crime offences. 30 succesfull prosecutions for fly tipping. 37% reduction in fly tipping year to date January 2010 March 2011 | Mainstream Budgets |  |
|  | Deliver yearly Grime busters environmental crime programme, to include publicity and prosecution efforts with reduction targets for dog fouling, fly-tipping, graffiti, and litter. | Phil Morton | Joint working with enviro education at crucial crew and other events. All junior schools in city involved March 2011 | Mainstream Budgets |  |
|  | Deliver yearly environmental partnerships programme, to include publicity and prosecution efforts with reduction targets for dog fouling, fly-tipping, graffiti, and litter. | Phil Morton | Partnerships with GMP, NCP ,GMFRS to reduce enviro crime through joint working March 2011 | Mainstream Budgets |  |
| Making full use of our licensing laws, including health and safety legislation, to improve the management of licensed premises | Identify and implement effective actions | Responsible Authorities Licensing Group | Group now meets monthly and monitors all activity Complete | Mainstream Budgets |  |

| Objective 4: Reducing the harm caused by drug and alcohol misuse Drugs |
| --- |
| Action | How/what activity? | Lead Agency/Officer | Timescales (when achieved by) | Indicative costs | National/ local indicator number |
| Prevention |  |  |  |  |  |
| Implement the Drug Interventions Programme (DIP) | Continue processes of Testing on arrest, Required Assessments and engagement in treatment whilst managing 15% reduction in the budget for 2010/2011. | DAAT | Throughout 10/11 | DIP Budget CJIT costs £400,000 | NI 16, 30, 38, 40 DIP KPIs 1,2,3,4 |
| Ensure robust information sharing systems between health services and criminal justice agencies | Cross referencing of PPO and MDT repeat positive drug tests | DAAT/Police | Process established and in place. Complete | Within existing resources | NI 16, 18, 30, 38 |
|  | Ensure data sharing between DAAT and CDRP to inform Strategic Treat Assessment | DAAT/CSU | Established and reported on in STA July 2009 Complete | Within existing resources | NI 16, 18, 30. 38 |

| Intervention |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Identify and target problematic drug users with repeat positive drug test histories. | Establish number of PDUs with 2 or more positive drug tests that are unknown to treatment service. Establish number of repeat positive testers that have had a treatment episode. | DAAT | This process has now been mainstreamed within the service’s perf romance management framework Complete | Within existing resources | NI 16, 30, 38, 40 |
| Make full use of criminal justice sanctions and interventions. | Ensure offenders are identified for Restriction on Bail, DIP Conditional Cautions and Drug Rehabilitation requirements (DRR) and PPO | Police/Probation | Throughout 10/11 | Within existing resources. | NI 16, 18, 30, 38, 40 |
| Identify and target drug using re-offenders with intervention programmes | Structured programme available at Aspire including abstinence and recovery pathway | DAAT | Provision has been reviewed and contracts group is now remodelling service to incorporate an abstinence/recovery pathway March 2011 | Within existing resources | NI 40 |
|  | Choose Change project established for AUR/under 12 month sentences prisoners | Manchester Prison | Established and funded until March 2011 | DIP budget £25,000 | NI 30, 38 |
| Dedicated Drug Court (DDC) established to deal effectively with drug misusing offenders committing crime to fund their drug use. | Board established to oversee activity | Community Justice Initiative | Established in July 2009 Complete | Support monies identified by HMCS Crime and Enforcement Directorate | NI 16, 18, 30, 38, 40 |
| Develop enhanced resettlement and accommodation services. | Develop a combined prison discharge resettlement / homeless advice service with combined links to homeless none priority cases located at Salford Probation | Probation Service | Tender exercise complete, service to be in place by May 2011 | Supporting People Budget | NI 18, 141, 143, 156 |
| Ensure Employment, Training and Education providers are engaging with drug using offenders. | Sustain P2W funding for a support into work grant. | DAAT | Throughout 10/11 | PTB £10,500 | NI 144, 152 |
|  | Maintain ETE provision within Probation OMU 1 | DAAT | Due to DIP budget cut this project has been de – commissioned from April 2010-01-22 Complete | DIP Budget £23,000 10/11 £0.00 | NI 144, 152 |

| Enforcement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Target supply of controlled drugs. | Develop community intelligence to inform planned operations | Police | Processes in place throughout 10/11 | Within existing resources | NI 21,24, 27, 42 |
| Use appropriate enforcement measures against premises that are being used for drug use, supply or production. | Develop intelligence to target cannabis farms. | Police | Intelligence systems developed enforcement action throughout 10/11 | Within existing resources | NI 21, 24, 27, 42 |

| Objective 4: Reducing the harm caused by drug and alcohol misuse Alcohol |
| --- |
| Action | How/what activity? | Lead Agency/Officer | Timescales (when achieved by) | Indicative costs | National/ local indicator number |
| Prevention |  |  |  |  |  |
| Educating young people about sensible drinking and the dangers of drugs | Implement Healthy Schools Initiative | Children’s Services | Healthy Schools Initiative implemented 2008 This is being further developed in the C&YP Plan and the the Alcohol Harm Reduction Strategy 2010/20 Complete | Mainstream Budgets | NI 39 |
| Strengthen support for people that frequently abuse alcohol | Develop a coordinated response taking referrals from A&E | Melanie Walters | The project to form a Hospital Assertive Alcohol Team has been completed. A business case is being raised with the PCT to secure funding. May 2010 | Mainstream Budgets | NI 39 |
| Developing improved consultation mechanisms | Establish an Alcohol Treatment Group and Alcohol Reference Group | DAAT | Established October 2009 Complete | Mainstream Budgets | NI 39 |
| Establishing data collection and sharing systems between the Emergency Department and Crime and Disorder Reduction Partnership | Establish assault data collection systems in the Emergency Department | Salford Royal Foundation Trust | In January 2010 we signed up for Traumatic Injury Information Group, the database is in place. Complete | Salford Royal NHS Foundation Trust Cost Neutral | NIs 15, 20, 32, 39, 41 |
|  | Agree protocols for sharing information with CDRP | Salford Royal Foundation Trust | To be completed by Sept 2010 Andrew MacDonald | Within existing resources | NIs 15, 20, 32, 39, 41 |
|  | Ensure information is utilised to plan prevention and enforcement activity | Crime & Disorder Reduction Partnership | Analyses systems to be developed March 2011 | Within existing resources | NIs 15, 20, 32, 39, 41 |
| Improving the use of the alcohol marker in police data | Identify good practice in other areas of the Country | Greater Manchester Police | System adopted in June 2009 whereby crime reporter is asked whether alcohol was a factor and is endorsed on the crime report Complete | Within existing resources | NIs 15, 20, 32, 39, 41 |
|  | Work with colleagues in Greater Manchester to identify how this can be implemented force wide | DAAT | See above June 2009 Complete | Within existing resources | NIs 15, 20, 32, 39, 41 |
| Conducting further local analysis to improve understanding of the relationship between alcohol sales and crime and anti-social behaviour | Map the locations of alcohol-related crimes and incidents, and those likely to be associated with alcohol to the locations of licensed premises | Salford City Council – Chief Executive’s | Systems in place, takes place quarterly reported to PDG Complete | Within existing resources | NIs 15, 20, 32, 39, 41 |
|  | Conduct a further trial of marking of products in off-licenses so the retailer can be identified | Greater Manchester Police | Trial unsuccessful as retailers unlikely to knowingly sell to underage when they know which product is marked. Discontinued. Complete | Mainstream Budgets | NIs 15, 20, 32, 39, 41 |
|  | Use data on locations of anti-social behaviour and reported crimes to analyse the impact of enforcement campaigns and work with alcohol retailers | Salford City Council – Chief Executive’s | Analyses now provided quarterly to PDG to inform enforcement activity Complete | Within existing resources | NIs 15, 20, 32, 39, 41 |
| Improving data collection to ensure that a detailed picture of the extent and nature of alcohol-related crime in the City is available, so that enforcement and prevention activity can be planned accordingly | Increase use of alcohol marker | GMPDave Wilkinson | Alcohol marker now endorsed on crime reports and incident reports to enable analyses to take place. Complete | Mainstream Budgets | NIs 15, 20, 32, 39, 41 |
| Working with licensees to reduce crime and anti-social behaviour | Provide crime prevention advice to licensed premises | Greater Manchester Police Ron Pennington | Advice provided by Crime Reduction Officers and Enviromental Health Officers as part of the Violence at Work initiative June 2009 Complete | Within existing resources | Nis 15, 20, 32, 39, 41 |
|  | Establish system to notify licensed premises when there are particular risks to their security | Greater Manchester Police Ron Pennington | Q4/2008-9 Now routinely conducted by Neighbourhood Inspectors Complete | Within Existing Resources |  |
|  | Establish Radio-Net systems for licensed premises in hotspots for alcohol-related crime and disorder | Greater Manchester Police | Q4/2009-10 | Up to £1,200 required per area, funding to be identified | Nis 15, 20, 32, 39, 41 |

| Intervention |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Further developing the criminal justice alcohol pathway | Evaluate the effectiveness of criminal justice alcohol interventions | DAAT | Research presented to CDRP/DAAT system specs redesigned Complete | £10,000 IDENTIFIED: NOMS/CDRP | NIs 15, 20, 32, 39, 41 |
|  | Sustain funding for Criminal Justice Alcohol Workers | Crime & Disorder Reduction Partnership | Funded by CDRP until March 2011To be funded by the PCT from April 2011 | £75,000 CDRP Reward Grant | NIs 15, 20, 32, 39, 41 |
|  | Identify mechanisms through which alcohol interventions can be provided to those not required to attend court | DAAT | Now contained in the respecification of the service and offer of the new NHS alcohol gateway service Complete | Within existing resources | NIs 15, 20, 32, 39, 41 |
|  | Ensure prisons are aware of local treatment pathways and make appropriate referrals | DAAT | A universal alcohol treatment pathway and criminal justice pathway is in development following Dept of Health Guidance. March 2011 | Within existing resources | NIs 15, 20, 32, 39, 41 |
|  | Develop alcohol worker input with Specialist Domestic Violence Court cases | DAAT | This is now part of the Job Description of these workers Complete | Within existing resources | NI 32 |
| Increasing the capacity and capability of criminal justice agencies to provide alcohol interventions | Train Probation staff to provide screening, brief interventions and initial assessment for Alcohol Treatment Requirements | DAAT | First tranche - bespoke E-Learning Probation / Police (including OMU) and YOT staff. Training all Salford staff in city wide training plan April 2011 | Within existing resources | NIs 15, 20, 32, 39, 41 |
|  | Extend the range of alcohol programmes offered through Probation for offenders drinking at hazardous and harmful levels | Probation | A Pilot of the COVAID programme commenced in January 2010 – this will be evaluated – if successful funding for an accredited programme via NOMS. Sept 2011 | Resource implications to be identified when Low Intensity Alcohol Programme has been accredited by NOMS | NIs 15, 20, 32, 39, 41 |
|  | Ensure that services working with offenders are able to make appropriate referrals into alcohol treatment | DAAT | Alcohol Treatment Group and the DAAT Criminal Justice Group Developing Pathways. March 2011 | Within existing resources | NIs 15, 20, 32, 39, 41 |

| Enforcement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Utilising new and existing powers to take action against licensed premises which contribute to crime, disorder and anti-social behaviour | Establish systems to monitor sales to drunks by licensed premises and take action where appropriate | Greater Manchester Police | March 2011 | £1,000 per month IDENTIFIED FROM POLICE BUDGET | NIs 15, 20, 32, 39, 41 |
|  | Utilise Police powers under the Violent Crime Reduction Act to fast track action against premises associated with high levels of violent crime | Greater Manchester Police | Ongoing March 2011 | Within existing resources | NIs 15, 20, 32, 39, 41 |
| Taking effective enforcement action against repeatedly offending licensed premises |  | Trading Standards/ police | Ongoing March 2011 | Within existing resources |  |
| Enforcing the alcohol exclusion zone across the city |  | GMP | Ongoing March 2011 | Within existing resources |  |
| Closing licensed premises associated with alcohol and drug related offences |  | Responsible Authorities Licensing Group | Ongoing March 2011 | Within existing resources |  |
| Using our full range of powers to enforce against alcohol misuse |  | Trading Standards/ police | Ongoing March 2011 | Within existing resources |  |