REPORT OF STRATEGIC DIRECTOR FOR ENVIRONMENT AND COMMUNITY SAFETY

TO:		Neighbourhoods Scrutiny Committee

DATE:		21 February 2011

TITLE:	Development of the Salford Community Safety Strategy 2011 - 14

EXECUTIVE SUMMARY:

This report advises Scrutiny Committee of the development of the new three year Salford Community Safety Strategy and invites comments on the strategy.

RECOMMENDATIONS:

That Scrutiny Committee provides comments on the draft community safety strategy during this current consultation period.

BACKGROUND DOCUMENTS:

Delivering Safer Communities: a guide to effective partnership working – guidance for Crime and Disorder Reduction Partnerships (CDRPs) and Community Safety Partnerships, Home Office, 2007.

Policing in the 21st Century: Reconnecting police and the people, Home Office, 2010

Salford Community Safety Strategy 2008 – 2011, Salford Community Safety Partnership

Salford Strategic Assessment 2010 – 2011, GMAC

EQUALITY IMPACT ASSESSMENT AND IMPLICATIONS:

The current strategy has an equality impact assessment which is under review and will form the basis of the assessment for the new strategy.

# ASSESSMENT OF RISK: LOW

LEGAL IMPLICATIONS:

It is a statutory requirement for Community Safety Partnerships to produce a three year strategy to tackle crime and disorder in their area.

FINANCIAL IMPLICATIONS:

Current thinking is that the strategy will be available online as a pdf file and not as hard copy which will save on printing and distribution costs.  Further consideration needs to be given to publishing a summary strategy for the public as is required.

# CONTACT OFFICER:	Roselyn Baker, Policy and Improvement Team,

# Customer and Support Services Directorate

# Salford City Council

# TEL. NO.	0161 793 3173

# EMAIL:	Roselyn.Baker@salford.gov.uk

WARD(S) TO WHICH REPORT RELATES:  All

DETAILS:

1.	Statutory framework

1.1	The Home Office guidance ‘Delivering Safer Communities: a guide to effective partnership working – guidance for Crime and Disorder Reduction Partnerships (CDRPs) and Community Safety Partnerships’ lays out the statutory requirements for CDRPs (as was) in relation to setting a crime and disorder reduction strategy (plan).

1.2	In July 2010 the Government published the consultation document, ‘Policing in the 21st Century: Reconnecting police and the people’ which included consultation on some changes to the statutory requirements of Community Safety Partnerships (CSPs).  However, the statutory requirements to produce strategic assessments (crime and disorder analysis) and partnership plans (community safety strategy) remain.  The requirements are:

- Develop a three year plan, which will be revised annually to reflect new priorities emerging from strategic assessments

- The plan should contain a strategy for tackling the identified crime and disorder in the area

- The plan will contain the priorities identified through the strategic assessment, including the community priorities based on consultation

- The plan has to contain information about the role of each partner in supporting delivery of the priorities and how this will be resourced

- The plan should contain information about the way in which performance against priorities will be measured

- The plan will also contain information about the way in which the partnership will engage with their communities

2	Development of the strategy

2.1	The 2008 – 2011 Salford Community Safety Strategy comes to an end on 31 March 2011 and the new strategy is required to come into effect from 1 April 2011.  The strategy will be underpinned by a detailed delivery/action plan that will identify all of the partnership activity that will deliver our agreed outcomes.  This delivery plan will be reviewed and updated on a six monthly basis in line with the GMAC strategic threat assessment process, with continued performance being driven by the Partnership Delivery Group.  The Community Safety Partnership Executive Group will continue to be informed of progress on a quarterly basis.

2.2	The following timetable shows how the strategy has been developed so far and the consultation process that is currently underway.

| Timetable for the development of the 2011 – 2014 Salford Community Safety Strategy |
| --- |
| Action: | By: |
| Strategic threat assessment commissioned | March 2010 |
| Strategic threat assessment ratified at Community Safety Partnership Executive Group – strategic aims, objectives and emerging priorities identified | August 2010 |
| Workshop where officers develop priorities and activity that address the strategic objectives | 12 January |
| Public consultation on the emerging priorities through Life in Salford magazine and the internet | 17 January |
| Internal communications about the strategy - home page council intranet + intranets of partners | 20 – 21 January |
| Drafting of strategy | 17 – 27 January |
| Draft strategy to community safety partners for comment | 28 January – end February |
| Draft strategy to Community Safety Partnership Executive Group for comment | 3 February |
| Draft strategy to all councillors for comment | 4 – 18 February |
| Draft strategy to Scrutiny Committee for comment | 21 February |
| Draft strategy to Cabinet Briefing for comment | 22 February |
| Draft strategy to Neighbourhood Community Committee Chairs + Deputies meeting for comment | 23 February |
| Development of delivery plan (aligned to business planning process/budget setting) | Mid February to end March |
| Strategy signed off by Lead Member for Community Safety | By 9 March |
| Approved at full council meeting (statutory requirement) | 16 March |
| Launch at Community Safety Partnership Executive Group | 30 March |
| Produce summary strategy as a public document | April |