CENTRAL SALFORD INTERNATIONAL COMPETITION TO DEVELOP A VISION AND REGENERATION FRAMEWORK – UPDATE ON APPOINTMENT OF THE SUCCESSFUL CONSORTIA

## Background

An International Competition to appoint consultants to undertake the development of the Vision and Regeneration Framework for Central Salford on behalf of the Central Salford Shadow Urban Regeneration Company (URC) Board was launched in April 2004. On July 29th 2004 the Panel of Judges shortlisted 5 internationally experienced consortia of architects, urban designers and economists led by:

- Alsop architects

- Arup Consultants

- Locum Consultants

- S333 architects

- KCAP architects

Following receipt of the shortlisted consortia’s 2nd stage submissions, Panel interviews took place on November 12th 2004. In addition the Panel took into account:

- Lowry Outlet Exhibition /focus group feedback

- Community Network research  undertaken with residents

Outcome

The Panel unanimously agreed to appoint a consortia led by Locum, the key members and experience of which are :

Locum Destination Consulting – Locum's regeneration services focus on creating successful destinations for visitors, residents and investors and developing realistic strategies for transformation which build on and enhance local identity and 'sense of place'. This expertise has recently been deployed in SalfordLondon, Gateshead, Liverpool, Sheffield, Glasgow, Plymouth, Swansea and Cardiff.

Toronto-based Urban Strategies Inc. offers a range of planning and urban design services to clients around the world. The company brings a robust, holistic, and consensus-building approach to complex urban development projects. Recent clients include the cities of Ottawa, Toronto, New York, Detroit, Manchester, Liverpool and Sheffield. Urban Strategies have a strong local knowledge and track record – they undertook the regeneration framework for New East Manchester, Central Salford’s sister URC, and assisted Manchester City Council with the plan to rebuild the City Centre after the IRA Bomb in 1996.

Massimiliano Fuksas Architetto is a major international architecture practice with a record of delivering acclaimed buildings all over the world. Recent works include ZEIL shopping centre in Frankfurt; Eindhoven city centre masterplan; Ferrari headquarters in Maranello; the new Italian Congress Centre in Rome; Europark in Austria; Italian Space Agency Headquarters in Rome; the Peace Centre in Jaffa / Israel; the International Trade Centre in Shanghai; and the new trade fair in Milan. This will be the first time Fuksas has worked in the UK.

The consortium also includes several experts to address specific challenges faced by Central Salford.

Professor Stuart Gulliver of the University of Glasgow is an authority on urban regeneration and has been closely involved with the transformation of Glasgow.

Native Land brings vital development management expertise.

Artscape specialises in arts-driven, community-based urban renewal.

Tenon Techlocate are specialist inward investment advisors.

## Outline timetable for the development of the Vision and Regeneration Framework

The indicative timetable for the commission is as follows:

| Milestone | Date |
| --- | --- |
| Approval of appointment by SCC Lead Member | November 15th 2004 |
| 1st day in Salford for consortia | November 29th 2004 |
| First stakeholder consultations | December 2004 /January 2005 |
| Vision and Regeneration Framework draft produced | April 2005 |
| Consultation on draft Vision and Regeneration Framework | May - September 2005 |
| Finalisation of Vision and Regeneration Framework | September 2005 |
| Development of Implementation Plan for Vision and Regeneration Framework | September - November 2005 |

Stakeholder consultation and community engagement

During the first phase of their work, either side of Christmas/New Year, the consultants will spend time reaching an understanding of all the work currently being undertaken to regenerate Salford. This will involve desk based research and interviews with a range of stakeholders, including Members, statutory/voluntary and community partners.

In addition at a very early stage the consultants will develop an action plan for involving residents and community /voluntary representatives throughout the process of development of the Vision and Regeneration Framework.

18.11.04