4. AN AREA WHERE CHILDREN AND YOUNG PEOPLE ARE VALUED

| Aim: Develop services for 0-5 year olds |
| --- |
| Ref. | ACTION | OUTCOME/ MEASURES OF SUCCESS | TIMESCALE | RESOURCES/ FUNDING | PARTNERS (Lead in bold) | COMMENTS |
| 4.1 | Develop provision of family support service. | Family support service model being delivered. | By March 2004. | Children’s Fund. Mainstream funding. | Children’s Fund Sure Start Early Years |  |
| 4.2 | Implement Sure Start Wave 5 plan. | Plan implemented. | By March 2004. | Sure Start. | Sure Start Other providers to be determined. |  |
| Aim: Develop services for young people |
| 4.3 | Deliver SAYO and SPARKY programmes. | Full SAYO/SPARKY programmes delivered. | On-going. | SAYO – NRF SAPRKY – current funding package | SAYO SPARKY |  |
| 4.4 | Develop outreach youth work. | Outreach youth work being carried out across the area. | By July 2004. | Mainstream funding. Youth Action Key Fund. | Youth Service |  |
| 4.5 | Establish Seedley and Langworthy Youth Forum. | Forum established. | By April 2004. |  |  |  |
| 4.6 | Develop plans for future of Salford Lads and Girls Club. | Plans developed. | By May 2004 | Major sources of funding to be identified for: Roof repairs (Heritage Lottery Fund possible). | Salford Lads and Girls Club Management Committee Leslie Holmes SAYO | See section 2.7 |
| Ref. | ACTION | OUTCOME/ MEASURES OF SUCCESS | TIMESCALE | RESOURCES/ FUNDING | PARTNERS (Lead in bold) | COMMENTS |
| 4.7 | Stowell Field Project. |  |  |  |  | See section 2.8 |
| Aim: Access to health services for young people |
| 4.8 | Improve access to health services for young people. | Strategy agreed. Action programme implemented. | By April 2004. By August 2004. | Within existing budgets. | PCT Youth Service Neighbourhood Co-ordinator | See section 1 |