5. AN INCLUSIVE AREA WITH STRONGER COMMUNITIES

| Aim: To increase community participation and involvement |
| --- |
| Ref. | ACTION | OUTCOME/ MEASURES OF SUCCESS | TIMESCALE | RESOURCES/ FUNDING | PARTNERS (Lead in bold) | COMMENTS |
| 5.1 | Produce joint Tenant Participation /Community Development Worker strategy. | Strategy implemented. | By February 2004. | Within existing budgets. | Tenant Participation Community Development Worker |  |
| 5.2 | Implement Street Rep/Participation and Advocacy to Tenants on Housing Service (PATHS) model. | Street Rep or PATHS model implemented. | By July 2004. |  | Tenant Participation Community Development Worker |  |
| 5.3 | Develop Cornerstone Transitional board to become a fully operational board. | Cornerstone fully operational board in place. |  |  |  |  |
| 5.4 | Increase capacity of local groups to participate in local decision making. | Evidence of more groups participating in local decision making. | By October 2004. | Within existing budgets. | Neighbourhood Co-ordinator Community Network Community Development Worker Tenant Participation Local Elected Members |  |
| Aim: Increase community activity |
| Ref. | ACTION | OUTCOME/ MEASURES OF SUCCESS | TIMESCALE | RESOURCES/ FUNDING | PARTNERS (Lead in bold) | COMMENTS |
| 5.5 | Develop usage of new community room at Ordsall Neighbourhood Office. | Targets to be agreed by Steering Group | By August 2004 | Within existing budgets | Neighbourhood Office Steering Group |  |
| 5.6 | Open Ordsall Community Café. | Café Open. |  | Various: NOF (Fair share) Ordsall Community Committee | Ordsall Community Café Management Committee |  |
| 5.7 | Develop potential community use of Salford Lads and Girls Club. | New groups using club. | October 2004. | Various | Salford Lads and Girls Club Management Committee | See section 2.7 See section 4.6 |
| 5.8 | Develop support of tenant association/residents groups in Clarendon/Precinct area. | Support identified and available. | By January 2004. | Within existing funding. Community Committee | Neighbourhood Co-ordinator Tenant Participation Community Development Worker |  |
| 5.9 | Develop communication between Seedley and Langworthy Partnership Board and local people. | Evidence of developed communication mechanisms. | By April 2004. |  |  |  |
| 5.10 | Evaluate Seedley and Langworthy in Bloom. | Evaluation report produced Learning offered to other areas. | By February 2004. | Within existing budgets. | Community Regen Co-ordinator. |  |

# Also see Strengthening the Communities Action Plan (Seedley and Langworthy)