6. AN ECONOMICALLY PROSPEROUS AREA

| Aim: To maximise the employment opportunities for local people |
| --- |
| Ref. | ACTION | OUTCOME/ MEASURES OF SUCCESS | TIMESCALE | RESOURCES/ FUNDING | PARTNERS (Lead in bold) | COMMENTS |
| 6.1 | Exploit employment opportunities in the area (Lowry Designer Outlet, Regent Road Retail Park, Quays Businesses). | Joint survey with Jobcentre Plus to identify local people’s needs and Jobshop Plus targets. Development of Learn Direct Suite. Employer Liaison Officer in post to identify staffing needs and match. | October 2003– January 2004 January 2004 January 2004 | Mainstream | Jobshop Plus (Employment & Regeneration Partnership) |  |
| 6.2 | Implement/develop Salford Local Link Project. | To improve access to jobs within the area. | September 2003 – March 2004 | GMPTE | Salford Community Transport. |  |
| 6.3 | Provide ongoing opportunities for local people to access future Jobs Fairs in the city. | Instigated affective advertising/media campaigns to publicise events; Convenient and affordable transport/childcare arrangements in place to support events. | To be determined. | ERDF Objective 2 ESF SRB 5 City Council (in place) | Salford Employment Charter and Construction Partnership Economic Development Team (City of Salford) |  |
| Ref. | ACTION | OUTCOME/ MEASURES OF SUCCESS | TIMESCALE | RESOURCES/ FUNDING | PARTNERS (Lead in bold) | COMMENTS |
| 6.3 | continued |  |  |  | Employment and Regeneration Partnership (Manchester Enterprises) Employment Service. |  |
| 6.4 | Work in partnership with developer at Shopping City to maximise training and employment opportunities |  |  |  |  |  |
| Aim: To support businesses in the area |
| 6.5 | Review Quaywatch Scheme | Opportunities to extend the commercial and security benefits of the existing scheme into adjoining commercial area explored. | On-going | To be determined. Quaywatch to be self-sustaining in longer term. Possible Neighbourhood Renewal Fund. | Salford Community Safety Unit GMP |  |
| 6.6 | Development Community Caretaker pilot programme in Langworthy |  |  |  |  |  |
| Ref. | ACTION | OUTCOME/ MEASURES OF SUCCESS | TIMESCALE | RESOURCES/ FUNDING | PARTNERS (Lead in bold) | COMMENTS |
| 6.7 | Provide targeted business support to local retailers/businesses affected by physical improvements to Ordsall District Shopping Centre. | Existing jobs, businesses, shopping provision and other services safeguarded for the benefit of the local community and other visitors. | On-going | Mainstream. | Economic Development Team (City of Salford) Business Liaison Team (City of Salford) Salford Hundred Venture. |  |
| Aim: To encourage investment in the area |
| 6.8 | Target customer contact and shared service centres to invest in the area. | Global marketing through offices in the US and Taiwan, mail shots and promotion at trade fairs to encourage companies to invest. | 2003-2004 | Mainstream | MIDAS Business Liaison Team. |  |
| 6.9 | Explore branding opportunities for Ordsall/Langworthy area. | Branding/identity agreed. | By Septmber 2004 | Existing budgets. | Economic Development Marketing function Salford Partnership. | Tie in with Manchester Left Bank visual identity proposal. See section 7.8 |
| 6.10 | Deliver ELECT action plan (Seedley and Langworthy) | Action plan implemented. | On-going. | Bid to ERDF (Objective 2) |  | See ELECT action plan. |