## Sheet1
Cost | Scheme Name | Original | Cap | Paid | Start | Start | Start | Out to | Start | Finish | Paid | Forecast |  |  | Total | Comments
Code |  | Cost | Prog | to-date | Prelim' | Consult - | Detailed | Quotation | on Site | on Site | to | Spend |  |  | Spend
|  | Estimate | 10/11 | in 10/11 | Design | ation | Design |  |  |  | 2010-03-01 | 10/11 | 11/12 | Beyond
1. Major Highway Schemes
D00003 | Cadishead Way, Stage 1 |  |  | 0 | - | - | - | - | 1991-01-01 | 1992-03-01 | 9463 |  | 0 | 75 | 9538 | Scheme complete
D00004 | Cadishead Way, Stage 2 |  | 665 | 35 | - | - | - | - | 2004-02-04 | 2005-09-01 | 17348 | 665 | 0 | 0 | 18013 | Scheme complete
D00005 | Trinity Way, Stage 3 |  | 55 | 1 | - | - | - | - | 2001-02-01 | 2004-11-04 | 27569 | 55 | 0 | 0 | 27624 | Scheme complete
D00008 | A580 Exceptional Maintenance Scheme |  | 589 | 90 |  |  |  |  | 2011-01-01 | 2011-03-01 | 0 | 589 | 0 | 0 | 589 | Ring-fenced funding to be claimed via S38
D00009 | Quays Loop Road |  | 650 | 372 | 2010-01-01 | 2010-05-01 | 2010-05-01 | 2010-05-01 | 2010-07-01 | 2010-11-01 | 0 | 650 | 0 | 0 | 650 | On-site
| Sub-Total |  | 1959 | 498 | [6 empty] | 54380 | 1959 | 0 | 75 | 56414
2. Local Safety Schemes
D00101 | Anti-skid Surfacing Programme |  |  | 0 | - | - | - | - | 2010-04-01 | 2010-04-01 | 0 | 0 | 0 | 50 | 50
D00103 | Accident Investigation |  |  | 2 | - | - | - | - | 2010-04-01 | 2011-04-01 | 0 | 4 | 15 | 15 | 34 | On-going Programme - not used yet
D00104 | White Lining Programme |  |  | 1 | - | - | - | - | 2006-04-01 | 2010-03-01 | 0 | 1 | 0 | 15 | 16 | On-going programme
D00142 | B5229 Monton Centre Scheme |  |  | 1 | 2004-07-01 | 2005-08-01 | 2006-02-01 | 2006-05-01 | 2007-08-01 | 2008-07-01 | 356 | 1 | 0 | 0 | 357 | Complete
D00148 | A6 Chorley Road Route Scheme |  |  | 1 | 2006-05-01 | 2006-06-01 | 2007-06-01 | 2007-10-01 | 2008-01-01 | 2008-09-01 | 287 | 1 | 0 | 0 | 288 | Scheme complete
D00150 | Silver Street Area, Irlam, Consultation |  |  | 1 | 2006-04-01 | 2006-06-01 | 2006-11-01 | 2008-01-01 | 2009-01-01 | 2009-04-01 | 247 | 1 | 0 | 0 | 248 | Complete - late modifications
D00183 | Station Rd/Bolton Rd Ped'n Facilities |  |  | 0 | 2006-05-01 | 2006-08-01 | 2007-01-01 | 2007-07-01 | 2007-10-01 | 2008-10-01 | 991 | 0 | 0 | 0 | 991 | Complete - settlement of contractor a/c
D00186 | A666 / M60 J'n Cyclist Awareness |  |  | 0 | 2006-05-01: 2009-04-01; 2008-10-01: 2010-08-01 | 0 | 0 | 35 | 0 | 35 | Scheme deferred pending QBC works
D00202 | Trafford Rd/Quays Junction Signals |  |  | 0 |  |  | 2007-09-01 | 2007-11-01 | 2008-03-01 | 2008-09-01 | 244 | 0 | 0 | 0 | 244 | HS final a/c submitted
D00205 | A580 East Lancs Rd Speed Limit Reduction | 21 |  | 1 |  | 2007-04-01 | 2008-07-01 | 2008-09-01 | 2009-02-01 | 2010-03-01 | 2 | 19 | 0 | 0 | 21 | Complete
D00207 | Cavendish Rd / Bradford Rd Traffic Calming |  |  | 0 | - | - | - | - | 2007-11-01 | 2008-01-01 | 91 | 0 | 0 | 0 | 91 | Complete
D00208 | A6 Broad Street / Irlams O'th Height |  | 15 | 7 | n/a | n/a | 2007-10-01 | 2007-12-01 | 2008-01-01 | 2008-04-01 | 57 | 7 | 0 | 0 | 64 | Complete
D00209 | Leigh Road / Ellenbrook Road Junction Improvement | 50 | 30 | 0 | 2010-08-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | Apl-11 | 2011-05-01 | 3 | 0 | 40 | 0 | 43 | Commenced feasibility design
D00210 | A575 Walkden Road Pedestrian Improvements | 80 |  | 4 | 2009-01-01 | 2009-02-01 | 2009-03-01 | Apl09 | 2010-06-01 | 2010-07-01 | 215 | 4 | 0 | 0 | 219 | Complete
D00211 | Liverpool Road, Irlam, Pedestrian Improvements | 80 | 100 | 2 | 2009-04-01 | 2009-06-01 | 2010-08-01 | 2010-09-01 | Apl-11 | 2011-06-01 | 3 | 2 | 85 | 0 | 90 | Detailed Design
D00212 | A666 Bolton Road (Rivington Crescent) Ped Facilities | 15 |  | 0 | 2008-09-01 | 2008-12-01 | 2009-01-01 | 2009-01-01 | 2009-05-01 | 2009-05-01 | 16 | 0 | 0 | 0 | 16 | Complete
D00213 | Leicester Road Pedestrian Improvements |  |  | 24 | 2009-05-01 | 2010-08-01 | Apl-11 | 2011-05-01 | 2011-07-01 | 2011-09-01 | 8 | 24 | 108 | 0 | 140 | Consultation progressing
D00214 | School 20mph Zones |  | 80 | 3 | 2008-12-01 | Apl09 | 2010-08-01 | 2010-09-01 | 2011-01-01 | 2011-03-01 | 13 | 90 | 60 | 0 | 163 | Awaiting Approval
D00215 | Safer Routes to Schools |  | 60 | 2 | 2009-03-01 | 2010-09-01 | 2010-10-01 | 2011-01-01 | 2011-03-01 | 2011-04-01 | 37 | 50 | 130 | 0 | 217 | Awaiting approval N.O take report in December
D00216 | Newearth Rd / Ellenbrook Rd Mini-Roundabout |  | 60 | 6 | 2009-05-01 | 2009-07-01 | 2009-11-01 | 2010-12-01 | 2011-03-01 | Apl-11 | 11 | 30 | 80 | 0 | 121 | Detailed Design
D00217 | A666 Bolton Rd (Agecroft Rd - Irlams O'th Ht) Ped Fac |  |  | 33 | 2009-04-01 | 2009-08-01 | 2009-12-01 | 2009-11-01 | 2010-02-01 | 2010-03-01 | 53 | 8 | 0 | 0 | 61 | Complete
D00218 | Hilton Lane Traffic Calming Refurbishment | 80 |  | 0 | 2011-03-01: 2010-07-01; 2011-04-01: 2010-11-01 | 0 | 80 | 0 | 0 | 80 | On Site
| Sub-Total |  | 345 | 88 | [6 empty] | 2634 | 322 | 553 | 80 | 3589
3. Bridge Assessment and Strengthening
D00501 | Bridges general |  | 10 | 10 | - | - | - | - | 2006-04-01 | 2010-03-01 | 0 | 15 | 10 | 10 | 35 | Various Small Works -monies spent
D00503 | Subways |  |  | 0 | - | - | - | - | 2006-04-01 | 2010-03-01 | 0 | 0 | 5 | 5 | 10 | On-going Programme - not used yet
D00510 | Network Rail Bridges |  |  | 0 | 2005-08-01 | - | 2005-10-01 | - | - | - | 108 | 0 | 0 | 0 | 108 | Historic programme of studies, now complete
D00525 | Railtrack Incursion Works |  |  | 0 | - | - | - | - | 2003-10-01 | 2008-03-01 | 282 | 0 | 0 | 0 | 282
D00527 | Culvert Safety Improvement Programme |  |  | 31 | - | - | - | - | 2004-09-01 | 2011-03-01 | 106 | 80 | 0 | 0 | 186 | Managed by S Whittle
D00533 | Stott Lane Railway Bridge | 41 |  | 2 | 2004-08-04 | 2004-08-04 | 2009-08-01 | 2009-11-01 | 2010-01-01 | 2010-03-01 | 107 | 2 | 0 | 0 | 109 | Complete - awaiting final account
D00536 | East Ordsall Lane Canal Bridge |  |  | 0 | 2004-09-01 | 2004-09-01 | 2005-02-01 | 2005-08-01 | 2007-06-01 | 2008-09-01 | 309 | 0 | 0 | 0 | 309 | Extra works being valued - poss £50k
D00539 | Little Hulton Station Bridge | 731 |  | 0 | 2005-08-01 | 2005-08-01 | 2005-09-01 | 2008-05-01 | 2011-04-01 | 2011-07-01 | 31 | 0 | 0 | 700 | 731 | Prelim design - need decision on start date
D00545 | Footway Protection to Network Rail Bridges |  | 330 | 7 | - | - | 2010-07-01 | 2010-10-01 | 2011-01-01 | 2011-03-01 | 335 | 100 | 110 | 0 | 545 | Reduced prog for 2010/11
D00550 | Broad Street (Barr Hill) Parapet Repairs |  |  | 0 | 2011-01-01: 2007-10-01; 2011-03-01: 2008-09-01; 2011-04-01: 2008-11-01 | 164 | 16 | 0 | 0 | 180 | Complete - Awaiting info from HS on £16k - Paul H
D00551 | Leigh Road Culvert, Shaw Brook Tributory | 200 |  | 0 | 2009-03-01: 2008-01-01; 2010-10-01: 2008-10-01 | 6 | 0 | 0 | 200 | 206 | Scheme for 2010/11 (Awaiting UU agreement)
D00552 | Subways Improvement Programme |  | 200 | 10 | 2009-04-01 | 2009-04-01 | 2010-06-01 | 2010-08-01 | 2011-01-01 | 2011-03-01 | 8 | 260 | 0 | 0 | 268 | Tender return W/C 6/9
D00553 | Centenary Bridge Refurbishment |  |  | 2 | 2009-07-01 | 2009-07-01 | 2010-07-01 | 2010-10-01 | 2011-01-01 | 2011-03-01 | 62 | 4 | 120 | 0 | 186 | In Design
D00554 | Rossall Way Subway Parapet Strengthening |  |  | 0 | 2009-04-01 | 2009-04-01 | 2009-04-01 | 2009-09-01 | 2010-01-01 | 2010-02-01 | 26 | 2 | 0 | 0 | 28 | Complete - awaiting final account
D00555 | Kearton Drive Retaining Wall |  |  | 0 | 2009-04-01 | 2009-04-01 | 2009-04-01 | 2009-06-01 | 2009-09-01 | 2009-11-01 | 2 | 0 | 0 | 100 | 102 | Awaiting Design - need decision on start date
D00556 | Broad Street Footbridge | 104 | 160 | 16 | 2008-04-01 | 2008-06-01 | 2010-06-01 | 2010-08-01 | 2010-10-01 | 2010-12-01 | 23 | 44 | 100 | 0 | 167 | Out to tender
D00557 | Sherbourne Footbridge Refurbishment |  |  | 1 | [6 empty] | 1 | 1 | 0 | 250 | 252
D00558 | Barton Old Hall Bridge | 30 |  | 8 | 2008-04-01 | 2008-06-01 | 2009-10-01 | 2009-12-01 | 2010-02-01 | 2010-03-01 | 24 | 9 | 3 | 0 | 36 | Complete - awaiting final account
D00559 | Crescent Bridge Pavement Protection |  |  | 0 | [6 empty] | 1 | 0 | 0 | 0 | 1 | Now CSURC scheme
D00560 | Ellenbrook Culvert |  |  | 0 | [6 empty] | 5 | 0 | 0 | 200 | 205 | Scheme for 2009/10 - need cost estimate
D00561 | Culvert Condition Surveys |  | 20 | 18 | [6 empty] | 0 | 30 | 0 | 0 | 30 | 3 year prog to assess all culverts for HAMP
D00562 | Frederick Road Rail Bridges |  | 52 | 1 |  |  | 2010-07-01 | 2010-11-01 | 2011-01-01 | 2011-03-01 | 0 | 100 | 100 | 900 | 1100 | In Design - LM report Sept 10
| Sub-Total |  | 772 | 106 | [6 empty] | 1600 | 663 | 448 | 2365 | 5076
4. Principal Road Structural Maintenance
D00601 | A57 Liverpool Road, Cadishead | 400 |  | 208 | - | - | 2007-07-01 | 2007-10-01 | 2009-03-01 | 2010-03-01 | 95 | 212 | 0 | 0 | 307 | Complete
(New Moss Road - Fir Street)
D00605 | BVPI Surveys |  | 30 | 24 | - | - | - | - | 2003-08-01 | 2010-03-01 | 341 | 40 | 50 | 50 | 481 | FNS surveys
D00606 | A57 Liverpool Rd | 290 |  | 0 | - | - | 2006-06-01 | 2007-08-01 | 2008-04-01 | 2008-06-01 | 291 | 0 | 0 | 0 | 291 | Complete
(Boysnope - Barton Moss Road)
D00608 | Principal Road Maintenance - General |  |  | 21 | - | - | - | - | 2004-04-01 | 2010-03-01 | 74 | 0 | 0 | 0 | 74 | Recharge to Quays Loop Rd
D00635 | Street Lighting in Support of HIP | 200 |  | 2 | - | - | - | - | 2007-09-01 | 2010-03-01 | 438 | 2 | 0 | 0 | 440 | Complete - awaiting HS a/c
D00638 | Worsley Brow Roundabouts | 402 | 60 | 0 | 2007-11-01 | 2008-01-01 | 2008-01-01 | 2008-06-01 | 2010-03-01 | 2010-03-01 | 129 | 80 | 0 | 0 | 209 | Complete
D00639 | A572 Simpson Road / Leigh Road |  |  | 0 | 2009-12-01: 2007-11-01; 2010-02-01: 2008-01-01; 2010-03-01: 2008-06-01 | 602 | 0 | 0 | 0 | 602 | Complete
D00640 | Leicester Road Street Lighting Imp'ts | 75 |  | 0 | - | - | - | - | 2008-02-01 | 2008-10-01 | 1 | 0 | 0 | 0 | 1 | Complete
D00641 | Station Road Street Lighting Imp'ts | 25 |  | 0 | - | - | - | - | 2008-02-01 | 2008-07-01 | 25 | 0 | 0 | 0 | 25 | Complete
D00642 | Crash Barriers Renewal Programme |  |  | 3 | - | - | 2007-11-01 | 2008-07-01 | 2009-02-01 | 2010-03-01 | 263 | 5 | 0 | 0 | 268 | Review of Barton Lane
D00643 | Gully Replacement Programme | 100 |  | 37 | 2010-02-01: 2008-09-01; 2010-03-01: 2010-03-01 | 115 | 0 | 0 | 0 | 115
D00644 | Queen Street Resurfacing | 10 |  | 0 | 2010-02-01: 2008-12-01; 2010-03-01: 2008-12-01 | 11 | 0 | 0 | 0 | 11 | Complete
D00645 | Leigh Road (Standfield Drive - Ellenbrook Road) | 380 | 345 | 3 | 2009-12-01: 2010-08-01; 2010-02-01: 2011-01-01; 2010-03-01: 2011-03-01 | 27 | 150 | 100 | 0 | 277 | In detailed design
D00646 | Liverpool Road, Eccles (Peel St - Cawdor St) |  |  | 1 | [6 empty] | 7 | 1 | 293 | 0 | 301 | Topo Survey carried out
Topo Survey carried out
D00647 | Manchester Rd West (Cleggs Ln - Bolton Boundary) |  |  | 7 |  |  | 2010-08-01 | 2010-11-01 | 2011-01-01 | 2011-04-01 | 5 | 200 | 135 | 0 | 340 | Detailed Design commenced
D00648 | Moss Lane, Walkden | 350 | 350 | 12 |  | 2010-05-01 | 2010-04-01 | 2010-08-01 | 2010-10-01 | 2011-01-01 | 0 | 350 | 0 | 0 | 350 | Detailed Design commenced
????? | Liverpool Road, (New Moss Rd - Brinell Drive) |  |  | 0 |  |  | 2010-09-01 | 2011-12-01 | 2011-02-01 | 2011-04-01 | 0 | 0 | 115 | 0 | 115 | Scheme postponed until 2011/12
D00649 | Northumberland Street Resurfacing |  |  | 69 | [6 empty] | 0 | 0 | 0 | 0 | 0 | This scheme needs clarifying
| Sub-total |  | 785 | 387 | [6 empty] | 2424 | 1040 | 693 | 50 | 4207
5. Schemes To Assist Public Transport
D00709 | A57 Irlam Bus Stop Improvements |  | 80 | 5 | - | - | 2005-09-01 | 2010-06-01 | 2010-11-01 | 2011-01-01 | 151 | 91 | 0 | 0 | 242 | Approved - HS to undertake work
D00710 | Rail Station Access Improvements |  |  | 0 | 2007-07-01 | 2007-09-01 | 2007-10-01 | 2007-11-01 | 2008-01-01 | 2008-03-01 | 1 | 0 | 50 | 20 | 71 | Irlam Station C Park- Recharge Sal West
D00712 | Gore Street Bus Layover Facilities |  |  | 5 | [6 empty] | 0 | 5 | 20 | 0 | 25 | Feasibilirty only in 2010/11
D00713 | Victoria Bridge St Bus Lane Contraflow |  |  | 0 | [6 empty] | 0 | 5 | 100 | 0 | 105 | Feasibilirty only in 2010/11
| Sub-total |  | 80 | 10 | [6 empty] | 152 | 101 | 170 | 20 | 443
6. Schemes To Assist Cycling
D00805 | Cycle Parking Facilities |  | 15 | 0 | 2004-04-01 | 2004-06-01 | 2004-07-01 | 2009-08-01 | 2009-09-01 | 2009-10-01 | 76 | 10 | 10 | 10 | 106 | New sites required(brief req'd)
D00806 | Sustrans Routes NCN 6 |  |  | 0 | 2004-05-01 | 2004-07-01 | 2005-04-01 | 2006-12-01 | 2008-01-01 | 2008-06-01 | 360 | 0 | 0 | 0 | 360 | Complete - add signs req'd
D00807 | Cycling Projects Grant Fund |  |  | 0 | 2004-08-01 | 2004-09-01 | 2004-10-01 | 2005-01-05 | 2005-02-05 | 2005-03-01 | 29 | 0 | 40 | 40 | 109 | Bike Stations Initiative
D00809 | Cycle Parking Facilities at Schools |  | 30 | 0 | [6 empty] | 135 | 15 | 15 | 30 | 195 | Contributory funding to schools | bar: 2004-08-01 to 2005-03-01
D00812 | Bridgewater Way Contribution |  | 75 | 0 | - | - | - |  | 2007-01-01 | 2010-03-01 | 225 | 75 | 0 | 0 | 300 | Contribution to Bridgewater Canal Trust
D00813 | A56 Bury New Road Shared Facilities |  |  | 0 | 2006-05-01 | 2006-07-01 | 2006-04-01 | 2007-06-01 | 2009-01-01 | 2010-03-01 | 6 | 0 | 20 | 0 | 26 | Approved at TMU - Brief required
D00814 | Irlams O'th Height to Pendleton Roundabout |  |  | 0 | 2005-02-05: 2009-01-01; 2005-03-01: 2010-03-01 | 0 | 0 | 0 | 50 | 50 | Design Brief Required
D00815 | Sustrans Route 55 |  |  | 0 | - | - | - | - | 2008-01-01 | 2008-08-01 | 24 | 0 | 0 | 0 | 24 | Scheme complete
D00816 | Sustrans NCN Route 60 |  |  | 0 | [6 empty] | 0 | 0 | 0 | 200 | 200 | Reserve Scheme
D00817 | Links to Employment Sites |  |  | 3 | [6 empty] | 6 | 100 | 0 | 50 | 156 | Hessell St in 10/11 - design commenced
| Cycle Investment Area |  | 50 | 0 | [6 empty] | 0 | 0 | 75 | 75 | 150 | Links to city centre in 10/11
D00818 | Cycle Route Link - Liverpool Rd to Cad' Way | 100 |  | 4 | [6 empty] | 0 | 4 | 0 | 0 | 4 | Part of GM Waste access works - HS a/c req'd ?
D00819 | Cycle Centres |  | 50 | 0 | [6 empty] | 0 | 0 | 50 | 100 | 150
| Sub-total |  | 220 | 7 | [6 empty] | 861 | 204 | 210 | 555 | 1830
7. Other Minor Works
D00902 | Salford's Green Transport Plan |  |  | 0 | 2004-07-01 | 2004-09-01 | 2004-10-01 | 2004-12-01 | 2005-01-01 | 2009-03-01 | 111 | 0 | 0 | 0 | 111 | Cycle Lockers & Shower facilities
D00912 | Disabled Facilities at Pedestrian Crossings |  |  | 0 | - | - | - | - | 2008-01-01 | 2008-03-01 | 840 | 0 | 0 | 0 | 840 | complete
D00924 | Miscellaneous SRTS Works |  |  | 0 | - | - | - | - | 2003-08-01 | 2009-03-01 | 14 | 0 | 0 | 0 | 14 | Linked with School Travel Plans
D00934 | Dropped Kerbs & Tactile Paving Programme |  |  | 62 | - | - | - | - | 2007-08-01 | 2010-03-01 | 344 | 100 | 100 | 0 | 544 | Complete for 2010/11
D00939 | In Town Without My Car |  |  | 0 | - | - | - | - | 2006-09-01 | 2010-03-01 | 83 | 1 | 0 | 0 | 84
D00969 | Roe Green Loopline Phase 3 |  | 150 | 72 | 2008-03-01 |  | 2010-09-01 | 2010-10-01 | 2011-01-01 | 2011-03-01 | 516 | 160 | 150 | 0 | 826 | Clarify location of phse6 + amount of funding available
D00990 | Freight Signing Project |  |  | 0 | ? | ? | 2008-09-01 | 2008-11-01 | 2009-01-01 | 2009-02-01 | 24 | 0 | 0 | 0 | 24
D00991 | A6 Congestion Reduction Route 1 Improvements |  |  | 0 | [6 empty] | -8 | 200 | 0 | 0 | 192 | £180k funding for 10/11 - linked to URC
D00992 | A6 Chorley Road Pelican Crossing Improvements | 137 |  | 1 | 2004-10-01: 2008-01-01; 2005-01-01: 2009-01-01; 2009-03-01: 2010-03-01 | 132 | 1 | 0 | 0 | 133 | Complete
D00300 | Walkit Journey Planner Initiative | 0 |  | 0 | [6 empty] | 10 | 0 | 0 | 0 | 10 | Contribution to Walkit Initiative
????? | Plugged In Places Scheme |  | 50 | 0 | [6 empty] | 0 | 0 | 50 | 0 | 50 | Subject to successful GM bid
| Sub-total |  | 200 | 135 | [6 empty] | 2066 | 462 | 300 | 0 | 2828
8. Community Committee Schemes
D00943 | Ord/La - Pendleton Traffic Management | 28 |  | 0 | - | - | 2006-10-01 | 2006-11-01 | 2007-06-01 | 2007-07-01 | 29 | 0 | 0 | 0 | 29 | Complete - Phase 2
D00950 | I&C - Liverpool Rd / Fairhills Rd Ped Facilities |  |  | 0 | - | - | 2006-10-01 | 2007-01-01 | 2008-11-01 | 2008-01-01 | 155 | 0 | 0 | 0 | 155 | Complete
D00951 | I&C - Liverpool Rd / Ferry Hill Rd Ped Facilities | 24 |  | 0 | 2006-10-01 | 2006-10-01 | 2008-06-01 | 2008-07-01 | 2009-02-01 | 2009-03-01 | 13 | 0 | 0 | 0 | 13 | Complete
D00953 | W/B - A580 / Newearth Rd Ped Crossing Facils |  | 340 | 0 | 2007-09-01 | 2007-12-01 | 2008-02-01 | 2010-12-01 | 2011-03-01 | 2011-05-01 | 70 | -30 | 400 | 0 | 440 | Report submitted. Awaiting
D00954 | Sw - Mossfield Rd / Sefton Rd footpath | DAD |  | 0 | - | - | 2006-10-01 | 2006-11-01 | 2007-01-01 | 2007-02-01 | 56 | 0 | 0 | 0 | 56 | scheme completed
D00955 | Sw - Rake Ln / Lumbs Ln Traffic Calming | 84 |  | 0 | 2006-10-01 | 2006-10-01 | 2006-11-01 | 2006-12-01 | 2010-10-01 | 2010-11-01 | 57 | 14 | 0 | 0 | 71 | Complete
D00956 | Sw - Pendlebury Rd Residents Parking |  |  | 0 | - | - | 2006-11-01 | - | 2007-07-01 | 2007-10-01 | 89 | 0 | 0 | 0 | 89 | Ph 1 & Ph 2 complete
D00960 | Ecc - Alma Street Junction |  |  | 0 | - | - | 2006-12-01 | 2007-01-01 | 2009-02-01 | 2009-04-01 | 1 | 0 | 0 | 0 | 1 | Awaiting Eccles ok to proceed
D00961 | Ecc- Liverpool Rd Rumble Strips |  |  | 0 | [6 empty] | 17 | 0 | 0 | 0 | 17 | Complete | bar: 2007-09-01 to 2011-05-01
D00965 | Ecc- St Andrews Safer Routes to School |  |  | 0 | - | - | - | - | 2007-08-01 | 2007-09-01 | 40 | 0 | 0 | 0 | 40 | scheme completed
D00966 | O&L - Ordsall Lane Puffin Crossing | 16 | 12 | 0 |  | 2008-04-01 | 2008-05-01 | 2008-06-01 | 2011-04-01 | 2011-05-01 | 8 | 0 | 0 | 0 | 8 | URC funding now in 2011/12
D00971 | LH/W - Walkden Road Pelican Crossing | 61 |  | 4 | 2007-10-01 | 2008-01-01 | 2008-03-01 | 2008-06-01 | 2009-01-01 | 2009-03-01 | 14 | 4 | 0 | 0 | 18 | Complete
D00972 | Little Hulton & Walkden Feasibility Studies |  |  | 1 | [6 empty] | 15 | 1 | 0 | 0 | 16 | Costs related to scheme identification | bar: 2007-10-01 to 2009-03-01
D00973 | Claremont & Weaste Feasibility Studies |  |  | 2 | [6 empty] | 16 | 2 | 0 | 0 | 18 | Costs related to scheme identification | bar: 2007-10-01 to 2009-03-01
D00974 | Swinton Feasibility Studies |  |  | 2 | [6 empty] | 19 | 2 | 0 | 0 | 21 | Costs related to scheme identification | bar: 2007-10-01 to 2009-03-01
D00975 | Irlam & Cadsishead Feasibility Studies |  |  | 1 | [6 empty] | 5 | 1 | 0 | 0 | 6 | Costs related to scheme identification | bar: 2007-10-01 to 2009-03-01
D00976 | East Salford Feasibility Studies |  |  | 1 | [6 empty] | 23 | 1 | 0 | 0 | 24 | Costs related to scheme identification | bar: 2007-10-01 to 2009-03-01
D00977 | Eccles Feasibility Studies |  |  | 3 | [6 empty] | 18 | 3 | 0 | 0 | 21 | Costs related to scheme identification | bar: 2007-10-01 to 2009-03-01
D00978 | Ordsall & Langworthy Feasibility Studies |  |  | 1 | [6 empty] | 9 | 1 | 0 | 0 | 10 | Costs related to scheme identification | bar: 2007-10-01 to 2009-03-01
D00979 | Worsley & Boothstown Feasibility Studies |  |  | 1 | [6 empty] | 21 | 1 | 0 | 0 | 22 | Miscode- need to journal an amount to D00953 | bar: 2007-10-01 to 2009-03-01
D00980 | Hope Village Parking Improvements | 10 |  | 11 | 2007-11-01 | 2009-07-01 | 2009-08-01 | 2009-09-01 | 2010-12-01 | 2010-12-01 | 2 | 15 | 0 | 0 | 17 | Programmed start 06/12/2010
D00981 | C/W - Gilda Brook Subway Improvements | 37 |  | 0 |  | 2008-03-01 | 2008-05-01 | 2008-06-01 | 2008-09-01 | 2008-10-01 | 24 | 0 | 0 | 0 | 24 | Complete
D00982 | C/W - Bolton Road Parking Improvements |  | 70 | 0 | 2007-09-10 | 2008-03-01 | 2008-05-01 | 2008-06-01 | 2009-06-01 | 2009-12-01 | 150 | 0 | 0 | 0 | 150 | Complete-link to D00996
D00984 | Ecc - Eccles Station Footway Imps | 5 |  | 0 | 2007-09-10: n/a; 2008-03-01: n/a; 2008-05-01: 2007-11-01 | 2 | 0 | 0 | 0 | 2 | feasibilty complete
D00986 | Ecc - Pine Grove, Monton - SRTS | 75 |  | 0 |  | 2008-04-01 | 2008-05-01 | 2008-06-01 | 2009-01-01 | 2009-04-01 | 65 | 0 | 0 | 0 | 65 | Complete
D00987 | Wors & Booths - Fairmount Road Resurfacing |  |  | 0 | 2008-06-01: 2007-10-01; 2009-06-01: 2007-12-01; 2009-12-01: 2008-02-01 | 56 | 9 | 0 | 0 | 65 | Complete - Awaiting overheads resolution
D00988 | Wors & Booths - Ellenbrook Road Resurfacing | 20 |  | 0 | 2008-06-01: 2007-10-01; 2009-06-01: 2008-04-01; 2009-12-01: 2008-04-01 | 12 | 8 | 0 | 0 | 20 | Complete - Awaiting overheads resolution
D00989 | LH/W - Ashton Fields Drive / Campbell Way Junction | 35 |  | 0 | 2007-08-01 | 2007-09-01 | 2007-12-01 | 2008-01-01 | 2008-09-01 | 2009-10-01 | 60 | 0 | 0 | 0 | 60 | Complete - Awaiting overheads resolution
D00993 | Ecc - Parrin Lane - Speed Reduction | 15 |  | 0 | 2008-09-01: 2009-01-01; 2009-10-01: 2009-03-01 | 8 | 7 | 0 | 0 | 15 | Complete - Awaiting overheads resolution
D00994 | Ecc - Fox Street / College Croft Plateau | 5 |  | 0 | 2008-09-01: 2008-11-01; 2009-10-01: 2009-01-01 | 1 | 9 | 0 | 0 | 10 | Complete - Awaiting overheads resolution
D00996 | C/W - Bolton Road Pedestrian Improvements | 34 |  | 0 | 2008-09-01: 2009-06-01; 2009-10-01: 2009-12-01 | 2 | 0 | 0 | 0 | 2 | Complete - Awaiting overheads resolution
D00997 | C/W - Doveleys Road Speed Management | 13 |  | 0 |  | 2008-06-01 | 2008-07-01 | 2008-08-01 | 2008-09-01 | 2008-10-01 | 7 | 6 | 0 | 0 | 13 | Complete - Awaiting overheads resolution
D00998 | C/W - Derby Road Traffic Calming | 56 |  | 0 | 2008-09-01: 2009-01-01; 2009-10-01: 2009-02-01 | 67 | 0 | 0 | 0 | 67 | Complete - Awaiting overheads resolution
D00999 | Weaste Lane School Access Improvement | 4 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | Complete - Awaiting overheads resolution
D00021 | Sw - Cromwell Road / Hamilton Street | 28 |  | 0 |  | 2008-05-01 | 2008-07-01 | 2008-08-01 | 2009-05-01 | 2009-05-01 | 41 | 0 | 0 | 0 | 41 | Complete - Awaiting overheads resolution
D00022 | Sw - North Dean Street Resurfacing | 5 |  | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | Complete - Awaiting overheads resolution
D00023 | Sw - Gaskell Street Resurfacing | 10 |  | 0 | 2008-09-01: 2008-09-01; 2009-10-01: 2008-09-01 | 17 | 0 | 0 | 0 | 17 | Complete - Awaiting overheads resolution
D00024 | LH/W - A6 / Sharp St Speed Management | 7 |  | 0 | 2007-09-01: 2008-02-01; 2008-09-01: 2008-09-01; 2009-10-01: 2008-09-01 | 3 | 4 | 0 | 0 | 7 | Complete - Awaiting overheads resolution
D00025 | East Sal - New Hall Road Lighting Improvements |  |  | 0 | 2008-09-01: 2008-08-01; 2009-10-01: 2008-11-01 | 34 | 0 | 0 | 0 | 34 | Complete - Awaiting overheads resolution
D00026 | East Sal - Gt Clowes St Speed Management | 12 |  | 0 | 2007-09-01: 2008-05-01; 2008-09-01: 2008-09-01; 2009-10-01: 2008-10-01 | 7 | 5 | 0 | 0 | 12 | Complete - Awaiting overheads resolution
D00027 | East Sal - Lower Broughton Road Speed Management | 11 |  | 0 | 2007-09-01: 2008-05-01; 2008-09-01: 2008-09-01; 2009-10-01: 2008-10-01 | 7 | 4 | 0 | 0 | 11 | Complete - Awaiting overheads resolution
D00028 | East Sal - Neville Road Traffic Calming | 15 |  | 3 |  | 2010-07-01 | 2010-11-01 | 2011-01-01 | 2011-03-01 | Apl-11 | 2 | 11 | 30 | 0 | 43 | Community Committee approval received
D00029 | East Sal - Gerald Road Lighting Improvements |  |  | 0 | [6 empty] | 2 | 0 | 0 | 0 | 2 | Complete
D00030 | Ecc - Ellesmere Street Traffic Calming | 41 |  | 0 |  | 2008-06-01 | 2008-07-01 | 2008-09-01 | 2009-02-01 | 2009-03-01 | 62 | 0 | 0 | 0 | 62 | Complete
D00031 | East Sal - Summerville/ Duchy Subway Improvements | 18 |  | 1 | 2008-09-01: 2008-06-01; 2009-10-01: 2008-10-01 | 29 | 1 | 0 | 0 | 30 | Complete
D00032 | LH?W - Old Clough Lane - Driver Feedback Sign | 12 |  | 0 | 2008-09-01: 2009-01-01; 2009-10-01: 2009-01-01 | 8 | 4 | 0 | 0 | 12 | Complete - awaiting final account
D00034 | LH/W Memorial Road Speed Management | 5 |  | 0 | 2008-09-01: 2009-01-01; 2009-10-01: 2009-01-01 | 6 | 0 | 0 | 0 | 6 | Complete
D00035 | Ecc - Worsley Road, Eccles, Speed Management | 10 |  | 0 | 2008-09-01: 2009-01-01; 2009-10-01: 2009-01-01 | 8 | 2 | 0 | 0 | 10 | Complete - awaiting final account
D00036 | Sw - Thorn Road Traffic Calming | 30 | 37 | 16 | 2008-11-01 |  |  | 2010-06-01 | 2010-10-01 | 2010-11-01 | 5 | 48 | 0 | 0 | 53 | Complete
D00037 | LH/W - Mort Lane Speed Management Scheme | 5 |  | 0 | 2008-09-01: 2009-02-01; 2009-10-01: 2009-03-01 | 6 | 0 | 0 | 0 | 6 | Complete
D00038 | Ecc- Buteel St Street Lighting | 4 |  | 0 | [6 empty] | 3 | 0 | 0 | 0 | 3 | Complete
D00039 | East Sal - Legh Street Pedestrian Improvements | 80 |  | 0 | 2008-11-01 | 2009-01-01 | 2009-03-01 | Apl-09 | 2009-07-01 | 2009-08-01 | 103 | 0 | 0 | 0 | 103 | Complete
D00040 | Ecc - Gleave Road Dropped Crossings | 4 |  | 0 | 2008-09-01: 2009-02-01; 2009-10-01: 2009-02-01 | 4 | 0 | 0 | 0 | 4 | Complete
D00041 | C/W Bolton Road Speed Management | 13 |  | 3 | 2008-01-01: 2009-02-01; 2008-09-01: 2009-03-01; 2009-10-01: Apl09 | 14 | 0 | 0 | 0 | 14 | Complete
D00042 | East Sal - Village Street, Street Lighitng Improvements | 0 | 22 | 0 | 2008-09-01: 2011-01-01; 2009-10-01: 2011-02-01 | 3 | 24 | 0 | 0 | 27 | Street Lighting progressing
D00043 | East Sal - Albert Park Rad, Street Lighting | 0 |  | 0 | 2008-09-01: 2009-02-01; 2009-10-01: Apl09 | 15 | 4 | 0 | 0 | 19 | Complete - awaiting final account
D00044 | Riverside Street Lighting, Gerald Road | 0 |  | 0 | 2008-09-01: 2009-02-01; 2009-10-01: Apl09 | 47 | 0 | 0 | 0 | 47 | Complete
D00045 | O & L - Freya Grove Traffic Calming | 12 |  | 0 |  | 2009-02-01 | 2009-03-01 | 2009-03-01 | 2009-12-01 | 2009-12-01 | 16 | 0 | 0 | 0 | 16 | Complete - awaiting final account
D00046 | O & L - Sedgefield Close Traffic Calming | 13 |  | 0 |  | 2009-02-01 | 2009-03-01 | 2009-03-01 | 2009-08-01 | 2009-09-01 | 30 | 0 | 0 | 0 | 30 | Complete
D00047 | O&L - Ordsall Estate 20mph Zone | 90 | 175 | 13 | 2009-03-01 | 2009-08-01 | 2009-10-01 | 2010-02-01 | 2011-01-01 | 2011-03-01 | 24 | 176 | 0 | 0 | 200 | Objection rcvd may require Reg Panel report
D00048 | LH/W - Sharp Street Speed Management | 15 |  | 0 | 2010-02-01: 2009-02-01; 2011-01-01: 2009-03-01; 2011-03-01: Apl09 | 15 | 0 | 0 | 0 | 15 | Complete
D00049 | East Sal - Littleton Road Pedestrian Crossing | 20 |  | 0 | 2011-01-01: 2009-03-01; 2011-03-01: 2009-07-01 | 20 | 0 | 0 | 0 | 20 | ES contribution to NDC scheme
D00301 | LH/W - Peel Lane Traffic Calming |  | 28 | 0 | 2009-02-01 | 2009-03-01 | 2010-07-01 | 2010-09-01 | 2011-01-01 | 2011-02-01 | 0 | 0 | 0 | 28 | 28 | CCmmttee placed on hold
D00302 | LH/W - Manchester Rd / Cleggs Lane Ped Facilities |  | 190 | 2 | 2009-02-01 | 2009-03-01 | 2010-11-01 | 2011-01-01 | Apl-11 | 2011-06-01 | 7 | 50 | 173 | 0 | 230 | LM report being drafted
D00303 | O & L - Jubilee Street Traffic Calming | 25 |  | 0 | Apl-09 | 2009-05-01 | 2009-06-01 | 2009-07-01 | 2009-11-01 | 2009-12-01 | 35 | 0 | 0 | 0 | 35 | Complete - awaiting final account
D00304 | Ecc - Rook Street Traffic Management | 32 |  | 0 | 2009-09-01 | 2009-10-01 | 2009-11-01 | 2010-01-01 | 2010-03-01 | 2010-04-01 | 1 | 0 | 0 | 0 | 1 | Scheme dropped by CC
D00305 | East Sal - Lwr Broughton Rd Dropped kerbs / Tactiles | 35 | 35 | 31 | 2009-06-01 | 2009-08-01 | 2009-11-01 | 2009-12-01 | 2010-02-01 | 2010-03-01 | 43 | 0 | 0 | 0 | 43 | Complete
D00306 | East Sal - Dunedin/ Helensville - Traffic calming | 15 | 15 | 0 | 2009-11-01 | 2010-08-01 | 2010-10-01 | 2010-11-01 | 2011-01-01 | 2011-02-01 | 0 | 0 | 0 | 0 | 0 | Scheme dropped by CCmmttee
D00307 | Sw - Dean's Road/ Ellesmere Street - Traffic calming | 41 | 41 | 1 | 2009-09-01 | 2010-09-01 | 2010-11-01 | 2010-12-01 | 2011-03-01 | Apl-11 | 0 | 20 | 21 | 0 | 41 | SD report being drafted
D00308 | Sw - Broomhall Road - Traffic calming | 17 | 17 | 14 | 2009-08-01 | 2009-11-01 | 2010-01-01 | 2010-03-01 | 2010-07-01 | 2010-07-01 | 1 | 16 | 0 | 0 | 17 | Complete
D00309 | East Sal - Bank Ln/ Barclays Av - pedestrian facilities | 18 | 18 | 0 | Apl-10 | 2010-08-01 | 2010-10-01 | 2010-12-01 | 2011-02-01 | Mch-11 | 0 | 0 | 0 | 0 | 0 | Scheme dropped by CCmmttee
D00310 | C/W - Lancaster Road Pedestrian Refuge | 0 | 15 | 7 | 2009-06-01 | 2009-08-01 | 2009-10-01 | 2009-11-01 | 2010-01-01 | 2010-02-01 | 11 | 7 | 0 | 0 | 18 | Complete
D00311 | Rocky Lane Driver Feedback Sign |  |  | 15 |  | 2010-07-01 | 2010-08-01 | 2010-08-01 | 2010-10-01 | 2010-10-01 |  | 7 |  |  |  | Complete
D00312 | Peel Green Traffic Management Scheme |  |  | 2 | [7 empty] | 3 |  |  |  | Dropped by Eccles £3k for surveys
D00313 | Sw - Driver Feedback Signs - Swinton |  |  | 17 |  | 2010-07-01 |  | 2010-08-01 | 2010-10-01 | 2010-10-01 | 0 | 22 | 0 | 0 | 22 | Complete
D00314 | Ecc - Weymouth Road / Gee Lane - Resurfacing | 27 |  | 1 |  |  | 2010-07-01 | 2010-08-01 | 2010-10-01 | 2010-10-01 | 0 | 1 | 0 | 0 | 1 | Complete
D00315 | Ecc - Edison Road Dropped Crossings | 3 |  | 3 | 2010-01-01: 2010-10-01; 2010-02-01: 2010-10-01 | 0 | 3 | 0 | 0 | 3 | Complete
D00316 | Ecc - Edison Road 20mph Zone | 32 |  | 1 | 2010-09-01 | 2010-09-01 | 2010-10-01 | 2010-11-01 | 2011-02-01 | 2011-03-01 | 0 | 32 | 0 | 0 | 32 | Consultation progressing
D00317 | Ecc - Hereford Rd / Winchester Rd Traffic Calming | 35 |  | 1 | 2010-08-01 | 2010-08-01 | 2010-09-01 | 2010-11-01 | 2011-01-01 | 2011-02-01 | 0 | 35 | 0 | 0 | 35 | SD report being drafted
D00318 | Ecc - Lansdowne Road Bollards | 2 |  | 0 | 2010-01-01: 2010-11-01; 2010-02-01: 2010-11-01 | 0 | 0 | 0 | 0 | 0 | Scheme dropped by CCmmttee
D00319 | Ecc - Schofield Road Footpath Improvements | 26 |  | 1 | 2010-09-01 | 2010-10-01 | 2010-12-01 | 2011-01-01 | 2011-03-01 | Apl-11 | 0 | 26 | 0 | 0 | 26 | ENV services approval - SD report
D00320 | Ecc - Ellesmere Street Dropped Crossings | 24 |  | 1 | 2010-09-01 |  | 2010-09-01 | 2010-10-01 | 2010-12-01 | 2010-12-01 | 0 | 24 | 0 | 0 | 24 | On site
D00321 | Ecc - Albert Street Footway Improvement | 7 |  | 5 | 2010-01-01: 2010-09-01; 2010-02-01: 2010-09-01 | 0 | 7 | 0 | 0 | 7 | Complete
D00322 | Sw - Enfield Road / Westmeade Traffic Calming | 20 |  | 0 | 2010-06-01 | 2010-07-01 | 2010-08-01 | 2010-09-01 | 2011-01-01 | 2011-02-01 | 0 | 20 | 0 | 0 | 20 | TRO currently being advertised
D00323 | Sw - Lumn's Lane Speed Management | 30 |  | 0 | 2010-10-01 | 2010-10-01 | 2011-01-01 | 2011-02-01 | 2011-03-01 | Apl-11 | 0 | 15 | 15 | 0 | 30 | Consultation ongoing
D00324 | Sw - Silverdale Traffic Calming | 25 |  | 0 | 2010-10-01 | 2011-01-01 | 2011-03-01 | Apl-11 | 2011-06-01 | 2011-07-01 | 0 | 2 | 23 | 0 | 25 | Consultation in New Year
D00325 | I&C - Irlam & Cadishead Driver Feedback Signs | 35 |  | 0 | 2011-01-01: 2011-01-01; 2011-02-01: 2011-01-01 | 0 | 8 | 0 | 27 | 35 | DFS on order
D00326 | East Sal - Albert Park Road Area Traffic Calming | 35 |  | 0 | 2010-10-01 | 2011-01-01 | 2011-03-01 | Apl-11 | 2011-06-01 | 2011-07-01 | 0 | 2 | 33 | 0 | 35 | Consultation in New Year
D00327 | East Sal - Whit Lane Traffic Calming | 20 |  | 0 | 2010-10-01 | 2011-02-01 | Apl-11 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 0 | 0 | 0 | 20 | 20 | Consultation in New Year
D00328 | W/B - School 20mph Zone, Worsley | 85 |  | 0 | 2010-10-01 | 2011-02-01 | Apl-11 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 0 | 0 | 0 | 85 | 85 | Depending on decision on A580 all red
D00329 | C/W - Fairthorpe Road Traffic Calming | 31 |  | 0 | 2010-10-01 | 2011-02-01 | Apl-11 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 0 | 2 | 29 | 0 | 31 | Consultation in New Year
D00330 | C/W - Welwyn Drive Area Traffic Calming | 24 |  | 0 | 2010-10-01 | 2011-02-01 | Apl-11 | 2011-07-01 | 2011-08-01 | 2011-09-01 | 0 | 2 | 0 | 22 | 24 | Consultation in New Year
D00331 | C/W - Fairfield Street Traffic Calming | 15 |  | 0 | 2010-10-01 | Apl-11 | 2011-06-01 | 2011-09-01 | 2012-01-01 | 2012-02-01 | 0 | 2 | 3 | 10 | 15 | Depending on BoA poss 2012 scheme
D00332 | C/W - Dronfield Road Traffic Calming | 41 |  | 0 | 2010-10-01 | Apl-11 | 2011-06-01 | 2011-09-01 | 2012-01-01 | 2012-02-01 | 0 | 2 | 4 | 35 | 41 | Depending on BoA poss 2012 scheme
D00333 | LH/W - Hilltop Road Resurfacing | 15 |  | 0 | 2010-12-01 | 2011-02-01 | 2011-02-01 | 2011-03-01 | Apl-11 | Apl-11 | 0 | 15 | 0 | 0 | 15 | Order to DLO - work to be programmed in
D00334 | I&C - Astley Road Resurfacing | 60 |  | 0 | 2010-12-01 | 2011-02-01 | 2011-02-01 | 2011-03-01 | Apl-11 | Apl-11 | 0 | 60 | 0 | 0 | 60 | Order to DLO - work to be programmed in
D00335 | C/W - Driver Feedback Signs | 14 |  | 0 | 2011-01-01: 2011-01-01; 2011-02-01: 2011-01-01 | 0 | 14 | 0 | 0 | 14 | DFS on order
| Allocations for 2010/11 |  | 800 | 0 | [6 empty] | 0 |  | 800 | 0 | 800
| Congestion Monitoring Funding | [14 empty] | £180k credited to cost code D00991
| Carry forward from 2009/10 |  | 432 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0
| Reduction due to 25% cuts |  | -740 | [7 empty] | 0 | 0 | 0 | 0 | 0
| Sub-total |  | 1507 | 165 | [6 empty] | 1760 | 734 | 1531 | 227 | 4252
| Total Minor Works |  | 3909 | 898 | [6 empty] | 11497 | 3526 | 3905 | 3297 | 22225 | Minor works allocation is £3.909m for 2010/11
[12 empty] | -383 |  |  |  | Minor Works over-programming
|  |  |  | 22.9726 | [7 empty] | 90.2021 |  |  |  | Percentage Spend Minor Works
| GRAND TOTAL |  | 5868 | 1396 | [6 empty] | 65877 | 5485 | 3905 | 3372 | 78639
|  |  |  | 23.79 | [7 empty] | 93.4731 |  |  |  | Percentage Total Spend