REPORT OF THE DEPUTY DIRECTOR FOR HOUSING AND PLANNING

TO THE LEAD MEMBER FOR PLANNING ON 28 JANUARY 2008

TITLE: A666 BOLTON ROAD/STATION ROAD – JUNCTION IMPROVEMENT

RECOMMENDATIONS:

That Lead Member for Planning is recommended to: accept the agreed target cost of £498,800.00 from negotiation with our partner contractor Birse Civils Ltd. to carry out the improvement works at the junction of the A666 Bolton Road and Station Road in Pendlebury. The works include the widening and resurfacing of the carriageway, provision of new pedestrian facilities and the installation of new traffic signals.

EXECUTIVE SUMMARY: The purpose of this report is to seek authority to accept the quotation from Urban Vision Partnership Ltd/Birse Civils Ltd. to carry out improvement works to the junction of the A666 Bolton Road and Station Road in Pendlebury.

BACKGROUND DOCUMENTS:

Report to Traffic Management Unit – 29/11/06

Report to Lead Member – 30/07/07

ASSESSMENT OF RISK:  Low

SOURCE OF FUNDING:

Local Safety Scheme Block 3, Transport Capital Programme

Greater Manchester Passenger Transport Executive

LEGAL IMPLICATIONS:

Contact Officer and Extension No: Ian Sheard - 3084

Comments: Report okay when examined against the monitoring officer’s checklist

FINANCIAL IMPLICATIONS:

Contact Officer and Extension No: Nigel Dickens - 2585

Comments: Report okay when examined against the monitoring officer’s checklist

## COMMUNICATION IMPLICATIONS: N/A

VALUE FOR MONEY IMPLICATIONS: N/A

CLIENT IMPLICATIONS:

Contact Officer and extension No: Darren Findley - 3849

The client has been consulted and the scheme is included in the Block 3 Transport Capital Programme 2007/08

PROPERTY: N/A

HUMAN RESOURCES: N/A

CONTACT OFFICERS: Stephen Hands	/Neil Ashmall Telephone: 01617794931/4883

WARD(S) TO WHICH REPORT RELATE(S): Pendlebury, Swinton North

KEY COUNCIL POLICIES: ENHANCING LIFE IN SALFORD

Reducing the number of people killed or seriously injured on Salford’s roads

- Background:

1.1	The junction has been identified as having an unacceptably high number of collisions, especially those involving pedestrians, in the last 3 years, there have been 13 other collisions involving vehicle manoeuvres.

1.2	The junction suffers from severe congestion at peak times, which is of concern to Greater Manchester Passenger Transport Executive (GMPTE) and bus operators. As part of their programme to improve bus services, GMPTE have offered to contribute funding for the improvements to the junction.

1.3	Advanced civil engineering works and the diversion of Statutory Authorities’ plant were approved in the report to Lead Member on 27/7/07. The advanced civil engineering works were completed by Birse Civils Ltd on 2/11/07.  The diversion works began immediately after and will be completed prior to the commencement of the main works.

- Details:

2.1	Traffic modeling work has indicated a proposal to widen and re-align the             junction, which will provide substantial benefit to motorists allowing separate straight on, left and right turn lanes in either direction along Bolton Road. This will alleviate delays with vehicles turning, reducing queue lengths at peak times.

2.2	The widening of the highway allows for the introduction of protected red/green    man crossing facilities across all four legs of the junction. This will assist in reducing the number of collisions with pedestrians and enable pedestrians from all aspects of society to cross the junction in safety.

2.3	The widening of the highway has required the transferring of land from Environmental Services to Housing and Planning Directorate.

2.4	Diversion works by statutory authorities are currently in progress and are scheduled to finish by the end of January ‘08.

2.5	Once the diversionary works are completed, the main contract to construct the junction improvement will commence in February 2008 and take twenty weeks to complete.

2.6	The proposals will be undertaken in liaison with and take due account of the proposed West Salford Gateway Action Plan.

- Financial Implications

3.1	The scheme has been included within 2007/08 Block 3 Transport Capital Programme allocation.

3.2	Work undertaken by the statutory authorities altered whilst on site and subsequently costs have differed from those submitted on their respective detailed cost estimates. The final costs have yet to be submitted, however, United Utilities Water and National Grid Transco have significantly reduced the scope of work required. Costs will now amount to approximately £133,000, as opposed to £188,930 previously reported.

3.3	Increased advance civils works, undertaken in October/November 2007, to allow a greater quantity of work off highway, resulted in these costs increasing to £65,341.82. from the reported estimate of £34,300. However, the reduction in cost of the statutory authorities’ diversion works gives a net saving of £24,888.18 on the cost previously reported.

3.4	A contribution of £240,000 from GMPTE is allocated to this scheme from their 2007/08 programme.

Agreed Target Cost            	                        £498,800.00

(including the Advance Civil Engineering

works)	            				(£65,341.82)

Statutory Undertakers diversions		£133,000.00

(completed)

GMUTC works – estimated			£  60,000.00

Urbanvision Fees				£ 53,387.69

Overall Scheme Total				£745,187.69

GMPTE contribution				£240,000.00

Salford contribution				£505,187.69

- Recommendation

4.1	The recommendation is that Lead Member gives approval to this report, allowing  Birse Civils Ltd. to be commissioned to undertake the works.

Bob Osborne

Deputy Director of Housing and Planning

# Text boxes

Part 1