|  | ITEM NO. |
| --- | --- |

REPORT OF THE STRATEGIC DIRECTOR OF SUSTAINABLE REGENERATION AND THE DIRECTOR OF CHANGE

TO THE LEAD MEMBER FOR PROPERTY ON 29 OCTOBER 2010

| TITLE: | Strategic Property - City Council Core Sites Office Accommodation – Minerva House – Update 2 |
| --- | --- |

RECOMMENDATIONS:

- That the programme of moves to accommodate staff from Minerva House into the other Core Sites is agreed.

- That the estimates for costs associated with the moves are approved as within the office moves budget for 2010/11.

EXECUTIVE SUMMARY:

The closure of Minerva House will make a saving for the council in excess of £500,000 p.a. once the closure costs are met.

The schedule of moves set out below will also enable the lease on the 8th floor offices in St James’s House to be released from April 2011 at an additional saving of £79,000 p.a.

This report outlines a final programme of office moves to enable the displaced staff (292) from Minerva House and St. James’s house to be located within the remaining core office sites.  This relocation will require moves within the Civic Centre / Innovation House / Unity House / Elmstead House complex of a further 360 staff. Estimates of costs for 2010/11 and 2011/12 are included.

BACKGROUND DOCUMENTS:

Report of Report to the Lead member for Property of 14th September 2010

KEY DECISION:	N/A

DETAILS:

- As agreed in the report of the 14th September  the moves programme outlined below has been designed to achieve the following;

  - To create a coherent space for staff working for Children’s Services that supports their future service plans, meets the necessary confidentiality and security requirements relating to some of their work and integrates them into other supporting services.

  - To locate other occupants of Minerva House within the relevant “common service” areas existing in the Civic Centre complex.

  - To reflect, as far as possible, the existing office refurbishment plans and work within existing refurbishment budgets.

  - To design office space to cope with a significantly higher density of users than hitherto, implementing the new office principles for all moves. This will also include, where necessary, enhanced welfare facilities, efficient desk layouts etc.

- The aim of the planned moves and refurbishments is to achieve the above objectives within the current years office moves budget of £1.74m when other agreed and priority moves are also included. A full schedule of costed moves and works is attached.

- Full benefit has also been taken to maximise the opportunity of the moves to undertake planned, but not scheduled, refurbishment of offices that are below the current expected standard. This means that the short-term option of using Minerva House is optimised, to effectively “decamp” teams before its closure. In doing this we can create further opportunities for office rationalisation onto the core sites after Minerva House has been closed. In particular it is proposed to refurbish the ground floor east and first floor west of Unity   this programme.

- The total budgeted expenditure in 2010/11 is;

Minerva-related works;         £1.113m

Other                                     £0.633m

Total                                      £1.746m

(note: some non-Minerva related moves have already been achieved e.g. Innovation House and the relocation of Community Safety to Turnpike House)

- The figures include £170k to refurbish the 1st floor west of Unity House. However the schedule of moves at present indicates that this will not be possible in the current financial year and may require a carry forward to 2011/12. Also proposed for 2011/12 is the refitting of the 1st floor of Phase 2 to bring it into conformity with the other floors. This will be included in the bid for office moves for 2011/12.

- To reduce costs furniture, telephones, ICT equipment etc. that can be reused within the refurbished office spaces have been identified and sequenced into the programme.

- The current space (in relation to net internal area) in Minerva House is 10.4 sq metres per person. Destination spaces will operate at 8 sq metres per person or better.

EQUALITY IMPACT ASSESSMENT AND IMPLICATIONS:

The review of office accommodation is underpinned by an understanding of the requirements of the Disability Discrimination Act and the promotion of equal access to work for all existing and potential employees. This will include an assessment of reasonable adjustments for staff with additional requirements.

ASSESSMENT OF RISK:

High – This is the largest office moves programme undertaken by the Council.

SOURCE OF FUNDING: Identified in the report

LEGAL IMPLICATIONS:

Now a valid break notice has been served for Minerva House, it cannot be withdrawn. The lease break for St James’s House will be served by 31st December 2010 allowing for it to be terminated on the 31st March 2011.

FINANCIAL IMPLICATIONS: Identified in the report

OTHER DIRECTORATES CONSULTED:

Via One Council Team and specifically Children’s Services.

CONTACT OFFICER:  Rob Pickering 2818 / Martin Vickers 3407

WARD(S) TO WHICH REPORT RELATE(S): Swinton North

ANNEX 1

Note the budget identified includes costs for building works, furniture, ICT and physical moves.

| Location | Work | Start | End | Budget (000s) | Moving Out | To | Moving In | From |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 2: 3rd floor middle + end | Refurbishment | 08/11/2010 | 07/01/2011 | 180 | SR 25/10/2010 | Phase1: 2nd floor | ICT 10/01/2011 | Phase 1: 3rd floor |
|  |  |  |  |  | Energy Audit 05/11/2010 | Phase 2:1st floor | Scrutiny 19/11/2010 | Phase 2: 1st floor middle |
|  |  |  |  |  |  |  | Gov Services 19/11/2010 |  |
| Civic 4th Floor | Part Refurbishment | 22/11/2010 | 26/11/2010 | 19 | SR 19/11/2010 | Phase 2: 1st floor middle | ICT from 29/11/2010 | Phase 2: 2nd floor middle |
| Phase 2: 2nd floor middle | Refurbishment | 31/01/2011 | 25/03/2011 | 145 | ICT from 29/11/2010 | 4th Floor | Economic Development 28/03/2010 | Unity: 2nd floor West |
|  |  |  |  |  | SR Accountants 03/01/2011 | Phase 2: 1st floor middle |  |  |
| Phase 2: 1st floor middle | none 2010/2011 Refurbishment 2011/12 | 29/11/2010 |  | 13 (146 2011/12) | Legal 19/11/2010 | Phase 2: 1st floor 1.4 | SR Accountants 03/01/2011 | Phase 2: 2nd floor middle |
|  |  |  |  |  | Scrutiny 19/11/2010 | Phase 2:3rd floor middle/end | SR 19/11/2010 | 4th Floor |
| Phase 2: 1.4 | furniture + VOIP + wiring + lockers |  | Before 19/11/2010 | 27 |  |  | Legal 19/11/2010 | Phase 2; 1st floor middle + 1.1 |
| Phase 2:1st floor end (1.1) | furniture + VOIP + wiring | 06/12/2010 | 17/12/2010 | 6 | Legal 19/11/2010 (holding place for legal files until 24/12/2010) | Phase 2: 1st floor middle/end | SP&P + E&C 01/04/2011 | Unity: 2nd floor West |
| Location | Work | Start | End | Budget (000s) | Moving Out | To | Moving In | From |
| Phase 2: ground floor end (G1) | Refurbishment | 22/09/2010 | 22/10/2010 | 46 | none |  | Change from 15/11/2010 | Unity 2nd floor West |
|  |  |  |  |  |  |  | Change from 15/11/2010 | Minerva |
|  |  |  |  |  |  |  | Change 31/01/2010 | St James’s |
| Phase 1: 3rd floor | Refurbishment | 10/01/2011 | 25/03/2011 | 103 | ICT 10/01/2010 | Phase 2: 3rd floor middle | Children’s Services 28/03/2011 | Minerva |
| Phase 1: 2nd floor | Refit + additional desks | 04/10/2010 | 22/10/2010 | 52 | none |  | SR 25/10/2010 | 3rd Floor end |
| Unity: 2nd floor East | Galley Kitchens + VOIP | 03/01/2011 | 07/01/2011 | 34 | M&C 13/12/2010 | Elmstead |  |  |
|  |  |  |  |  |  |  | Then Children’s Services | Minerva |
| Unity: 2nd floor West | Galley Kitchens + VOIP | 07/03/2011 | 11/03/2011 | 34 | Change/E&C/ SP&P 01/04/2011 | Phase 2: ground floor |  |  |
|  |  |  |  |  | Skills & Work 15/11/2010 | Cash Office | Then Children’s Services | Minerva |
|  |  |  |  |  | Economic Development 28/03/2011 | Phase 2: 2nd floor middle |  |  |
| Unity: 1st Floor East | none |  |  | 9 |  |  | Schools Accountants 03/01/2011 | Minerva |
|  |  |  |  |  |  |  | e-trading 03/01/2011 | Unity: 1st floor West |
| Location | Work | Start | End | Budget (000s) | Moving Out | To | Moving In | From |
| Unity: ground floor East | Refurbishment | 07/02/2011 | 11/04/2011 | 179 | Benefits 04/02/2011 | decamp space | Benefits 14/04/2011 | decamp space |
| Unity: 1st floor West | Refurbishment | 18/04/2011 | 01/07/2011 | 170 (unlikely to be started in 2010/11) | Finance 15/04/2011 | decamp space | Finance 04/07/2011 | decamp space |
|  |  |  |  |  |  |  | CS Finance 04/07/2010 | Minerva |
| Cash Office | Mend Roof | 1/11/2010 | 12/11/2010 | 7 | Benefits 29/10/2010 | Unity: ground floor both sides | Skills & Work 15/11/2010 | Unity 2nd floor West |
| Elmstead | Re-decorate | 15/11/2010 | 03/12/2010 | 33 | Comm Safety 15/10/2010 | Turnpike | M&C | Unity:2nd floor East 13/12/2010 |
| St James’s House | none |  |  | 4 | Change 31/01/2011 | Phase 2: ground floor end |  |  |
|  |  |  |  |  | Change Admin 25/03/2011 | tba |  |  |
|  | VOIP rollout |  |  | 48 |  |  |  |  |
|  | Telephony |  |  | 5 |  |  |  |  |