## Sheet1
Development Services Capital Monitoring 2005/06
July | [5 empty] | Funding | [16 empty] | Comments
Project | Capital | Adjustments/ |  | Actual
| Programme | Slippage | Total | Spend |  | Unsupported | Capital | RCCO | Grant | [8 empty] | Section 106 | Insurance | Other | Total
| 2005/06 |  |  | July |  | Borrowing | Receipts |  | NWDA | ERDF | NRF | HMRF | NDC | Surestart | LIFT | PDG | Fairshares
| £000 | £000 | £000 | £000 | Comments | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Manchester Bolton Bury Canal | 667 | 38 | 705 | 0 |  | 667 | 38 | [13 empty] | 705 |  | Brittish Waterways Scheme - USB until s106 monies come in - see s/sheet
Liverpool Road Eccles | 280 | 41 | 321 | 0 |  |  | 80 |  |  |  | 141 | [5 empty] | 100 |  |  |  | 321 |  | Move to CEX?
Detroit Bridge | 500 | 75 | 575 | 235 |  |  | 250 | [10 empty] | 250 |  | 75 | 575 |  | £75K Block 3?
City Academy Access Road | 800 | 0 | 800 | 0 |  |  | 700 | [12 empty] | 100 | 800 |  | £100K to be determined
Investment in Highways | 6810 | 83 | 6893 | 829.3 |  | 6893 | [14 empty] | 6893
Eccles Town Centre (slippage from 04/05) | 589 | 0 | 589 | 6.9 |  |  | 589 | [13 empty] | 589
Chapel Street/URC: -
Economic Development: -
Management of Crescent Police Station | 15 | 0 | 15 | 0 |  |  | 15 | [13 empty] | 15
Business Improvement Grants | 40 | 0 | 40 | 0 |  |  | 40 | [13 empty] | 40
Salford Innovation Park | 20 | 0 | 20 | 0 |  |  | 20 | [13 empty] | 20
Creative Industries Development Services (CIDS) | 22 | 0 | 22 | 0 |  |  | 22 | [13 empty] | 22
Chapel St Business Group | 33 | 0 | 33 | 0 |  |  | 33 | [13 empty] | 33
Programme management contribution | 20 | 0 | 20 | 0 |  |  | 20 | [13 empty] | 20
Cultural Quarter: -
Cultural Development Grants | 25 | 0 | 25 | 0 |  |  | 25 | [13 empty] | 25
Church lighting and DDA works | 40 | 0 | 40 | 0 |  |  | 40 | [13 empty] | 40
Salford Museum contribn to improvement works | 5 | 0 | 5 | 0 |  |  | 5 | [13 empty] | 5
Public Realm Improvements: -
Refurb works Bexley Square | 21 | 0 | 21 | 0 | Balance - cost not known |  | 21 | [13 empty] | 21
Health and Safety works Firestation Square | 29 | 0 | 29 | 0 |  |  | 29 | [13 empty] | 29
Chapel Street Walking Plan: -
CCTV Ph2 | 31 | 0 | 31 | 0 |  |  | 31 | [13 empty] | 31
Signage to Trinity Link (Uni Campus to City Centre) | 19 | 0 | 19 | 0 | Balance - cost not known |  | 19 | [13 empty] | 19
Contribution to URC Business Plan | 180 | 0 | 180 | 0 |  |  | 180 | [13 empty] | 180
Chapel Street/URC (04/05 Slippage) | 167 | 12 | 179 | 0 | £107K CCTV, £31K from above |  | 179 | [13 empty] | 179
Chapel St. Sub-Total | 667 | 12 | 679 | 0 |  | 0 | 679 | 0 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 679
Ordsall Neighbourhood Offices | 277 | 118 | 395 | 0.4 |  |  | 172 | 34 | [5 empty] | 174 |  |  |  |  | 15 |  | 395
LIVIA Community Engagement Programme (CCC) | 100 | 3 | 103 | 16.5 | £125K 06/07 |  |  |  | 103 | [11 empty] | 103
Newlands (LIVIA) | 100 | 0 | 100 | 1.2 | £100K to support CCC + N'lands |  | 100 | [13 empty] | 100
New Leaf Worsley Delph | 240 | -240 | 0 | [17 empty] | 0
Disabled Access Improvements | 250 | 89 | 339 | 47.3 |  |  | 339 | [13 empty] | 339
Dealing with the Disadvantaged | 100 | 0 | 100 | 0 | [12 empty] | 100 |  |  |  | 100
Advanced Fees (see below) | 100 | 0 | 100 | 72.3 |  |  | 100 | [13 empty] | 100
Emerson House | 0 | 100 | 100 | 10.4 |  |  | 20 | [7 empty] | 80 | [5 empty] | 100
Improvement Works Swinton Civic Centre | 0 | 62 | 62 | 0 |  |  | 10 | 7 | [7 empty] | 45 |  |  |  |  | 62
Ordsall Rec Drainage | 0 | 58 | 58 | 0 |  |  |  | 58 | [12 empty] | 58
Disposal costs | 0 | 22 | 22 | 108.3 |  |  | 22 | [13 empty] | 22 |  | Disposal costs netted off receipt
Former Police Station Stanwell Rd | 0 | 735 | 735 | 0 | [15 empty] | 735 | 735 |  | £735k Cap Rcpts or USB
Higher Broughton Community Hub | 0 | 445 | 445 | 0 | [15 empty] | 445 | 445 |  | £445 Cap Rcpts or USB
Demolition Newcroft High School | 0 | 58 | 58 | 0 |  |  | 58 | [13 empty] | 58
NWDA Headroom Projects | 0 | 0 | 0 | 7.2 | [16 empty] | 0 |  | No funding identified
Env and Security Imps Fees Broughton Village | 0 | 0 | 0 | 3.2 | [16 empty] | 0
Salford Shopping Food Retail Development | 0 | 0 | 0 | 61.1 | [16 empty] | 0
Hulme Street Nursery | 300 | 0 | 300 | 0 |  |  | 300 | [13 empty] | 300
Land at Meadow Rd/ Adelphi St | 2800 | 0 | 2800 | 0 |  |  | 2800 | [13 empty] | 2800
04/05 Slippage (not identified above): -
LIVIA (02/03 programme?) | 0 | 69 | 69 | 0 |  |  | 6 |  | 52 | [10 empty] | 11 | 69 |  | £11K Biffa Waste
NWDA Tatton Park | 0 | 26 | 26 | 0 |  |  |  |  | 26 | [11 empty] | 26 |  | Didn't spend all of grant
Trinity Park | 0 | 70 | 70 | 0 |  |  | 38 |  |  |  |  | 20 | [5 empty] | 12 |  |  | 70
Oakwood | 0 | 9 | 9 | 0 | [13 empty] | 9 |  |  | 9
Eccles Town Hall Auditorium | 0 | 4 | 4 | 0 |  |  | 4 | [13 empty] | 4
Countryside Programme | 0 | 10 | 10 | 0 |  |  | 10 | [13 empty] | 10
Barton Strategic Employment Site | 0 | 75 | 75 | 0 |  |  | 75 | [13 empty] | 75
Conserving and developing Ordsall Hall | 0 | 148 | 148 | 17.2 |  |  | 139 | 9 | [12 empty] | 148
SRB | 0 | 1 | 1 | 0 |  |  | 1 | [13 empty] | 1 |  | ???
Quays Maintenance Office Move | 0 | 3 | 3 | 3.5 |  |  | 3 | [13 empty] | 3
Footpath Works | 0 | 279 | 279 | 0 |  |  | 279 | [13 empty] | 279
Relocation TIC | 0 | 1 | 1 | 0 |  |  | 1 | [13 empty] | 1 |  | ???
Proposed adjustments: -
New Deal (from CEX): - | 0 | 0 | 0 | 0 | [16 empty] | 0
Pendleton Church Area Study | 0 | 0 | 0 | 110 | [16 empty] | 0
Highway & Community Safety | 0 | 30 | 30 | 4.4 | [8 empty] | 30 | [7 empty] | 30
Minor Works | 0 | 10 | 10 | 0 | [8 empty] | 10 | [7 empty] | 10
Mini Bus | 0 | 6 | 6 | 0 | [8 empty] | 6 | [7 empty] | 6
Move Liverpool Rd to CEX | 0 | -460 | -460 | 0 |  |  | -180 |  |  |  | -180 | [5 empty] | -100 |  |  |  | -460
TOTAL | 14580 | 1980 | 16560 | 1534.2 |  | 7560 | 6633 | 108 | 181 | 0 | -39 | 20 | 46 | 174 | 80 | 45 | 100 | 271 | 15 | 1366 | 16560 | 16560