| PART 1 (OPEN TO THE PUBLIC) | ITEM NO. |
| --- | --- |

REPORT OF THE STRATEGIC DIRECTOR OF HOUSING AND PLANNING

TO THE LEAD MEMBER FOR PLANNING

ON THE 6TH DECEMBER 2004

TITLE : A5066 Oldfield Road Primary Route Network Resurfacing Scheme

RECOMMENDATIONS :

i) That approval is given to accept the tender of £119,099.64 from Westshield Ltd. for the resurfacing and associated works to the A5066 Oldfield Road (Ordsall Lane to Regent Road)

ii) That approval is given to enter into negotiations with Westshield Ltd. to enable the resurfacing of the A5066 Oldfield Road from Regent Road to Liverpool Street

iii) That an exception to Contractual Standing Order number 4.1 be authorised

EXECUTIVE SUMMARY : The purpose of the report is to provide details of tenders returned for the resurfacing works to A5066 Oldfield Road (Ordsall Lane to Regent Road) and to seek approval to negotiate with the lowest tendering contractor to enable the resurfacing of an adjacent length of the A5066 (Regent Road to Liverpool Street).

BACKGROUND DOCUMENTS :	Report to Lead Members for Development Services and

Corporate Services 14th June 2004  - Approval of 2004/05 Block 3 Transport Capital Programme

ASSESSMENT OF RISK: LOW

THE SOURCE OF FUNDING IS; Transport Capital Programme (Block 3)

LEGAL ADVICE OBTAINED; Not received

FINANCIAL ADVICE OBTAINED; D McAllister

CONTACT OFFICER : D A Dean x3866

WARD(S) TO WHICH REPORT RELATE(S); Ordsall and Langworthy

KEY COUNCIL POLICIES; Safer Salford / Stronger Communities, Local Transport Plan

  - BACKGROUND;

  - At the Lead Member Briefing on the 14th June 2004, approval was given to the Block 3 Transport Capital Programme 2004 / 05.

  - An allocation of £175k is included within the Programme for the resurfacing of the A5066 Oldfield Road from Ordsall Lane to Regent Road.

  - Also included within the Programme was a list of reserve schemes that will form the basis of the programme of works for 2005/06. Included within that list of reserve schemes is the section of the A5066 Oldfield Road from Regent Road to the Crescent.

  - These resurfacing schemes have been identified from the results of the primary route condition surveys.

  - Works to the section of the A5066 Oldfield Road from Ordsall Lane to Regent Road will include resurfacing of the carriageways and footways. There are no records as to when this section of the A5066 was last resurfaced and the carriageway in particular is in poor condition

  - A resurfacing scheme to the A5066 Oldfield Road from Regent Road to the Crescent was carried out in 1993. This scheme excluded resurfacing of the junction with Liverpool Street and terminated approximately 100m north of the junction with Regent Road. The Liverpool Street junction and the area around the Regent Road junction are now considered to be in poor condition and in need of repair. This work was to be carried out as part of the 2005/06 programme.

  - However, it has been confirmed recently with Valley and Vale Properties Ltd. that resurfacing works to the A5066 Oldfield Road at the junction with Liverpool Street will be undertaken at the Developer’s expense as part of a Section 278 (Highways Act 1980) Agreement for the proposed Middlewood Locks Development. It is anticipated that this scheme will be on site in 2005.

  - It is considered appropriate therefore, that the remaining length of the A5066 around the junction with Regent Road be brought forward and included within the current programme of works for delivery this financial year. It is estimated that this additional work will cost approximately £120k.

  - It is recommended that detailed design be undertaken and that negotiations be entered into to determine if it is practical and economical to carry out this additional works as a variation to the proposed contract with Westshield Ltd.

  - It is expected that this approach will minimise the disruption to residents and traffic. Reductions in the time taken to procure a further suitable contractor should bring cost benefit to the Council and enable the works to be carried out in this financial year

  - A report seeking approval to the quotation agreed with Westshield Ltd will be submitted at a future meeting.

2.0	DETAILS;

  - The work to the A5066 Oldfield Road from Ordsall Lane to Regent Road comprises;

- Resurfacing of the carriageway.

- Rekerbing and reconstruction of the footways in bituminous materials

  - The additional work at the Oldfield Road / Regent Road junction will comprise;

- Resurfacing the junction of Oldfield Road / Regent Road

- Resurfacing Oldfield Road for approximately 100m north of the junction with Regent Road

- Rekerbing and reconstruction of the footways in bituminous materials

- FINANCIAL IMPLICATIONS

3.1 There is an allocation of £175k within the Block 3 Transport Capital Programme for this scheme. However, it is anticipated that there will be some slippage on other schemes within the programme and that additional funding is available to extend the works as recommended, estimated at £120k.

  - Tenders for the resurfacing of the A5066 Oldfield Road from Ordsall Lane to Regent Road were invited from the following;

- Aggregate Industries UK Ltd

- City Highways

- Hanson Quarry Products Ltd

- RMC Surfacing  Ltd

- Tarmac Ltd

- Westshield Ltd

  - Tenders have been returned and checked and the figures received are as follows;

- £119,099.64	 (corrected from £119,461.98)

- £120,533.10 	 (corrected from £109,575.51)

- £134,084.60

- £142,628.65

- £149,482.41

- £219,006.06

3.4	The cost of the scheme as tendered will be;

Works cost 	£119,099.64

Fees		£  13,527.30

Total 		£132,626.94

3.5 	It is recommended that the scheme for resurfacing of the carriageway and associated works to the A5066 Oldfield Road from Ordsall Lane to Regent Road be awarded to Westshield Ltd. for the sum of £119,099.64.

3.6 It is estimated that the additional work at the junction of Oldfield Road and Regent Road, subject to negotiation will cost approximately £120k.

4.0 CONCLUSIONS;

4.1 Resurfacing of the A5066 Oldfield Road from Ordsall Lane to Regent Road has been identified as a priority from the structural condition surveys. It is proposed that Westshield Ltd. carry out the improvement works. It is also proposed that the scheme be extended to include works across the junction of Regent Road.

Malcolm Sykes

# Strategic Director of Housing and Planning

Updated : 31/10/03