## Sheet1
Cost | Scheme Name | Current | Cap | Paid | Start | Start | Start | Out to | Start | Finish | Paid | Forecast |  |  | Total | Comments
Code |  | Respon- | Prog | to-date | Prelim' | Consult - | Detailed | Tender | on Site | on Site | to | Spend |  |  | Spend
|  | sibility | 06/07 | in 06/07 | Design | ation | Design |  |  |  | 2006-03-01 | 06/07 | 07/08 | Beyond
1. Major Highway Schemes
D00003 | Cadishead Way, Stage 1 | DF | 75 | 0 | - | - | - | - | 1991-01-01 | 1992-03-01 | 9463 | 0 | 75 | 0 | 9538 | Scheme complete
D00004 | Cadishead Way, Stage 2 | DD | 2491 | 261 | - | - | - | - | 2004-02-04 | 2005-09-01 | 15570 | 2491 | 1315 | 0 | 19376 | Scheme complete
D00005 | Trinity Way, Stage 3 | PG | 870 | 0 | - | - | - | - | 2001-02-01 | 2004-11-04 | 26665 | 870 | 0 | 0 | 27535 | Scheme complete
| Sub-Total |  | 3436 | 261 | [6 empty] | 51698 | 3361 | 1390 | 0 | 56449
2. Local Safety Schemes
D00101 | Anti-skid Surfacing Programme | SW | 50 | 2 | - | - | - | - | 2006-04-01 | 2007-03-01 | 0 | 50 | 50 | 50 | 150 | On-going programme
D00103 | Accident Investigation | AD | 20 | 2 | - | - | - | - | 2006-04-01 | 2007-03-01 | 0 | 20 | 20 | 20 | 60 | General fund for investigations/maintenance
D00104 | White Lining Programme | SF | 15 | 1 | - | - | - | - | 2006-04-01 | 2007-03-01 | 0 | 15 | 15 | 15 | 45 | On-going programme
D00105 | Road Safety Strategy | AD | 5 | 1 | - | - | - | - | 2006-04-01 | 2007-03-01 | 0 | 5 | 5 | 5 | 15 | AD to produce in 2006/07
D00119 | Barton Lane Ped Improvements | SF | 0 | 3 | 2004-08-01 | 2004-09-01 | 2004-10-01 | 2005-11-01 | 2006-01-01 | 2006-03-01 | 38 | 3 | 0 | 0 | 41 | Complete
D00141 | Moorside Rd/Wardley Ind Estate Area Sch | SF | 50 | 4 | 2004-04-01 | 2005-05-01 | 2005-06-01 | 2005-12-01 | 2006-03-01 | 2006-06-01 | 64 | 50 | 50 | 0 | 164 | Scheme on site
D00142 | B5229 Monton Centre Scheme | AD | 240 | 6 | 2004-07-01 | 2005-08-01 | 2006-02-01 | 2006-05-01 | 2006-10-01 | 2007-01-01 | 23 | 240 | 140 | 0 | 403 | Diversion route for closure of Worsley Rd
D00148 | A6 Chorley Road Route Scheme | SF | 0 | 2 | 2006-05-01 | 2006-06-01 | 2006-06-01 | 2006-09-01 | 2006-10-01 | 2007-01-01 | 4 | 110 | 0 | 0 | 114 | Awaiting design brief
D00150 | Silver Street Area, Irlam, Consultation | PA | 0 | 0 | 2006-04-01 | 2006-06-01 | 2006-11-01 | 2007-01-01 | 2007-04-01 | 2007-06-01 | 0 | 10 | 0 | 0 | 10 | Consultation only in 2006/07
D00173 | New Lane, Winton | SF | 0 | 0 | 2004-06-01 | 2004-07-01 | 2004-10-04 | 2005-01-05 | 2005-02-05 | 2005-06-01 | 89 | 0 | 0 | 0 | 89 | Scheme complete
D00175 | Amendments to Early T Calming Schemes | PG | 0 | 0 | 2004-07-04 | 2004-08-04 | 2004-09-04 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 47 | 0 | 0 | 0 | 47 | Includes Littleton Rd & Hilton Lane.
D00178 | Greenleach Lane, Worsley | SF | 0 | 4 | 2004-07-01 | 2004-08-04 | 2005-01-05 | 2005-10-01 | 2006-06-01 | 2006-05-01 | 110 | 10 | 0 | 0 | 120 | Work will tie in with re-surfacing scheme
D00179 | Oxford Road Remedial Traffic Calming | SF | 0 | 0 | 2004-06-04 | 2004-08-04 | 2004-09-04 | 2004-12-04 | 2005-02-05 | 2005-04-05 | 180 | 0 | 0 | 0 | 180 | Scheme complete
D00180 | Langley Rd Speed Reduction Measures | AD | 0 | 0 | 2005-04-01 | 2005-05-01 | 2005-08-01 | 2005-10-01 | 2005-01-01 | 2005-02-01 | 68 | 0 | 0 | 0 | 68 | Scheme complete
D00181 | Light Oaks Primary Safer Routes | SS | 38 | 0 | 2005-04-01 | 2005-10-01 | 2005-11-01 | 2006-04-01 | 2006-09-01 | 2006-10-01 | 0 | 38 | 0 | 0 | 38 | Awaiting finish of sufacing scheme
D00182 | St Georges High School Safer Routes | SS | 20 | 1 | 2005-04-01 | 2005-10-01 | 2005-11-01 | 2006-04-01 | 2006-08-01 | 2006-09-01 | 1 | 20 | 0 | 0 | 21 | Awaiting quote
D00183 | Station Rd/Bolton Rd Ped'n Facilities | AD | 75 | 1 | 2006-05-01 | 2006-08-01 | 2007-01-01 | 2007-03-01 | 2007-07-01 | 2007-09-01 | 11 | 75 | 0 | 0 | 86 | Awaiting instruction to go ahead with design
D00184 | Gerald Road Area Traffic Calming | SF | 65 | 8 | - | 2005-06-01 | 2005-10-01 | 2006-01-01 | 2006-03-01 | 2006-06-01 | 43 | 65 | 0 | 0 | 108 | Scheme on site
D00185 | Partington Ln/Worsley Rd Junction | SF | 0 | 0 | 2005-07-01 | 2005-08-01 | 2005-10-01 | 2005-12-01 | 2006-03-01 | 2006-04-01 | 3 | 0 | 0 | 0 | 3 | Scheme complete
D00186 | A666 / M60 J'n Cyclist Awareness | AD | 35 | 0 | 2006-05-01 | 2006-08-01 | 2007-01-01 | 2007-03-01 | 2007-07-01 | 2007-09-01 | 0 | 35 | 0 | 0 | 35 | Improvements to signing & st lighting
D00187 | Parrin Lane/Monton Fields St Lighting | PA | 20 | 0 | 2006-06-01 | 2006-07-01 | 2006-09-01 | 2006-11-01 | 2007-01-01 | 2007-02-01 | 0 | 20 | 0 | 0 | 20 | Improvements to signing
D00189 | Motorcycle Casualty Reduction Initiative | PA | 0 | 0 | 2005-10-01 | - | 2005-11-01 | - | 2006-02-01 | 2007-03-01 | 4 | 0 | 0 | 0 | 4 | Scheme complete
D00190 | Captain Fold Lane - Dealing with Disadvantage | AD | 0 | 0 | - | - | 2005-09-01 | 2005-10-01 | 2005-10-01 | 2005-11-01 | 133 | 0 | 0 | 0 | 133 | Scheme from D00176 - scheme complete
D00191 | Traffic Calming Priority Ranking Work | AD | 0 | 0 | 2006-07-01 | - | - | - | - | 2006-10-01 | 0 | 10 | 0 | 0 | 10 | One-off payment to consultant to undertake work
D00200 | Cow Lane Safer Routes to School | PA | 0 | 0 | 2006-04-01 | 2006-06-01 | 2006-09-01 | 2006-10-01 | 2007-01-01 | 2007-02-01 | 0 | 20 | 0 | 0 | 20 | Improving condition of Cow Lane footpath
D00201 | Mass Action Sites | AD | 0 | 0 | 2006-06-01 | 2006-08-01 | 2006-11-01 | 2007-01-01 | 2007-03-01 | 2007-04-01 | 0 | 25 | 0 | 0 | 25 | Low cost remedial signing improvements
| Sub-Total |  | 633 | 35 | [6 empty] | 818 | 821 | 280 | 90 | 2009
3. Bridge Assessment and Strengthening
D00500 | Bridge Inspections and Assessments | MG | 0 | 0 | - | - | - | - | 2006-04-01 | 2007-03-01 | 0 | 0 | 0 | 0 | 0 | On-going Programme
D00501 | Bridges general | MG | 10 | 0 | - | - | - | - | 2006-04-01 | 2007-03-01 | 0 | 10 | 10 | 10 | 30 | Various Small Works
D00503 | Subways | MG | 5 | 0 | - | - | - | - | 2006-04-01 | 2007-03-01 | 0 | 5 | 5 | 5 | 15 | On-going Programme
D00510 | Network Rail Bridges | MG | 0 | 0 | 2005-08-01 | - | 2005-10-01 | - | - | - | 90 | 0 | 0 | 0 | 90 | Design work only in 05/06
D00512 | Eccles Old Road Underpass | MG | 0 | 0 | 2003-09-03 | 2003-09-03 | 2003-09-03 | 2003-12-03 | 2006-04-01 | 2007-03-01 | 85 | 0 | 0 | 0 | 85 | Scheme complete
D00524 | Pendleton Roundabout Parapets Ph1 | MG | 0 | 0 | - | - | - | - | 2003-12-01 | 2004-05-01 | 286 | 0 | 0 | 0 | 286 | Scheme complete
D00525 | Railtrack Incursion Works | MG | 0 | 1 | - | - | - | - | 2003-10-01 | 2006-03-01 | 175 | 1 | 0 | 0 | 176 | Awaiting site start at Broughton Rd
D00527 | Culvert Safety Improvement Programme | IT | 20 | 0 | - | - | - | - | 2004-09-01 | 2006-03-01 | 29 | 20 | 20 | 16 | 85 | Managed by Ian Thew
D00531 | Eccles Road Footbridge Painting | MG | 0 | 0 | 2004-04-04 | 2004-04-04 | 2004-04-04 | 2004-05-04 | 2004-07-04 | 2004-10-04 | 51 | 0 | 0 | 0 | 51 | Scheme complete
D00532 | Hough Lane Footbridge | MG | 0 | 1 | 2004-05-04 | 2004-05-04 | 2004-05-04 | 2004-07-04 | 2004-08-04 | 2004-10-04 | 162 | 1 | 0 | 0 | 163 | Scheme complete
D00533 | Stott Lane Railway Bridge | MG | 40 | 0 | 2004-08-04 | 2004-08-04 | 2007-12-01 | - | - | - | 0 | 10 | 0 | 0 | 10 | Detailed design in Progress
D00534 | Heywood Way Subway Infill | MG | 0 | 0 | [6 empty] | 0 | 0 | 0 | 135 | 135 | Scheme awaiting decisions re Precinct | bar: 2006-06-01 to 2007-04-01
D00535 | Pendleton Roundabout Parapets Ph2 | MG | 0 | 0 | 2004-07-01 | 2004-07-01 | 2004-07-01 | 2004-08-01 | 2005-01-05 | 2005-03-05 | 247 | 0 | 0 | 0 | 247 | Scheme complete
D00536 | East Ordsall Lane Canal Bridge | MG | 145 | 0 | 2004-09-01 | 2004-09-01 | 2005-02-01 | 2005-08-01 | 2006-06-01 | 2007-03-01 | 60 | 225 | 0 | 0 | 285 | Part of canal re-opening works.
D00537 | Eccles Old Road Subway Drainage | MG | 0 | 4 | 2005-09-01 | 2005-09-01 | 2005-10-01 | 2006-01-01 | 2006-03-01 | 2006-03-01 | 20 | 4 | 0 | 0 | 24 | Scheme out to tender
D00538 | Swinton Subway (Moorside Ramp) | MG | 0 | 0 | 2005-09-01 | 2005-09-01 | 2005-09-01 | 2006-04-01 | 2006-06-01 | 2006-08-01 | 2 | 0 | 0 | 0 | 2 | Detailed design in Progress
D00539 | Little Hulton Station Bridge | MG | 300 | 0 | 2005-08-01 | 2005-08-01 | 2005-09-01 | 2005-11-01 | 2006-01-01 | 2006-03-01 | 4 | 300 | 0 | 0 | 304 | Detailed design in Progress
D00540 | West/East Bridges, Pendleton Roundabout | MG | 0 | 0 | 2005-06-01 | 2005-06-01 | 2005-06-01 | 2005-10-01 | 2006-02-01 | 2006-04-01 | 3 | 0 | 0 | 0 | 3 | Scheme now combined with D00543
D00541 | Monton Canal Bridge | MG | 0 | 0 | 2005-01-01 | 2005-02-01 | 2005-03-01 | 2005-07-01 | 2005-08-01 | 2005-10-01 | 67 | 0 | 0 | 0 | 67 | Scheme complete
D00542 | Mariners Canal Central Footbridge | MG | 0 | 0 | 2005-01-01 | 2005-01-01 | 2005-02-01 | 2005-04-01 | 2005-05-01 | 2005-07-01 | 31 | 0 | 0 | 0 | 31 | Scheme complete
D00543 | Pendleton Roundabout Retaining Walls | MG | 10 | 78 | 2005-08-01 | 2005-08-01 | 2005-08-01 | 2005-10-01 | 2006-02-01 | 2006-04-01 | 212 | 78 | 0 | 0 | 290 | Scheme on site
D00544 | Centenary Bridge Abutments | MG | 0 | 0 | 2004-11-01 | 2004-11-01 | 2004-12-01 | 2005-01-01 | 2005-03-01 | 2005-03-01 | 8 | 0 | 0 | 0 | 8 | Scheme complete
D00545 | Footway Protection to Network Rail Bridges | SM | 300 | 1 |  |  | 2006-03-01 | 2006-08-01 | 2006-10-01 | 2007-03-01 | 0 | 300 | 0 | 0 | 300 | Programme for 2006/07
D00546 | Colliery Railway Bridge, East Lancs Rd | SM | 50 | 0 |  |  | 2006-08-01 | 2006-11-01 | 2007-01-01 | 2007-03-01 | 0 | 50 | 0 | 0 | 50
D00547 | East Lancs Rd Footbridge Feasibility | MG | 0 | 0 | 2005-03-01: 2006-10-01 | 0 | 20 | 0 | 0 | 20
D00548 | Gerald Road Footbridge Refurbishment | SM | 0 | 0 |  |  | 2006-06-01 | 2006-08-01 | 2006-10-01 | 2006-12-01 | 0 | 100 | 0 | 0 | 100
D00549 | Blackfriars Footbridge Repainting | SM | 0 | 0 |  |  | 2006-06-01 | 2006-07-01 | 2006-09-01 | 2006-10-01 | 0 | 65 | 0 | 0 | 65
| Sub-Total |  | 880 | 85 | [6 empty] | 1532 | 1189 | 35 | 15 | 2771
4. Principal Road Structural Maintenance
D00601 | A57 Liverpool Road, Cadishead | - | 0 | 0 | - | - | 2006-06-01 | 2006-09-01 | 2006-10-01 | 2007-01-01 | 1 | 300 | 0 | 0 | 301 | To commence after Cadishead Way Scheme
(New Moss Road - Fir Street)
D00605 | BVPI Surveys | SW | 30 | 10 | - | - | - | - | 2003-08-01 | 2008-03-01 | 162 | 30 | 0 | 30 | 222
D00606 | A57 Liverpool Rd | - | 200 | 1 | - | - | 2006-06-01 | 2006-09-01 | 2006-10-01 | 2007-01-01 | 8 | 200 | 0 | 0 | 208 | Survey in progress
(Boysnope - Barton Moss Road)
D00608 | Principal Road Maintenance - General | - | 20 | 0 | - | - | - | - | 2004-04-01 | 2005-03-01 | 18 | 20 | 20 | 20 | 78 | Payment of retentions, etc
D00610 | A575 Walkden Road | DD | 0 | 0 | - | - | - | - | 2004-01-01 | 2004-06-01 | 180 | 0 | 0 | 0 | 180 | Scheme complete
(Manchester Road - Park Road)
D00614 | Structural Maintenance of Minor Roads | SW | 0 | 1 | - | - | - | - | 2003-10-01 | 2005-03-01 | 792 | 1 | 0 | 0 | 793
D00616 | A56 Bury New Rd | DD | 0 | 0 | - | - | - | - | 2003-11-01 | 2005-01-05 | 12 | 0 | 0 | 0 | 12 | Scheme complete, previously as part of
| (Boundary to Moor Lane) | [14 empty] | A56 QBC scheme.
D00617 | A5066 Adelphi Street & Silk Street | DD | 0 | 0 | - | - | 2004-07-01 | 2004-09-01 | 2004-11-01 | 2005-03-05 | 375 | 0 | 0 | 0 | 375 | Scheme complete
D00618 | A5066 Oldfield Road | NW | 0 | 0 | - | - | 2004-08-01 | 2004-10-01 | 2005-01-05 | 2005-03-01 | 139 | 0 | 0 | 0 | 139 | Scheme complete
(Ordsall Lane - Regent Road)
D00619 | A5066 Oldfield Road | DD | 0 | 0 | - | - | 2004-10-01 | 2004-12-01 | 2005-01-01 | 2205-03-01 | 164 | 0 | 0 | 0 | 164 | Scheme complete
(Regent Road - Crescent)
D00620 | A575 Cleggs Lane | DD | 0 | 14 | - | - | 2004-12-04 | 2005-03-01 | 2005-08-01 | 2005-11-01 | 483 | 15 | 0 | 0 | 498 | Scheme complete
(A6 - Bolton Boundary)
D00629 | Street Lighting Inventory Work | SC | 60 | 0 | - | - | - | - | - | 2006-12-01 | 0 | 60 | 0 | 0 | 60 | Detailed inventory required by DfT
D00630 | Langworthy Road | DD | 0 | 0 | 2005-04-01 | - | 2005-05-01 | 2005-08-01 | 2005-10-01 | 2006-01-01 | 323 | 0 | 0 | 0 | 323 | Scheme complete
(Liverpool Street - Eccles New Road)
D00631 | Albion Way (Broad St - Regent Rd) | DD | 0 | 0 | 2006-05-01 | - | 2006-06-01 | 2006-09-01 | 2006-11-01 | 2007-02-01 | 1 | 0 | 550 | 0 | 551 | Scheme on hold
D00632 | Worsley Road | DD | 470 | 3 | 2005-06-01 | - | 2005-07-01 | 2006-02-01 | 2006-07-01 | 2006-10-01 | 20 | 450 | 0 | 0 | 470 | In detailed design
(East Lancs Rd - Ringlow Park Rd)
D00633 | A666 Manchester Road | DD | 10 | 2 | 2005-05-01 | - | 2005-06-01 | 2005-11-01 | 2006-01-01 | 2006-03-01 | 358 | 10 | 0 | 0 | 368 | Scheme complete
(Clifton House Road - Manley Avenue)
D00634 | Cadishead Way Stage 1 Repairs | PRG | 0 | 0 | - | - | - | - | 2005-08-01 | 2005-09-01 | 276 | 0 | 0 | 0 | 276 | Scheme complete
D00635 | Street Lighting in support of H I Prog | SC | 0 | 0 | - | - | - | - | 2005-09-01 | 2007-03-01 | 52 | 30 | 0 | 0 | 82
D00636 | Cadishead Way Stage 1 Repairs (Phase 2) | PRG | 250 | 3 | - | - | - | 2006-08-01 | 2006-09-01 | 2006-11-01 | 0 | 250 | 0 | 0 | 250
| Sub-total |  | 1040 | 34 | [6 empty] | 3363 | 1366 | 570 | 50 | 5349
5. Schemes To Assist Public Transport
D00703 | A56 Quality Bus Corridor | DD | 0 | 1 | - | - | - | - | 2003-11-01 | 2005-01-05 | 669 | 1 | 0 | 0 | 670 | Scheme complete
D00708 | Central Station Study | DF | 0 | 0 | [6 empty] | 39 | 0 | 0 | 0 | 39 | Possible further contribution needed | bar: 2005-01-01 to 2005-10-01
D00709 | A57 Irlam Bus Stop Improvements | DF | 81 | 1 | - | - | 2005-09-01 | 2005-11-01 | 2006-01-01 | 2007-04-01 | 50 | 120 | 0 | 0 | 170 | Spend dependent on D00929, incl Moss Vale
D00710 | Rail Station Access Improvements | DF | 0 | 0 | 2006-07-01 | 2006-09-01 | 2006-10-01 | 2006-11-01 | 2007-01-01 | 2007-03-01 | 0 | 20 | 20 | 20 | 60
| Sub-total |  | 81 | 2 | [6 empty] | 758 | 141 | 20 | 20 | 939
6. Schemes To Assist Cycling
D00803 | Barton Cycling Facilities | TL | 0 | 1 | 2004-04-01 | 2004-06-01 | 2004-07-01 | 2005-01-05 | 2005-03-05 | 2005-05-05 | 414 | 1 | 0 | 0 | 415 | Scheme complete
D00805 | Cycle Parking Facilities | PC | 10 | 1 | 2004-04-01 | 2004-06-01 | 2004-07-01 | 2004-08-01 | 2004-09-01 | 2005-03-01 | 10 | 40 | 10 | 10 | 70 | Ongoing programme
D00806 | Sustrans Routes | PG | 100 | 1 | 2004-05-01 | 2004-07-01 | 2005-04-01 | 2005-06-01 | 2005-07-01 | 2005-09-01 | 54 | 200 | 150 | 150 | 554 | Scheme on site
D00807 | Cycling Projects Grant Fund | DF | 30 | 0 | 2004-08-01 | 2004-09-01 | 2004-10-01 | 2005-01-05 | 2005-02-05 | 2005-03-01 | 29 | 30 | 50 | 50 | 159 | Bike Stations Initiative
D00808 | Tyldesley Loopline Surfacing Improv'ts | NO | 60 | 0 | 2005-01-05 | 2005-02-05 | 2005-02-05 | 2005-01-01 | 2006-07-01 | 2006-09-01 | 52 | 60 | 0 | 0 | 112 | Cost £160k, Sustrans now contributed £40k
D00809 | Cycle Parking Facilities at Schools | SG | 75 | 0 | [6 empty] | 45 | 75 | 75 | 0 | 195 | Contributory funding to schools | bar: 2004-08-01 to 2005-03-01
D00810 | Irwell Walk, Charlestown, New Deal Cont' | DF | 0 | 0 | [6 empty] | 15 | 0 | 0 | 0 | 15 | Contributory funding to Groundwork | bar: 2004-08-01 to 2005-03-01
D00811 | A580 East Lancs Rd (To Wigan Boundary) | PC | 10 | 2 | 2005-05-01 | - | 2005-07-01 | 2005-08-01 | 2006-06-01 | 2006-07-01 | 2 | 10 | 0 | 0 | 12 | Awaiting quote
D00812 | Bridgewater Way Contribution | DF | 75 | 0 | [6 empty] | 0 | 75 | 0 | 0 | 75 | Contribution to project in 2006/07. | bar: 2004-08-01 to 2005-03-01
D00813 | A56 Bury New Road Shared Facilities | LE | 0 | 0 | 2006-05-01 | 2006-07-01 | 2006-04-01 | 2006-06-01 | 2006-07-01 | 2006-09-01 | 0 | 25 | 0 | 0 | 25
D00814 | Irlams O'th Height to Pendleton Roundabout | LE | 0 | 0 | 2006-05-01 | 2006-07-01 | 2006-08-01 | 2006-11-01 | 2007-01-01 | 2007-03-01 | 0 | 30 | 0 | 0 | 30
| Sub-total |  | 360 | 5 | [6 empty] | 621 | 546 | 285 | 210 | 1662
7. Other Minor Works
D00901 | GM Local Transport Plan | DF | 40 | 0 | - | - | - | - | 1999-04-01 | 2005-03-01 | 168 | 40 | 40 | 40 | 288 | AGMA contribution
D00902 | Salford's Green Transport Plan | SG | 25 | 0 | 2004-07-01 | 2004-09-01 | 2004-10-01 | 2004-12-01 | 2005-01-01 | 2005-03-01 | 73 | 25 | 25 | 25 | 148 | Car park & Swinton Study in 05/06
D00903 | M60/ PRN Signing | NA | 0 | 0 | - | - | - | - | 1998-04-01 | 2005-03-01 | 145 | 0 | 0 | 0 | 145 | Scheme complete
D00909 | AGMA Countywide Advertising | DI | 0 | 0 | - | - | - | - | 2000-04-01 | 2005-03-01 | 25 | 5 | 0 | 0 | 30 | On-going contribution to AGMA initiatives
D00912 | Disabled Facilities at Pedestrian Crossings | JH | 0 | 6 | - | - | - | - | 2003-04-01 | 2005-03-01 | 554 | 100 | 0 | 0 | 654 | Ongoing programme - needs identifying
D00918 | Chapel St Pedestrian Route Improve'ts | JP | 0 | 0 | - | - | - | 2004-06-01 | 2004-08-01 | 2004-10-01 | 71 | 3 | 0 | 0 | 74 | Scheme complete
D00923 | Little Moss Lane Works | DAD | 50 | 5 | - | - | - | - | 2006-07-01 | 2006-09-01 | 376 | 50 | 0 | 0 | 426 | Complete (apart from Worsley St)
D00924 | Miscellaneous SRTS Works | SG | 5 | 0 | - | - | - | - | 2003-08-01 | 2005-03-01 | 4 | 5 | 5 | 5 | 19 | Linked with School Travel Plans
D00925 | GMTU Non-core Modelling Work | JH | 10 | 0 | - | - | - | - | 2003-06-01 | 2005-03-01 | 9 | 10 | 0 | 0 | 19 | PTE Study into Trafford Park 05/06
D00926 | Public Rights of Way Signing | NO/ST | 15 | 0 | 2004-07-01 | 2004-08-01 | 2004-10-01 | 2004-12-01 | 2005-01-01 | 2006-03-01 | 33 | 15 | 0 | 0 | 48 | Works in progress
D00927 | Public Rights of Way Improvements | NO/ST | 0 | 3 | 2004-06-01 | 2004-07-01 | 2004-08-01 | 2004-10-01 | 2004-12-01 | 2005-03-01 | 3 | 0 | 0 | 0 | 3 | 05/06 spend now coded as D00938
D00928 | Barton Rd/Barton Ln J'n Improvement | JP | 0 | 0 | 2004-06-01 | 2004-07-01 | 2004-08-01 | 2004-10-01 | 2005-01-05 | 2005-03-05 | 248 | 0 | 0 | 0 | 248 | Scheme complete
D00929 | Liverpool Rd, Cadishead, Town Centre | DF | 0 | 0 | 2006-04-01 | 2006-06-01 | 2006-08-01 | 2006-10-01 | 2007-01-01 | 2007-05-01 | 0 | 210 | 0 | 0 | 210 | Initial scheme design in progress
D00930 | Oaklands Road | PG | 0 | 0 | 2007-01-01: 2004-10-04; 2007-05-01: 2004-12-04 | 24 | 0 | 0 | 0 | 24 | Scheme complete - total cost £73k (New Deal)
D00931 | Chapel St/New Bailey St Ped Facilities | MWK | 0 | 0 | 2004-09-04 | 2004-10-04 | 2004-10-05 | 2004-12-05 | 2005-02-05 | 2005-04-05 | 38 | 0 | 0 | 0 | 38 | Scheme complete
D00932 | Station Road Puffin Crossing | PC | 0 | 0 | 2004-06-04 | 2004-09-04 | 2004-10-04 | 2004-12-04 | 2005-08-01 | 2005-09-01 | 64 | 0 | 0 | 0 | 64 | Scheme complete
D00934 | Dropped Kerbs & Tactile Paving Programme | NO | 0 | 11 | - | - | - | - | 2005-12-01 | 2006-03-01 | 79 | 100 | 0 | 0 | 179 | Scheme on Site - ongoing prog
D00935 | A6 Chorley Rd / Moorside Rd Ped' Facilities | MWK | 0 | 0 | [6 empty] | 0 | 50 | 0 | 0 | 50
D00936 | Chapel Street Traffic Management | DF | 0 | 0 | 2004-04-01 | 2005-05-01 | 2006-08-01 | 2006-11-01 | 2007-01-01 | 2007-12-01 | 0 | 100 | 0 | 0 | 100 | Awaiting feasibility assessment
D00938 | Roe Green Loopline - PROW | NO | 0 | 2 | - | - | 2005-10-01 | 2005-12-01 | 2006-08-01 | 2006-11-01 | 23 | 240 | 0 | 0 | 263 | Detailed design in progress
D00939 | In Town Without My Car | SL | 30 | 0 | - | - | - | - | 2005-09-01 | 2005-09-01 | 30 | 30 | 0 | 0 | 60
D00940 | Fairhills Rd Puffin Crossing Contribution | PRG | 0 | 0 | - | - | - | - | 2005-09-01 | 2005-10-01 | 0 | 0 | 0 | 0 | 0 | Scheme complete
D00941 | Liverpool Rd / Cadishead Way Gyratory | DF | 0 | 0 | 2006-06-01 | 2006-08-01 | 2006-10-01 | 2007-01-01 | 2007-04-01 | 2007-06-01 | 0 | 5 | 0 | 0 | 5 | Feasibility in 2006/07
| Sub-total |  | 175 | 27 | [6 empty] | 1967 | 988 | 70 | 70 | 3095
| GRAND TOTAL |  | 6605 | 449 | [6 empty] | 60757 | 8412 | 2650 | 455 | 72274 | Minor works allocation is £3.979m for 2006/07