S A L F O R D   C I T Y   C O U N C I L

Housing and Planning Directorate

2006/07 BLOCK 3  -  TRANSPORT CAPITAL PROGRAMME

# Summary as at 5 June 2006

### SUMMARY OF BLOCK 3 PROGRAMME

#### Local Transport Capital Expenditure Settlement for 2006/07				£3.979m

Total Block 3 Resources Available (Approved Capital Programme  -  See Below)		£8.067m

Forecast Spend										£8.412m

Actual Spend											£0.449m

Forecast Spend to Resources Available 							    104%

Forecast Spend to Resources Available  -  Excluding MSIRR & Cadishead Way 		    127%

Actual Spend to Resources Available  							        6%

Actual Spend to Resources Available  -  Excluding MSIRR & Cadishead Way 		        5%

Year Elapsed 											      23%

| ###### Block 3 Transport Capital Programme ###### Expenditure Details (£000s) | Accepted Expenditure | Approved Capital Programme | Forecast Spend | Actual Spend |
| --- | --- | --- | --- | --- |
| Major Schemes ## MSIRR Cadishead Way, Stage 2 Cad Way, Stage 2 - 05/06 Resources Brought Fwd | - - - | - - 4088 | 870 - 2491 | 0 - 261 |
| Bridge Assessment & Strengthening Principal Road Structural Maintenance | } 1719 } | 880 1040 | 1189 1366 | 85 34 |
| ##### Integrated Minor Works - Local Safety Schemes - Schemes to Assist Public Transport - Schemes to Assist Cycling - Other Minor Works | } } 2260 } } | } 633 } 81 } 370 } 975 | 821 141 546 988 | 35 2 5 27 |
| ##### TOTALS | 3979 | 8067 | 8412 | 449 |

## HP/DF/T/8/8						     		                             6 June 2006