| PART 1 | ITEM NO. |
| --- | --- |

REPORT OF THE STRATEGIC DIRECTOR FOR SUSTAINABLE REGENERATION

TO THE LEAD MEMBER FOR PLANNING

FOR BRIEFING ON 6th October 2009

FOR DECISION ON 20th October 2009

TITLE:	Salford Local Development Scheme 2009/10 – 2011/12 Revision A

RECOMMENDATION:

The Lead Member for Planning is recommended to approve the Local Development Scheme 2009/10 – 2011/12 Revision A for submission to the Secretary of State;

EXECUTIVE SUMMARY: The last Local Development Scheme 2009/10 – 2011/12 was approved in August 2009.  It is now necessary to amend this to add the Greater Manchester Joint Minerals Development Plan Document and to make a minor amendment to the production timetable for the Core Strategy. This report sets out the proposed revision of the Local Development Scheme and seeks its approval for submission to the Secretary of State.

BACKGROUND DOCUMENTS:	None

(Available for public inspection)

KEY DECISION:	Yes

| 1.0 | Background |
| --- | --- |
| 1.1 | The Local Development Scheme describes what the city council is going to do to prepare new and revised local development documents for the city over a 3-year period. It contains the key milestones for the production of these documents. The Local Development Scheme must be submitted to the relevant Government Office for formal approval by the Secretary of State. The council’s performance against these timetables is monitored and therefore the Local Development Scheme is a key document for the council in terms of performance management. |
| 1.2 1.3 | The current Local Development Scheme (2009/10 – 2011/12) was approved by the Secretary of State in August 2009. Since its publication agreement has been reached at AGMA level to produce the Greater Manchester Joint Minerals Development Plan Document. It is therefore now necessary to revise the Local Development Scheme to incorporate the information and timetable for this Development Plan Document. In addition it is necessary to amend the Core Strategy timetable to reflect the fact that consultation on the Preferred Option will now be between November 2009 and January 2010. |
| 2.0 | Details |
|  | Core Strategy |
| 2.1 | Work has been continuing on the production of the Core Strategy. Additional time has been required to secure adequate internal consultation on and agreement to the preferred option documentation, and consequently the public consultation on the document has been delayed a month. It will now run from November 2009 to January 2010. The later stages of the document’s production are not affected by this change. However whilst revising the Local Development Scheme to accommodate a new Development Plan Document it is considered expedient to revise the timetable for the Core Strategy to reflect this change. |
| 2.2 2.3 2.4 | Greater Manchester Joint Minerals Development Plan Document Agreement was reached by AGMA at the end of August for the production of a Greater Manchester Joint Minerals Development Plan Document. Work will commence on this document in November 2009 and therefore it is necessary to amend the Local Development Scheme immediately to incorporate the information and timetables relating to its production. Proposals Map The Proposals Map needs to be updated every time a Development Plan Document is adopted. Given the addition of a new Development Plan Document within the Local Development Scheme, the dates for updating the Proposal Map will need to be altered. A copy of the revised Local Development Scheme is attached in Annex 1 to this report. |
| 3.0 | Conclusion |
| 3.1 | The revised Local Development Scheme makes amendments to the timetables for the Core Strategy and adds the information and timetable for the recently agreed Greater Manchester Joint Minerals Development Plan Document. |
| 4.0 4.1 | Recommendations The Lead Member for Planning is recommended to approve the Local Development Scheme 2009/10 – 2011/12 Revision A for submission to the Secretary of State. |

KEY COUNCIL POLICIES:

COMMUNITY IMPACT ASSESSMENT AND IMPLICATIONS:-  The Local Development Scheme is a programme management document that sets out the timetables for the production of documents.  It has no impact on equality and diversity issues.

ASSESSMENT OF RISK: Low.  The Local Development Scheme is a statutory document which we are required to produce.

SOURCE OF FUNDING:  N/A

LEGAL IMPLICATIONS Supplied by Richard Lester (Ext 2129)

There are no legal implications in the report itself. The Council has a statutory duty to produce and review its Local Development Scheme.

FINANCIAL IMPLICATIONS Supplied by Steve Bayley (Ext 2584)

There are no financial implications as the report does not propose any expenditure.

OTHER DIRECTORATES CONSULTED: None

CONTACT OFFICER: Alison Partington	TEL. NO.	3780

WARD(S) TO WHICH REPORT RELATE(S): All

Annex 1 : Local Development Scheme 2009/10 – 2011/12 Revision A