|  | ITEM NO. |
| --- | --- |

REPORT OF MANAGING DIRECTOR OF URBAN VISION PARTNERSHIP LTD

TO THE LEAD MEMBER FOR PLANNING ON MONDAY 26th September 2005

TITLE: DRAFT SCOPING REPORT FOR THE SUSTAINABILITY APPRAISAL FOR TREES AND DEVELOPMENT SUPPLEMENTARY PLANNING DOCUMENT (T&DSPD)

RECOMMENDATIONS: THAT APPROVAL be given:

- to consult on the scoping report for the sustainability appraisal that will accompany the T&DSPD

- TO THE LIST OF BODIES TO BE CONSULTED.

EXECUTIVE SUMMARY: THE REPORT SEEKS APPROVAL TO CONSULT ON THE SCOPING REPORT FOR THE SUSTAINABILITY APPRAISAL THAT WILL ACCOMPANY THE T&DSPD

BACKGROUND DOCUMENTS (Other than source material): NONE

ASSESSMENT OF RISK: LOW

SOURCE OF FUNDING: Not applicable

COMMENTS OF THE STRATEGIC DIRECTOR OF CUSTOMER AND SUPPORT SERVICES (or his representative):

- LEGAL IMPLICATIONS		Provided by: RICHARD LESTER

- FINANCIAL IMPLICATIONS	Provided by: NIGEL DICKENS

PROPERTY (if applicable): NOT APPLICABLE

CLIENT CONSULTED:	YES

HUMAN RESOURCES (if applicable): NOT APPLICABLE

CONTACT OFFICER : ANTHONY STEPHENSON 793 3767

WARD(S) TO WHICH REPORT RELATE(S): ALL

KEY COUNCIL POLICIES: UNITARY DEVELOPMENT PLAN

DETAILS

- Introduction

1.1	The Local Development Scheme (LDS) identifies the production of a Supplementary Planning Document for Trees and Development.  The purpose of the SPD is to provide clear guidance for the protection and enhancement of the City’s treescape in relation to new developments.

  - It is a statutory requirement that all such documents are accompanied by a Sustainability Appraisal that fully encompasses the requirements of the Strategic Environmental Assessment Directive.

- Trees and Development - SPD

  - The T&DSPD will be a significant material consideration in the determination of planning applications and appeals.  It will also be conducive to a transparent and efficient planning process.

  - The production of the T&DSPD will take approximately 12 months.  The key stages are set out in the table below.

| Stage | Date |
| --- | --- |
| Consultation on Scoping Report | September-November 2005 |
| Production of draft SPD and Sustainability Appraisal of preferred options | September-December 2005 |
| Statutory consultation period | February – March 2006* |
| Reports on outcomes of consultation | June – July 2006 |
| Adoption | July 2006 |

* In the interests of efficiency and effectiveness, a number of development control SPDs will all be consulted on at the same time, which is why there is a delay between producing the draft and the start of the consultation period.

- Draft Scoping Report

  - The draft SA Scoping Report identifies how the Sustainability Appraisal will be carried out. It identifies baseline information that should be collected and monitored to support preparation of the T&DSPD and suggests indicators that will test the impact of the document.  It identifies sustainability issues that should be addressed in the T&DSPD and suggests sustainability objectives.

  - The purpose of the consultation on the scoping report is to give consultees the opportunity to comment on the content of the SA at an early opportunity.  Any issues raised can then be incorporated in the preparation of the T&DSPD and supporting SA.

  - A copy of the draft scoping report is attached.  It is considered to be a sound and robust basis for consultation.

- Consultation

  - The scoping report is largely a technical document that considers the process of the Sustainability Appraisal rather than its content.  As such it is not considered appropriate for the draft scoping report to be subject of widespread consultation.  The production process for the T&DSPD involves a 6 week period of consultation in February-March 2006 when members of the public will have the opportunity to influence the contents of the T&DSPD and the Sustainability Appraisal.

  - It is a requirement that consultation on the Scoping Report is carried out with the 4 statutory consultees (English Heritage, English Nature, Countryside Agency and the Environment Agency) together with other appropriate stakeholders.  In this case it is proposed that the following bodies with key economic, social interests are also consulted:

- GONW

- North West Regional Assembly.

5.0	Conclusion

5.1	It is recommended that the draft Scoping Report for the Sustainability Appraisal that will accompany the T&DSPD be approved for consultation, and that the following bodies be consulted thereon:

- English Heritage

- English Nature

- Countryside Agency

- Environment Agency

- GONW

- NWRA

Bill Taylor

Managing Director of Urban Vision Partnership Ltd