## Sheet1
Cost | Scheme Name | Current | Cap | Paid | Start | Start | Start | Out to | Start | Finish | Paid | Forecast |  |  | Total | Comments
Code |  | Respon- | Prog | to-date | Prelim' | Consult - | Detailed | Tender | on Site | on Site | to | Spend |  |  | Spend
|  | sibility | 05/06 | in 05/06 | Design | ation | Design |  |  |  | 2005-03-01 | 05/06 | 06/07 | Beyond
1. Major Highway Schemes
D00003 | Cadishead Way, Stage 1 | DF | 75 | 1 | - | - | - | - | 1991-01-01 | 1992-03-01 | 9463 | 75 | 0 | 0 | 9538 | Scheme complete
D00004 | Cadishead Way, Stage 2 | DD | 7878 | 3433 | - | - | - | - | 2004-02-04 | 2005-09-01 | 11941 | 6966 | 912 | 0 | 19819 | Scheme complete
D00005 | Trinity Way, Stage 3 | PG | 1332 | 2901 | - | - | - | - | 2001-02-01 | 2004-11-04 | 23641 | 3719 | 0 | 0 | 27360 | Scheme complete
| Sub-Total |  | 9285 | 6335 | [6 empty] | 45045 | 10760 | 912 | 0 | 56717
2. Local Safety Schemes
D00101 | Anti-skid Surfacing Programme | SW | 100 | 0 | - | - | - | - | 2005-04-01 | 2006-03-01 | 0 | 100 | 50 | 50 | 200 | On-going programme
D00103 | Accident Investigation | AD | 20 | 16 | - | - | - | - | 2005-04-01 | 2006-03-01 | 0 | 20 | 20 | 20 | 60 | General fund for investigations/maintenance
D00104 | White Lining Programme | AD | 15 | 0 | - | - | - | - | 2005-04-01 | 2006-03-01 | 0 | 15 | 15 | 15 | 45 | On-going programme
D00105 | Road Safety Strategy | AD | 5 | 4 | - | - | - | - | 2005-04-01 | 2006-03-01 | 0 | 5 | 5 | 5 | 15 | AD to produce for 05/06
D00119 | Barton Lane Ped Improvements | SF | 50 | 0 | 2004-08-01 | 2004-09-01 | 2004-10-01 | 2005-11-01 | 2006-01-01 | 2006-03-01 | 4 | 50 | 0 | 0 | 54 | Detailed Design in Progress
D00121 | A6 High Street/ Campbell Way | MWK | 100 | 0 | - | - | 2004-07-04 | - | - | - | 0 | 1 | 111 | 0 | 112 | Not AI scheme - now unlikely to proceed
D00141 | Moorside Rd/Wardley Ind Estate Area Sch | SF | 40 | 3 | 2004-04-01 | 2005-05-01 | 2005-06-01 | 2005-11-01 | 2006-01-01 | 2006-03-01 | 20 | 80 | 0 | 0 | 100 | Detailed Design in Progress
D00142 | B5229 Monton Centre Scheme | AD | 100 | 5 | 2004-07-01 | 2005-08-01 | 2005-11-01 | 2006-02-01 | 2006-04-01 | 2006-07-01 | 12 | 10 | 90 | 0 | 112 | Fees only in 05/06 . Includes St Lighting
D00143 | Cadishead NW Area Safety Scheme | JP | 0 | 0 | - | - | - | - | 2003-12-01 | 2004-03-01 | 247 | 0 | 0 | 0 | 247 | Scheme complete
D00148 | A6 Chorley Road Route Scheme | AD | 100 | 0 | 2005-11-01 | 2006-01-01 | 2006-05-01 | 2006-08-01 | 2006-10-01 | 2007-01-01 | 4 | 2 | 100 | 0 | 106 | Scheme to investigated in 05/06.
D00161 | Trafford Road, Eccles, Speed Management | AD | 0 | 5 | - | - | 2004-05-01 | 2004-07-01 | 2004-10-04 | 2004-12-04 | 80 | 5 | 0 | 0 | 85 | Scheme complete
D00172 | Kersal Area Traffic Calming | JP | 0 | 0 | - | - | - | - | 2003-03-01 | 2004-03-01 | 64 | 0 | 0 | 0 | 64 | Scheme complete
D00173 | New Lane, Winton | SF | 0 | 7 | 2004-06-01 | 2004-07-01 | 2004-10-04 | 2005-01-05 | 2005-02-05 | 2005-06-01 | 22 | 70 | 0 | 0 | 92 | Scheme complete
D00175 | Amendments to Early T Calming Schemes | PG | 0 | 11 | 2004-07-04 | 2004-08-04 | 2004-09-04 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 14 | 8 | 0 | 0 | 22 | Includes Littleton Rd & Hilton Lane.
D00176 | Dealing with Disadvantage Initiative | AD | 80 | 5 | - | - | 2005-06-01 | 2005-07-01 | 2005-09-01 | 2005-12-01 | 0 | 50 | 0 | 0 | 50 | Up-front funding for DfT funded initiative
D00177 | Liverpool Rd, Cad, Speed Management | AD | 0 | 0 | [6 empty] | 0 | 0 | 40 | 0 | 40 | Possible scheme to follow Cad Way Stage 2
D00178 | Greenleach Lane, Worsley | SF | 30 | 21 | 2004-07-01 | 2004-08-04 | 2005-01-05 | 2005-10-01 | 2005-11-01 | 2005-12-01 | 4 | 30 | 0 | 0 | 34 | Amendments made following consultation
D00179 | Oxford Road Remedial Traffic Calming | SF | 10 | 0 | 2004-06-04 | 2004-08-04 | 2004-09-04 | 2004-12-04 | 2005-02-05 | 2005-04-05 | 62 | 80 | 0 | 0 | 142 | Scheme complete
D00180 | Langley Rd Speed Reduction Measures | AD | 0 | 9 | 2005-04-01 | 2005-05-01 | 2005-08-01 | 2005-10-01 | 2005-01-01 | 2005-02-01 | 0 | 50 | 0 | 0 | 50 | Scheme complete
D00181 | Light Oaks Primary Safer Routes | PW | 60 | 0 | 2005-04-01 | 2005-10-01 | 2005-11-01 | 2006-01-01 | 2006-03-01 | 2006-04-01 | 0 | 20 | 20 | 0 | 40 | Signs, lines & VMS
D00182 | St Georges High School Safer Routes | PW | 60 | 0 | 2005-04-01 | 2005-10-01 | 2005-11-01 | 2006-01-01 | 2006-03-01 | 2006-04-01 | 0 | 10 | 20 | 0 | 30
D00183 | Station Rd/Bolton Rd Ped'n Facilities | AD | 0 | 5 | 2005-05-01 | 2005-08-01 | 2005-10-01 | 2006-01-01 | 2006-03-01 | 2006-08-01 | 0 | 5 | 75 | 0 | 80 | Pedestrian Crossing Facilities
D00184 | Gerald Road Area Traffic Calming | SF | 0 | 2 | - | 2005-06-01 | 2005-10-01 | 2005-12-01 | 2006-01-01 | 2006-03-01 | 0 | 75 | 0 | 0 | 75 | Detailed Design in Progress
D00185 | Partington Ln/Worsley Rd Junction | SF | 0 | 2 | 2005-07-01 | 2005-08-01 | 2005-10-01 | 2005-12-01 | 2006-02-01 | 2006-04-01 | 0 | 10 | 0 | 0 | 10
D00186 | A666 / M60 J'n Cyclist Awareness | AD | 0 | 0 | 2005-07-01 | 2005-08-01 | 2006-04-01 | 2006-05-01 | 2006-06-01 | 2006-07-01 | 0 | 2 | 33 | 0 | 35 | Improvements to signing & st lighting
D00187 | Parrin Lane/Monton Fields St Lighting | SF | 0 | 0 | 2005-07-01 | 2005-08-01 | 2005-10-01 | 2006-01-01 | 2006-03-01 | 2006-04-01 | 0 | 25 | 0 | 0 | 25 | Improvements to signing & st lighting
D00189 | Motorcycle Casualty Reduction Initiative | AD | 0 | 0 | 2005-10-01 | - | 2005-11-01 | - | 2006-02-01 | 2007-03-01 | 0 | 2 | 10 | 0 | 12 | Signing Scheme - work for Depot
D00190 | Captain Fold Lane - Dealing with Disadvantage | AD | 0 | 0 | - | - | 2005-09-01 | 2005-10-01 | 2005-10-01 | 2005-11-01 | 0 | 130 | 0 | 0 | 130 | Scheme from D00176 - scheme on site
| Sub-Total |  | 770 | 95 | [6 empty] | 533 | 855 | 589 | 90 | 2067
3. Bridge Assessment and Strengthening
D00500 | Bridge Inspections and Assessments | MG | 0 | 0 | - | - | - | - | 2005-04-01 | 2006-03-01 | 0 | 0 | 0 | 0 | 0 | On-going Programme
D00501 | Bridges general | MG | 10 | 1 | - | - | - | - | 2005-04-01 | 2006-03-01 | 0 | 10 | 10 | 10 | 30 | Various Small Works
D00503 | Subways | MG | 5 | 0 | - | - | - | - | 2005-04-01 | 2006-03-01 | 0 | 5 | 5 | 5 | 15 | On-going Programme
D00510 | Network Rail Bridges | MG | 0 | 0 | 2005-08-01 | - | 2005-10-01 | - | - | - | 0 | 90 | 0 | 0 | 90 | Design work only in 05/06
D00512 | Eccles Old Road Underpass | MG | 5 | 0 | 2003-09-03 | 2003-09-03 | 2003-09-03 | 2003-12-03 | 2004-01-01 | 2004-04-04 | 80 | 5 | 0 | 0 | 85 | Scheme complete
D00524 | Pendleton Roundabout Parapets Ph1 | MG | 0 | 13 | - | - | - | - | 2003-12-01 | 2004-05-01 | 273 | 13 | 0 | 0 | 286 | Scheme complete
D00525 | Railtrack Incursion Works | MG | 75 | 4 | - | - | - | - | 2003-10-01 | 2005-03-01 | 158 | 75 | 0 | 0 | 233 | Scheme on site
D00527 | Culvert Safety Improvement Programme | IT | 20 | 0 | - | - | - | - | 2004-09-01 | 2006-03-01 | 4 | 20 | 20 | 16 | 60 | Managed by Ian Thew
D00528 | Wallness Bridge | MG | 0 | 1 | 2003-12-03 | 2003-12-03 | 2003-12-03 | 2004-01-04 | 2004-05-01 | 2004-06-01 | 67 | 2 | 0 | 0 | 69 | Scheme complete
D00529 | West Egerton Street Bridge | MG | 0 | 0 | - | - |  |  | 2004-02-01 | 2004-07-01 | 60 | 0 | 0 | 0 | 60 | Scheme complete
D00530 | Woden Street Footbridge | MG | 0 | 0 | 2004-02-04 | 2004-02-04 | 2004-02-04 | 2004-05-04 | 2004-07-04 | 2004-10-04 | 149 | 0 | 0 | 0 | 149 | Scheme complete
D00531 | Eccles Road Footbridge Painting | MG | 0 | 0 | 2004-04-04 | 2004-04-04 | 2004-04-04 | 2004-05-04 | 2004-07-04 | 2004-10-04 | 50 | 2 | 0 | 0 | 52 | Scheme complete
D00532 | Hough Lane Footbridge | MG | 0 | 4 | 2004-05-04 | 2004-05-04 | 2004-05-04 | 2004-07-04 | 2004-08-04 | 2004-10-04 | 154 | 5 | 0 | 0 | 159 | Scheme complete
D00533 | Stott Lane Railway Bridge | MG | 75 | 0 | 2004-08-04 | 2004-08-04 | 2004-08-04 | 2004-11-04 | 2005-04-05 | 2005-08-05 | 0 | 0 | 75 | 5 | 80 | Detailed design in Progress
D00534 | Heywood Way Subway Infill | MG | 3 | 0 | [6 empty] | 0 | 3 | 135 | 0 | 138 | Scheme awaiting decisions re Precinct | bar: 2005-07-01 to 2006-04-01
D00535 | Pendleton Roundabout Parapets Ph2 | MG | 0 | 9 | 2004-07-01 | 2004-07-01 | 2004-07-01 | 2004-08-01 | 2005-01-05 | 2005-03-05 | 232 | 9 | 0 | 0 | 241 | Scheme complete
D00536 | East Ordsall Lane Canal Bridge | MG | 100 | 23 | 2004-09-01 | 2004-09-01 | 2005-02-01 | 2005-08-01 | 2005-12-01 | 2006-10-01 | 22 | 100 | 0 | 0 | 122 | Part of canal re-opening works.
D00537 | Eccles Old Road Subway Drainage | MG | 25 | 0 | 2005-09-01 | 2005-09-01 | 2005-10-01 | 2005-11-01 | 2006-01-01 | 2006-03-01 | 0 | 25 | 0 | 0 | 25 | Detailed design in Progress
D00538 | Swinton Subway (Moorside Ramp) | MG | 55 | 0 | 2005-09-01 | 2005-09-01 | 2005-09-01 | 2005-11-01 | 2006-01-01 | 2006-03-01 | 0 | 55 | 0 | 0 | 55 | Detailed design in Progress
D00539 | Little Hulton Station Bridge | MG | 75 | 0 | 2005-08-01 | 2005-08-01 | 2005-09-01 | 2005-11-01 | 2006-01-01 | 2006-03-01 | 0 | 115 | 0 | 0 | 115 | Detailed design in Progress
D00540 | West/East Bridges, Pendleton Roundabout | MG | 50 | 3 | 2005-06-01 | 2005-06-01 | 2005-06-01 | 2005-10-01 | 2006-02-01 | 2006-04-01 | 0 | 0 | 0 | 0 | 0 | Scheme now combined with D00543
D00541 | Monton Canal Bridge | MG | 100 | 40 | 2005-01-01 | 2005-02-01 | 2005-03-01 | 2005-07-01 | 2005-08-01 | 2005-10-01 | 0 | 100 | 0 | 0 | 100 | Scheme on site
D00542 | Mariners Canal Central Footbridge | MG | 25 | 30 | 2005-01-01 | 2005-01-01 | 2005-02-01 | 2005-04-01 | 2005-05-01 | 2005-07-01 | 0 | 30 | 0 | 0 | 30 | Scheme complete
D00543 | Pendleton Roundabout Retaining Walls | MG | 95 | 11 | 2005-08-01 | 2005-08-01 | 2005-08-01 | 2005-10-01 | 2006-02-01 | 2006-04-01 | 0 | 150 | 50 | 0 | 200 | Joint scheme with D00540
D00544 | Centenary Bridge Abutments | MG | 0 | 7 | 2004-11-01 | 2004-11-01 | 2004-12-01 | 2005-01-01 | 2005-03-01 | 2005-03-01 | 0 | 26 | 0 | 0 | 26 | Scheme complete
| Sub-Total |  | 718 | 146 | [6 empty] | 1249 | 840 | 295 | 15 | 2399
4. Principal Road Structural Maintenance
D00601 | A57 Liverpool Road, Cadishead | - | 0 | 1 | [6 empty] | 22 | 1 | 300 | 0 | 323 | To commence after Cadishead Way Scheme | bar: 2005-01-01 to 2005-02-01
(New Moss Road - Fir Street)
D00605 | BVPI Surveys | SW | 0 | 36 | - | - | - | - | 2003-08-01 | 2003-12-01 | 101 | 60 | 0 | 0 | 161
D00606 | A57 Liverpool Rd | - | 0 | 0 | [6 empty] | 8 | 0 | 200 | 0 | 208 | Scheme postponed | bar: 2005-01-01 to 2005-07-01
(Boysnope - Barton Moss Road)
D00608 | Principal Road Maintenance - General | - | 20 | 8 | - | - | - | - | 2004-04-01 | 2005-03-01 | 18 | 20 | 20 | 20 | 78 | Payment of retentions, etc
D00610 | A575 Walkden Road | DD | 0 | 1 | - | - | - | - | 2004-01-01 | 2004-06-01 | 175 | 8 | 0 | 0 | 183 | Scheme complete
(Manchester Road - Park Road)
D00614 | Structural Maintenance of Minor Roads | SW | 0 | 16 | - | - | - | - | 2003-10-01 | 2005-03-01 | 763 | 16 | 0 | 0 | 779
D00617 | A5066 Adelphi Street & Silk Street | DD | 5 | 7 | - | - | 2004-07-01 | 2004-09-01 | 2004-11-01 | 2005-03-05 | 298 | 7 | 0 | 0 | 305 | Scheme complete
D00618 | A5066 Oldfield Road | NW | 7 | 26 | - | - | 2004-08-01 | 2004-10-01 | 2005-01-05 | 2005-03-01 | 113 | 26 | 0 | 0 | 139 | Scheme complete
(Ordsall Lane - Regent Road)
D00619 | A5066 Oldfield Road | DD | 5 | 10 | - | - | 2004-10-01 | 2004-12-01 | 2005-01-01 | 2205-03-01 | 153 | 10 | 0 | 0 | 163 | Scheme complete
(Regent Road - Crescent)
D00620 | A575 Cleggs Lane | DD | 590 | 50 | - | - | 2004-12-04 | 2005-03-01 | 2005-08-01 | 2005-11-01 | 15 | 590 | 0 | 0 | 605 | Scheme on site
(A6 - Bolton Boundary)
D00629 | Street Lighting Inventory Work | SC | 60 | 0 | [6 empty] | 0 | 60 | 0 | 0 | 60 | Detailed inventory required by DfT | bar: 2005-01-01 to 2005-10-01
D00630 | Langworthy Road | DD | 240 | 12 | 2005-04-01 | - | 2005-05-01 | 2005-08-01 | 2005-10-01 | 2006-01-01 | 0 | 275 | 0 | 0 | 275 | Scheme on site
(Liverpool Street - Eccles New Road)
D00631 | Albion Way (Broad St - Regent Rd) | DD | 0 | 1 | 2006-05-01 | - | 2006-06-01 | 2006-09-01 | 2006-11-01 | 2007-02-01 | 0 | 5 | 550 | 0 | 555 | Scheme on hold
D00632 | Worsley Road | DD | 0 | 6 | 2005-06-01 | - | 2005-07-01 | 2005-10-01 | 2005-01-01 | 2006-03-01 | 0 | 470 | 0 | 0 | 470
(East Lancs Rd - Ringlow Park Rd)
D00633 | A666 Manchester Road | DD | 0 | 15 | 2005-05-01 | - | 2005-06-01 | 2005-11-01 | 2005-12-01 | 2006-02-01 | 0 | 340 | 10 | 0 | 350 | Out to tender
(Clifton House Road - Manley Avenue)
D00634 | Cadishead Way Stage 1 Repairs | PRG | 0 | 17 | - | - | - | - | 2005-08-01 | 2005-09-01 | 0 | 242 | 250 | 0 | 492 | Scheme complete
D00635 | Street Lighting in support of H I Prog | SC | 0 | 0 | - | - | - | - | 2005-09-01 | 2006-03-01 | 0 | 100 | 0 | 0 | 100
| Sub-total |  | 927 | 206 | [6 empty] | 1644 | 2230 | 1030 | 20 | 4924
5. Schemes To Assist Public Transport
D00703 | A56 Quality Bus Corridor | DD | 16 | 20 | - | - | - | - | 2003-11-01 | 2005-01-05 | 648 | 21 | 0 | 0 | 669 | Scheme complete
D00708 | Central Station Study | DF | 0 | 8 | [6 empty] | 31 | 8 | 0 | 0 | 39 | Possible further contribution needed | bar: 2005-01-01 to 2005-10-01
D00709 | A57 Irlam Bus Stop Improvements | DF | 0 | 4 | - | - | 2005-09-01 | 2005-11-01 | 2006-01-01 | 2007-04-01 | 0 | 60 | 60 | 0 | 120 | QBC costs to be reclaimed from GMPTE
(Detailed design in progress)
| Sub-total |  | 16 | 32 | [6 empty] | 679 | 89 | 60 | 0 | 828
6. Schemes To Assist Cycling
D00803 | Barton Cycling Facilities | TL | 280 | 276 | 2004-04-01 | 2004-06-01 | 2004-07-01 | 2005-01-05 | 2005-03-05 | 2005-05-05 | 67 | 363 | 0 | 0 | 430 | Scheme complete
D00805 | Cycle Parking Facilities | PC | 20 | 1 | 2004-04-01 | 2004-06-01 | 2004-07-01 | 2004-08-01 | 2004-09-01 | 2005-03-01 | 8 | 10 | 10 | 10 | 38 | Ongoing programme
D00806 | Sustrans Routes | PG | 200 | 27 | 2004-05-01 | 2004-07-01 | 2005-04-01 | 2005-06-01 | 2005-07-01 | 2005-09-01 | 5 | 72 | 150 | 150 | 377 | Scheme on site
D00807 | Cycling Projects Grant Fund | DF | 50 | 1 | 2004-08-01 | 2004-09-01 | 2004-10-01 | 2005-01-05 | 2005-02-05 | 2005-03-01 | 16 | 25 | 50 | 50 | 141 | Bike Stations Initiative
D00808 | Tyldesley Loopline Surfacing Improv'ts | NO | 0 | 0 | 2005-01-05 | 2005-02-05 | 2005-02-05 | 2005-03-05 | 2005-03-05 | 2005-05-05 | 0 | 120 | 0 | 0 | 120 | Cost £160k, Sustrans to contribute £40k
D00809 | Cycle Parking Facilities at Schools | SG | 75 | 0 | [6 empty] | 0 | 75 | 75 | 75 | 225 | Contributory funding to schools | bar: 2004-08-01 to 2005-03-01
D00810 | Irwell Walk, Charlestown, New Deal Cont' | DF | 15 | 0 | [6 empty] | 0 | 15 | 0 | 0 | 15 | Contributory funding to Groundwork | bar: 2004-08-01 to 2005-03-01
D00811 | A580 East Lancs Rd (To Wigan Boundary) | PC | 10 | 2 | 2005-05-01 | - | 2005-07-01 | 2005-08-01 | 2005-10-01 | 2005-11-01 | 0 | 10 | 0 | 0 | 10 | Completion of Shared use of footways
| Bridgewater Way | DF | 0 | 0 | [6 empty] | 0 | 0 | 75 | 0 | 75 | Contribution to project in 2006/07. | bar: 2004-08-01 to 2005-03-01
| Sub-total |  | 650 | 307 | [6 empty] | 96 | 690 | 360 | 285 | 1431
7. Other Minor Works
D00901 | GM Local Transport Plan | DF | 40 | 4 | - | - | - | - | 1999-04-01 | 2005-03-01 | 115 | 40 | 40 | 40 | 235 | AGMA contribution
D00902 | Salford's Green Transport Plan | SG | 25 | 0 | 2004-07-01 | 2004-09-01 | 2004-10-01 | 2004-12-01 | 2005-01-01 | 2005-03-01 | 45 | 30 | 0 | 0 | 75 | Cycle parking shelters in 04/05
D00903 | M60/ PRN Signing | NA | 0 | 1 | - | - | - | - | 1998-04-01 | 2005-03-01 | 144 | 1 | 0 | 0 | 145 | Scheme complete
D00909 | AGMA Countywide Advertising | DI | 0 | 0 | - | - | - | - | 2000-04-01 | 2005-03-01 | 21 | 5 | 0 | 0 | 26 | On-going contribution to AGMA initiatives
D00912 | Disabled Facilities at Pedestrian Crossings | JH | 150 | 56 | - | - | - | - | 2003-04-01 | 2005-03-01 | 477 | 150 | 150 | 150 | 927 | Ongoing programme - needs identifying
D00918 | Chapel St Pedestrian Route Improve'ts | JP | 0 | -8 | - | - | - | 2004-06-01 | 2004-08-01 | 2004-10-01 | 78 | 0 | 0 | 0 | 78 | Scheme complete
D00923 | Little Moss Lane Works | DAD | 50 | 1 | - | - | - | - | 2006-01-01 | 2006-03-01 | 365 | 50 | 0 | 0 | 415 | Complete (apart from Worsley St)
D00924 | Miscellaneous SRTS Works | SG | 15 | 0 | - | - | - | - | 2003-08-01 | 2005-03-01 | 2 | 0 | 10 | 10 | 22 | Linked with School Travel Plans
D00925 | GMTU Non-core Modelling Work | JH | 10 | 0 | - | - | - | - | 2003-06-01 | 2005-03-01 | 9 | 10 | 0 | 0 | 19 | Various assessment work by GMTU
D00926 | Public Rights of Way Signing | NO/ST | 30 | 0 | 2004-07-01 | 2004-08-01 | 2004-10-01 | 2004-12-01 | 2005-01-01 | 2006-03-01 | 5 | 30 | 15 | 0 | 50 | Work required under CROW Act
D00927 | Public Rights of Way Improvements | NO/ST | 250 | 15 | 2004-06-01 | 2004-07-01 | 2004-08-01 | 2004-10-01 | 2004-12-01 | 2005-03-01 | 3 | 15 | 250 | 250 | 518 | 05/06 spend now coded as D00938
D00928 | Barton Rd/Barton Ln J'n Improvement | JP | 15 | 29 | 2004-06-01 | 2004-07-01 | 2004-08-01 | 2004-10-01 | 2005-01-05 | 2005-03-05 | 210 | 29 | 0 | 0 | 239 | Scheme complete
D00929 | Liverpool Rd, Cadishead, Town Centre | DF | 10 | 0 | 2004-10-04 | 2005-01-05 | 2006-04-01 | 2006-09-01 | 2006-11-01 | 2007-05-01 | 0 | 10 | 250 | 350 | 610 | Consultation only during 2005/06
D00930 | Oaklands Road | PG | 0 | 2 | 2006-11-01: 2004-10-04; 2007-05-01: 2004-12-04 | 22 | 2 | 0 | 0 | 24 | Scheme complete - total cost £73k (New Deal)
D00931 | Chapel St/New Bailey St Ped Facilities | MWK | 0 | 38 | 2004-09-04 | 2004-10-04 | 2004-10-05 | 2004-12-05 | 2005-02-05 | 2005-04-05 | 0 | 40 | 0 | 0 | 40 | All-red phase requiring new signal equipment
D00932 | Station Road Puffin Crossing | PC | 25 | 19 | 2004-06-04 | 2004-09-04 | 2004-10-04 | 2004-12-04 | 2005-08-01 | 2005-09-01 | 1 | 40 | 0 | 0 | 41 | Scheme on site
D00933 | Langworthy Road Parking Layby | OA | 0 | 0 | - | - | - | - | 2005-01-05 | 2005-03-05 | 10 | 0 | 0 | 0 | 10 | Complete
D00934 | Dropped Kerbs & Tactile Paving Programme | NO | 100 | 3 | - | - | - | - | 2005-12-01 | 2006-03-01 | 0 | 100 | 100 | 100 | 300 | Ph1 Station Rd/Partington Lane
D00935 | A6 Chorley Rd / Moorside Rd Ped' Facilities | MWK | 50 | 0 | [6 empty] | 0 | 50 | 0 | 0 | 50 | Ph3 Newearth Rd
D00936 | Chapel Street Traffic Management | DF | 100 | 0 | 2004-04-01 | 2005-05-01 | 2006-08-01 | 2006-11-01 | 2007-01-01 | 2007-12-01 | 0 | 0 | 0 | 0 | 0 | Awaiting feasibility assessment
D00937 | Major Scheme Feasibility Studies | DF | 100 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | No longer pursuing in 05/06. | bar: 2004-04-01 to 2007-12-01
D00938 | Roe Green Loopline - PROW | NO | 0 | 0 | - | - | 2005-10-01 | 2005-12-01 | 2006-02-01 | 2006-05-01 | 0 | 145 | 155 | 0 | 300 | Detailed design in progress
(Chedsworth to Hilton Lane)
D00939 | Fairhills Rd Puffin Crossing Contribution | PRG | 0 | 0 | - | - | - | - | 2005-09-01 | 2005-10-01 | 0 | 25 | 0 | 0 | 25 | Scheme on site
| Sub-total |  | 970 | 160 | [6 empty] | 1507 | 772 | 970 | 900 | 4149
| GRAND TOTAL |  | 13336 | 7281 | [6 empty] | 50753 | 16236 | 4216 | 1310 | 72515 | Minor works allocation is £4.126m for 2005/06