## Sheet1
Development Services Capital Monitoring 2005/06
September | [7 empty] | Funding | [18 empty] | Comments
Project | Project | Capital |  |  |  | Actual
| Officer | Programme | Slippage | Adjustments | Total | Spend |  | Unsupported | Capital | RCCO | Grant | [10 empty] | Section 106 | Insurance | Other | Total
|  | 2005/06 |  |  |  | September |  | Borrowing | Receipts |  | NWDA | ERDF | SRB | NRF | HMRF | NDC | Surestart | LIFT | DfT | PDG | Fairshares
|  | £000 | £000 | £000 | £000 | £000 | Comments | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000 | £000
Manchester Bolton Bury Canal | D.Evans | 2391 | 38 | -1724 | 705 | 62.3 |  | 667 | 38 | [15 empty] | 705 |  | Brittish Waterways Scheme - USB until s106 monies come in - see s/sheet
Liverpool Road Eccles | P.Garrett/RS | 460 | 0 | -216 | 244 | 0 |  |  | 80 |  |  |  | 64 | 100 | [10 empty] | 244 |  | Move to CEX?
Detroit Bridge | P.Garrett | 500 | 75 | 20 | 595 | 379 |  |  | 345 | [12 empty] | 250 |  |  | 595 |  | £95 from F'path Works slippage
City Academy Access Road | P.Garrett | 800 | 0 | 0 | 800 | 9 |  |  | 700 | [14 empty] | 100 | 800 |  | £100K to be determined
Investment in Highways | J.Fergie | 6810 | 83 | -1893 | 5000 | 1104.3 |  | 5000 | [16 empty] | 5000
Eccles Town Centre (slippage from 04/05) | P.Holden | 589 | 0 | 0 | 589 | 6.9 |  |  | 589 | [15 empty] | 589
Chapel Street/URC: - | P.Baker
Economic Development: -
Management of Crescent Police Station |  | 15 | 0 | 0 | 15 | 0 |  |  | 27 | [15 empty] | 27 |  | £12k from below
Business Improvement Grants |  | 40 | 12 | 0 | 52 | 0 |  |  | 40 | [15 empty] | 40
Salford Innovation Park |  | 20 | 0 | 0 | 20 | 0 |  |  | 20 | [15 empty] | 20
Creative Industries Development Services (CIDS) |  | 22 | 0 | 0 | 22 | 0 |  |  | 22 | [15 empty] | 22
Chapel St Business Group |  | 33 | 0 | 0 | 33 | 0 |  |  | 33 | [15 empty] | 33
Programme management contribution |  | 20 | 0 | 0 | 20 | 0 |  |  | 20 | [15 empty] | 20
Cultural Quarter: -
Cultural Development Grants |  | 25 | 0 | 0 | 25 | 0 |  |  | 25 | [15 empty] | 25
Church lighting and DDA works |  | 40 | 0 | 0 | 40 | 0 |  |  | 40 | [15 empty] | 40
Salford Museum contribn to improvement works |  | 5 | 0 | 0 | 5 | 0 |  |  | 5 | [15 empty] | 5
Public Realm Improvements: -
Refurb works Bexley Square |  | 21 | 0 | 0 | 21 | 0 | Balance - cost not known |  | 21 | [15 empty] | 21
Health and Safety works Firestation Square |  | 29 | 0 | 0 | 29 | 0 |  |  | 29 | [15 empty] | 29
Chapel Street Walking Plan: -
CCTV Ph2 |  | 31 | 0 | 0 | 31 | 0 |  |  | 31 | [15 empty] | 31
Signage to Trinity Link (Uni Campus to City Centre) |  | 19 | 0 | 0 | 19 | 0 | Balance - cost not known |  | 19 | [15 empty] | 19
Contribution to URC Business Plan |  | 180 | 0 | 0 | 180 | 0 |  |  | 180 | [15 empty] | 180
Chapel Street/URC (04/05 Slippage) |  | 167 | 0 | 0 | 167 | 0 | £107K CCTV, £60K Casket Works (ED) |  | 167 | [15 empty] | 167 |  | £12k slippage to Crescent Police Station
Chapel St. Sub-Total |  | 667 | 12 | 0 | 679 | 0 |  | 0 | 679 | 0 | 0 | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  | 0 | 679
Ordsall Neighbourhood Offices | S.Durbar | 277 | 118 | 0 | 395 | 0.48 |  |  | 172 | 34 | [6 empty] | 174 | [5 empty] | 15 |  | 395
LIVIA Community Engagement Programme (CCC) | T.Jones | 100 | 3 | 0 | 103 | 46.4 | £125K 06/07 |  |  |  | 103 | [13 empty] | 103
Newlands (LIVIA) | T.Jones | 100 | 0 | 0 | 100 | 1.2 | £100K to support CCC + N'lands |  | 100 | [15 empty] | 100
Disabled Access Improvements | A.Hamer | 250 | 89 | 0 | 339 | 75 |  |  | 339 | [15 empty] | 339
Langworthy Area Traffic Calming | A.Devine | 100 | 0 | 136.5 | 236.5 | 0 | [12 empty] | 236.5 | [5 empty] | 236.5
Frederick Rd/Camp St Broughton - Junction Improvement | A.Devine | 0 | 0 | 52.7 | 52.7 | 0 | [12 empty] | 52.7 | [5 empty] | 52.7
Advanced Fees (see below) |  | 100 | 0 | 0 | 100 | 80.2 |  |  | 100 | [15 empty] | 100
Emerson House (SS?) |  | 0 | 100 | 0 | 100 | 18 |  |  | 20 | [8 empty] | 80 | [6 empty] | 100
Improvement Works Swinton Civic Centre |  | 0 | 62 | 0 | 62 | 0 |  |  | 10 | 7 | [9 empty] | 45 |  |  |  |  | 62
Disposal costs |  | 0 | 22 | 0 | 22 | 58.5 |  |  | 22 | [15 empty] | 22 |  | Disposal costs netted off receipt
Former Police Station Stanwell Rd |  | 0 | 735 | 0 | 735 | 0 | [17 empty] | 735 | 735 |  | £735k Cap Rcpts or USB
Higher Broughton Community Hub |  | 0 | 445 | 0 | 445 | 7 | [17 empty] | 445 | 445 |  | £445 Cap Rcpts or USB
Demolition Newcroft High School |  | 0 | 58 | 0 | 58 | 57.2 |  |  | 58 | [15 empty] | 58
NWDA Headroom Projects |  | 0 | 0 | 0 | 0 | 7.2 | [18 empty] | 0 |  | No funding identified
Salford Shopping Food Retail Development |  | 0 | 0 | 0 | 0 | 72.6 | [18 empty] | 0
Salford Methodist Church |  | 0 | 0 | 0 | 0 | 65.4 | [18 empty] | 0
Hulme Street Nursery |  | 0 | 0 | 300 | 300 | 0 |  |  | 300 | [15 empty] | 300 |  | Poss devel land back of Crescent - Nursery comp purch?
Land at Meadow Rd/ Adelphi St | R Wynne | 0 | 0 | 2800 | 2800 | 20.6 |  |  | 2800 | [15 empty] | 2800
Civic Centre Reception Refurb. |  | 0 | 0 | 45 | 45 | 48.5 |  |  | 45 | [15 empty] | 45
Office Moves |  | 0 | 0 | 717 | 717 | 2.2 |  |  | 717 | [15 empty] | 717
Turnpike Auditorium |  | 0 | 0 | 191 | 191 | 0 |  |  | 191 | [15 empty] | 191
04/05 Slippage (not identified above): -
LIVIA (02/03 programme?) |  |  | 69 | 0 | 69 | 0 |  |  | 6 |  | 52 | [12 empty] | 11 | 69 |  | £11K Biffa Waste
NWDA Tatton Park |  |  | 26 | 0 | 26 | 0 |  |  |  |  | 26 | [13 empty] | 26 |  | Didn't spend all of grant
Trinity Park |  |  | 70 | 0 | 70 | 0 |  |  | 38 | [5 empty] | 20 | [6 empty] | 12 |  |  | 70
Oakwood |  |  | 9 | 0 | 9 | 0 | [15 empty] | 9 |  |  | 9
Eccles Town Hall Auditorium |  |  | 4 | 0 | 4 | 0 |  |  | 4 | [15 empty] | 4
Countryside Programme |  |  | 10 | 0 | 10 | 0 |  |  | 10 | [15 empty] | 10
Barton Strategic Employment Site |  |  | 75 | 0 | 75 | 0 |  |  | 75 | [15 empty] | 75
Conserving and developing Ordsall Hall |  |  | 18 | 130 | 148 | 48.7 |  |  | 139 | 9 | [14 empty] | 148
SRB |  |  | 1 | 0 | 1 | 0.6 |  |  | 1 | [15 empty] | 1 |  | ???
Quays Maintenance Office Move |  |  | 3 | 0 | 3 | 3.5 |  |  | 3 | [15 empty] | 3
Footpath Works |  |  | 279 | -95 | 184 | 1 |  |  | 184 | [15 empty] | 184 |  | £95k to Detroit Bridge
Relocation TIC |  |  | 1 | 0 | 1 | 0 |  |  | 1 | [15 empty] | 1 |  | ???
Relocation TIC
New Deal (from CEX): - |  |  | 0 | 0 | 0 | 0 | [18 empty] | 0
Pendleton Church Area Study |  |  | 0 | 0 | 0 | 123.1 | £75k Cromwell Rd public art | [17 empty] | 0
Highway & Community Safety |  |  | 30 | 0 | 30 | 4.4 | [9 empty] | 30 | [8 empty] | 30
Minor Works |  |  | 10 | 0 | 10 | 1 | [9 empty] | 10 | [8 empty] | 10
Physical Design Strategy |  |  | 0 | 0 | 0 | 0.8 | [18 empty] | 0
Mini Bus |  |  | 6 | 0 | 6 | 0.3 | [9 empty] | 6 | [8 empty] | 6
TOTAL |  | 13144 | 2451 | 464.2 | 16059.2 | 2305.38 |  | 5667 | 7766 | 50 | 181 | 0 | 64 | 100 | 20 | 46 | 174 | 80 | 289.2 | 45 | 0 | 271 | 15 | 1291 | 16059.2 | 16059.2
Note on F12: from H'ways slippage
Note on F17: from Chapel St/URC 04/05 slippage
Note on G76: detroit bridge
Note on F18: from Chapel St/URC 04/05 slippage